## Task_Export_Table
ID | Unique_ID | Active | Task Mode | Task_Name | Duration | Type | Outline_Level | Baseline_Duration | Predecessors | Start_Date | Finish_Date | Early_Start | Early_Finish | Late_Start | Late_Finish | Free_Slack | Total_Slack | Leveling_Delay | Percent_Complete | Actual_Start | Actual_Finish | Baseline_Start | Baseline_Finish | Constraint_Type | Constraint_Date | Stop | Resume | Created | Scheduled_Work | Baseline_Work | Actual_Work | Cost | Fixed_Cost | Baseline_Cost | Actual_Cost | Remaining_Cost | WBS | Priority | Milestone | Summary | Rollup | Text1 | Text2 | Text3 | Text4 | Text5 | Text6 | Text7 | Text8 | Text9 | Text10 | Cost1 | Cost2 | Cost3 | Duration1 | Duration2 | Duration3 | Flag1 | Flag2 | Flag3 | Flag4 | Flag5 | Flag6 | Flag7 | Flag8 | Flag9 | Flag10 | Marked | Number1 | Number2 | Number3 | Number4 | Number5 | Subproject_File
0 | 0 | Yes | Auto Scheduled | NO.43-45 BEERWAH PDE, BEERWAH | 873 d | Fixed Duration | 0 | 847d |  | 1 May 2023 8:00 AM | 9 November 2026 5:00 PM | Mon 1/05/23 | Mon 9/11/26 | Mon 1/05/23 | Mon 9/11/26 | 0d | 0d | 0ed | 0.25 | Mon 1/05/23 | NA | 1 May 2023 8:00 AM | 1 October 2026 5:00 PM | As Soon As Possible | NA | Mon 1/05/23 | Mon 1/05/23 | Mon 23/11/20 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 500 | No | Yes | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
1 | 3918 | Yes | Auto Scheduled | KEY PROJECT MILESTONES | 873 d | Fixed Duration | 1 | 847d |  | 1 May 2023 8:00 AM | 9 November 2026 5:00 PM | Mon 1/05/23 | Mon 9/11/26 | Mon 1/05/23 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | Mon 1/05/23 | NA | 1 May 2023 8:00 AM | 1 October 2026 5:00 PM | As Soon As Possible | NA | Mon 1/05/23 | Mon 1/05/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
2 | 3920 | Yes | Auto Scheduled | Building Approval #01 - Approved | 0 d | Fixed Duration | 2 | 0d | 37 | 1 March 2024 8:00 AM | 1 March 2024 8:00 AM | Fri 1/03/24 | Fri 1/03/24 | Fri 1/03/24 | Fri 1/03/24 | 0d | 0d | 0ed | 1 | Fri 1/03/24 | Fri 1/03/24 | 1 March 2024 5:00 PM | 1 March 2024 5:00 PM | As Soon As Possible | NA | Fri 1/03/24 | Fri 1/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.1 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
3 | 4733 | Yes | Auto Scheduled | Building Approval #01 - Required | 0 d | Fixed Duration | 2 | 0d | 123 | 11 December 2024 8:00 AM | 11 December 2024 8:00 AM | Wed 11/12/24 | Wed 11/12/24 | Wed 11/12/24 | Wed 11/12/24 | 0d | 0d | 0ed | 1 | Wed 11/12/24 | Wed 11/12/24 | 11 December 2024 8:00 AM | 11 December 2024 8:00 AM | As Soon As Possible | NA | Wed 11/12/24 | Wed 11/12/24 | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.2 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
4 | 3921 | Yes | Auto Scheduled | Building Approval #02 - Approved | 0 d | Fixed Duration | 2 | 0d | 40 | 9 April 2024 8:00 AM | 9 April 2024 8:00 AM | Tue 9/04/24 | Tue 9/04/24 | Tue 9/04/24 | Tue 9/04/24 | 0d | 0d | 0ed | 1 | Tue 9/04/24 | Tue 9/04/24 | 9 April 2024 5:00 PM | 9 April 2024 5:00 PM | As Soon As Possible | NA | Tue 9/04/24 | Tue 9/04/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.3 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
5 | 4844 | Yes | Auto Scheduled | Building Approval #02 - Required | 0 d | Fixed Duration | 2 | 0d | 215 | 4 March 2025 8:00 AM | 4 March 2025 8:00 AM | Tue 4/03/25 | Tue 4/03/25 | Tue 4/03/25 | Tue 4/03/25 | 0d | 0d | 0ed | 1 | Tue 4/03/25 | Tue 4/03/25 | 4 March 2025 5:00 PM | 4 March 2025 5:00 PM | As Soon As Possible | NA | Tue 4/03/25 | Tue 4/03/25 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.4 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
6 | 4880 | Yes | Auto Scheduled | Development Services Agreement - Effective Date | 0 d | Fixed Duration | 2 | 0d | 85 | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.5 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
7 | 4881 | Yes | Auto Scheduled | Subcontract Engagement, Procurement & Mobilsation | 0 d | Fixed Duration | 2 | 0d |  | 1 May 2023 8:00 AM | 1 May 2023 5:00 PM | Mon 1/05/23 | Mon 1/05/23 | Mon 1/05/23 | Mon 1/05/23 | 0d | 0d | 0ed | 1 | Mon 1/05/23 | Mon 1/05/23 | 1 May 2023 8:00 AM | 1 May 2023 8:00 AM | As Soon As Possible | NA | Mon 1/05/23 | Mon 1/05/23 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.6 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
8 | 4728 | Yes | Auto Scheduled | Commence On Site Works | 0 d | Fixed Duration | 2 | 0d | 124SS | 11 December 2024 8:00 AM | 11 December 2024 8:00 AM | Wed 11/12/24 | Wed 11/12/24 | Wed 11/12/24 | Wed 11/12/24 | 0d | 0d | 0ed | 1 | Wed 11/12/24 | Wed 11/12/24 | 11 December 2024 8:00 AM | 11 December 2024 8:00 AM | As Soon As Possible | NA | Wed 11/12/24 | Wed 11/12/24 | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.7 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
9 | 4730 | Yes | Auto Scheduled | Structure Complete | 0 d | Fixed Duration | 2 | 0d | 338 | 14 January 2026 5:00 PM | 14 January 2026 5:00 PM | Wed 14/01/26 | Wed 14/01/26 | Mon 9/11/26 | Mon 9/11/26 | 207d | 207d | 0ed | 0 | NA | NA | 1 December 2025 5:00 PM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.8 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
10 | 4731 | Yes | Auto Scheduled | All Buildings Water Tight | 0 d | Fixed Duration | 2 | 0d | 401 | 4 February 2026 5:00 PM | 4 February 2026 5:00 PM | Wed 4/02/26 | Wed 4/02/26 | Mon 9/11/26 | Mon 9/11/26 | 193d | 193d | 0ed | 0 | NA | NA | 19 December 2025 5:00 PM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.9 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
11 | 4732 | Yes | Auto Scheduled | External Façade Finishes Complete | 0 d | Fixed Duration | 2 | 0d | 459 | 10 March 2026 5:00 PM | 10 March 2026 5:00 PM | Tue 10/03/26 | Tue 10/03/26 | Mon 9/11/26 | Mon 9/11/26 | 169d | 169d | 0ed | 0 | NA | NA | 2 February 2026 5:00 PM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.10 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
12 | 3922 | Yes | Auto Scheduled | Scaffold Removed from Site | 0 d | Fixed Duration | 2 | 0d | 473 | 21 April 2026 5:00 PM | 21 April 2026 5:00 PM | Tue 21/04/26 | Tue 21/04/26 | Mon 9/11/26 | Mon 9/11/26 | 141d | 141d | 0ed | 0 | NA | NA | 12 March 2026 5:00 PM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.11 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
13 | 4847 | Yes | Auto Scheduled | Builder's Lift Available | 0 d | Fixed Duration | 2 | 0d | 479 | 16 April 2026 5:00 PM | 16 April 2026 5:00 PM | Thu 16/04/26 | Thu 16/04/26 | Mon 9/11/26 | Mon 9/11/26 | 144d | 144d | 0ed | 0 | NA | NA | 9 March 2026 5:00 PM | 9 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.12 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
14 | 4735 | Yes | Auto Scheduled | Internal Finishes Complete | 0 d | Fixed Duration | 2 | 0d | 681 | 9 April 2026 5:00 PM | 9 April 2026 5:00 PM | Thu 9/04/26 | Thu 9/04/26 | Mon 9/11/26 | Mon 9/11/26 | 149d | 149d | 0ed | 0 | NA | NA | 2 March 2026 5:00 PM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.13 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
15 | 4848 | Yes | Auto Scheduled | Permanent Power Available | 0 d | Fixed Duration | 2 | 0d | 485 | 7 May 2026 5:00 PM | 7 May 2026 5:00 PM | Thu 7/05/26 | Thu 7/05/26 | Mon 9/11/26 | Mon 9/11/26 | 130d | 130d | 0ed | 0 | NA | NA | 27 March 2026 5:00 PM | 27 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.14 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
16 | 4849 | Yes | Auto Scheduled | Landscaping & External Works Complete | 0 d | Fixed Duration | 2 | 0d | 706,718 | 18 June 2026 5:00 PM | 18 June 2026 5:00 PM | Thu 18/06/26 | Thu 18/06/26 | Mon 9/11/26 | Mon 9/11/26 | 101d | 101d | 0ed | 0 | NA | NA | 12 May 2026 5:00 PM | 12 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.15 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
17 | 4850 | Yes | Auto Scheduled | Project Completion | 0 d | Fixed Duration | 2 | 0d | 734 | 9 November 2026 5:00 PM | 9 November 2026 5:00 PM | Mon 9/11/26 | Mon 9/11/26 | Mon 9/11/26 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | NA | NA | 1 October 2026 5:00 PM | 1 October 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 1.16 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
18 | 3978 | Yes | Auto Scheduled | OFF SITE WORKS | 293 d | Fixed Duration | 1 | 293d |  | 4 October 2023 8:00 AM | 10 December 2024 5:00 PM | Wed 4/10/23 | Tue 10/12/24 | Wed 4/10/23 | Mon 9/11/26 | 472d | 472d | 0ed | 0.69999999999999996 | Wed 4/10/23 | NA | 4 October 2023 8:00 AM | 10 December 2024 5:00 PM | As Soon As Possible | NA | Tue 24/10/23 | Tue 24/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
19 | 3923 | Yes | Auto Scheduled | AUTHORITY APPROVALS | 1 d | Fixed Duration | 2 | 1d |  | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | As Soon As Possible | NA | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
20 | 3924 | Yes | Auto Scheduled | Council Development Approval | 1 d | Fixed Duration | 3 | 1d | 27 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | As Soon As Possible | NA | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
21 | 3925 | Yes | Auto Scheduled | Council Minor Change Approval | 1 d | Fixed Duration | 3 | 1d | 27 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Start No Earlier Than | Tue 30/05/23 | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
22 | 3926 | Yes | Auto Scheduled | Council Plumbing Approval (70 units) | 1 d | Fixed Duration | 3 | 1d | 27 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | As Soon As Possible | NA | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
23 | 3927 | Yes | Auto Scheduled | Energex Connection Offer | 1 d | Fixed Duration | 3 | 1d | 27 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | As Soon As Possible | NA | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
24 | 3928 | Yes | Auto Scheduled | Unity Water Water & Sewerage Connection | 1 d | Fixed Duration | 3 | 1d | 27 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | Fri 15/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Fri 15/12/23 | 15 December 2023 8:00 AM | 15 December 2023 5:00 PM | As Soon As Possible | NA | Fri 15/12/23 | Fri 15/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
25 | 3930 | Yes | Auto Scheduled | DESIGN PROGRAM | 31 d | Fixed Duration | 2 | 31d |  | 14 December 2023 8:00 AM | 9 February 2024 5:00 PM | Thu 14/12/23 | Fri 9/02/24 | Thu 14/12/23 | Fri 9/02/24 | 0d | 0d | 0ed | 1 | Thu 14/12/23 | Fri 9/02/24 | 14 December 2023 8:00 AM | 9 February 2024 5:00 PM | As Soon As Possible | NA | Thu 14/12/23 | Thu 14/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
26 | 3938 | Yes | Auto Scheduled | DESIGN | 31 d | Fixed Duration | 3 | 31d |  | 14 December 2023 8:00 AM | 9 February 2024 5:00 PM | Thu 14/12/23 | Fri 9/02/24 | Thu 14/12/23 | Fri 9/02/24 | 0d | 0d | 0ed | 1 | Thu 14/12/23 | Fri 9/02/24 | 14 December 2023 8:00 AM | 9 February 2024 5:00 PM | As Soon As Possible | NA | Thu 14/12/23 | Thu 14/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
27 | 3931 | Yes | Auto Scheduled | Initial Design Coordination Meeting | 1 d | Fixed Duration | 4 | 1d |  | 14 December 2023 8:00 AM | 14 December 2023 5:00 PM | Thu 14/12/23 | Thu 14/12/23 | Thu 14/12/23 | Thu 14/12/23 | 0d | 0d | 0ed | 1 | Thu 14/12/23 | Thu 14/12/23 | 14 December 2023 8:00 AM | 14 December 2023 5:00 PM | Start No Earlier Than | Thu 14/12/23 | Thu 14/12/23 | Thu 14/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
28 | 3932 | Yes | Auto Scheduled | Review & comment of Social Housing summary & Development Consent Matrix | 5 d | Fixed Duration | 4 | 5d | 27 | 15 December 2023 8:00 AM | 21 December 2023 5:00 PM | Fri 15/12/23 | Thu 21/12/23 | Fri 15/12/23 | Thu 21/12/23 | 0d | 0d | 0ed | 1 | Fri 15/12/23 | Thu 21/12/23 | 15 December 2023 8:00 AM | 21 December 2023 5:00 PM | As Soon As Possible | NA | Thu 21/12/23 | Thu 21/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
29 | 3933 | Yes | Auto Scheduled | Issue of general layouts & floor plans | 5 d | Fixed Duration | 4 | 5d | 28 | 22 December 2023 8:00 AM | 11 January 2024 5:00 PM | Fri 22/12/23 | Thu 11/01/24 | Fri 22/12/23 | Thu 11/01/24 | 0d | 0d | 0ed | 1 | Fri 22/12/23 | Thu 11/01/24 | 22 December 2023 8:00 AM | 11 January 2024 5:00 PM | As Soon As Possible | NA | Thu 11/01/24 | Thu 11/01/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
30 | 3934 | Yes | Auto Scheduled | Coordination of general layouts & floor plans | 5 d | Fixed Duration | 4 | 5d | 29 | 12 January 2024 8:00 AM | 18 January 2024 5:00 PM | Fri 12/01/24 | Thu 18/01/24 | Fri 12/01/24 | Thu 18/01/24 | 0d | 0d | 0ed | 1 | Fri 12/01/24 | Thu 18/01/24 | 12 January 2024 8:00 AM | 18 January 2024 5:00 PM | As Soon As Possible | NA | Thu 18/01/24 | Thu 18/01/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
31 | 3935 | Yes | Auto Scheduled | Issue of coordinated general layouts & floors | 5 d | Fixed Duration | 4 | 5d | 30 | 19 January 2024 8:00 AM | 25 January 2024 5:00 PM | Fri 19/01/24 | Thu 25/01/24 | Fri 19/01/24 | Thu 25/01/24 | 0d | 0d | 0ed | 1 | Fri 19/01/24 | Thu 25/01/24 | 19 January 2024 8:00 AM | 25 January 2024 5:00 PM | As Soon As Possible | NA | Thu 25/01/24 | Thu 25/01/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
32 | 3936 | Yes | Auto Scheduled | Review and comment of coordinated plans | 5 d | Fixed Duration | 4 | 5d | 31 | 29 January 2024 8:00 AM | 2 February 2024 5:00 PM | Mon 29/01/24 | Fri 2/02/24 | Mon 29/01/24 | Fri 2/02/24 | 0d | 0d | 0ed | 1 | Mon 29/01/24 | Fri 2/02/24 | 29 January 2024 8:00 AM | 2 February 2024 5:00 PM | As Soon As Possible | NA | Fri 2/02/24 | Fri 2/02/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
33 | 3937 | Yes | Auto Scheduled | Issue of complete design set | 5 d | Fixed Duration | 4 | 5d | 32 | 5 February 2024 8:00 AM | 9 February 2024 5:00 PM | Mon 5/02/24 | Fri 9/02/24 | Mon 5/02/24 | Fri 9/02/24 | 0d | 0d | 0ed | 1 | Mon 5/02/24 | Fri 9/02/24 | 5 February 2024 8:00 AM | 9 February 2024 5:00 PM | As Soon As Possible | NA | Fri 9/02/24 | Fri 9/02/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.2.1.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
34 | 3988 | Yes | Auto Scheduled | BUILDING APPROVAL | 40 d | Fixed Duration | 2 | 40d |  | 12 February 2024 8:00 AM | 9 April 2024 5:00 PM | Mon 12/02/24 | Tue 9/04/24 | Mon 12/02/24 | Tue 9/04/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Tue 9/04/24 | 12 February 2024 8:00 AM | 9 April 2024 5:00 PM | As Soon As Possible | NA | Fri 16/02/24 | Fri 16/02/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
35 | 3991 | Yes | Auto Scheduled | Building Approval #01 - Prepare & Submit | 5 d | Fixed Duration | 3 | 5d | 33 | 12 February 2024 8:00 AM | 16 February 2024 5:00 PM | Mon 12/02/24 | Fri 16/02/24 | Mon 12/02/24 | Fri 16/02/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 16/02/24 | 12 February 2024 8:00 AM | 16 February 2024 5:00 PM | As Soon As Possible | NA | Fri 16/02/24 | Fri 16/02/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
36 | 3990 | Yes | Auto Scheduled | Building Approval #01 - Review Period | 10 d | Fixed Duration | 3 | 10d | 35 | 19 February 2024 8:00 AM | 1 March 2024 5:00 PM | Mon 19/02/24 | Fri 1/03/24 | Mon 19/02/24 | Fri 1/03/24 | 0d | 0d | 0ed | 1 | Mon 19/02/24 | Fri 1/03/24 | 19 February 2024 8:00 AM | 1 March 2024 5:00 PM | As Soon As Possible | NA | Fri 1/03/24 | Fri 1/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
37 | 3989 | Yes | Auto Scheduled | Building Approval #01 - Approved | 0 d | Fixed Duration | 3 | 0d | 36 | 1 March 2024 8:00 AM | 1 March 2024 8:00 AM | Fri 1/03/24 | Fri 1/03/24 | Fri 1/03/24 | Fri 1/03/24 | 0d | 0d | 0ed | 1 | Fri 1/03/24 | Fri 1/03/24 | 1 March 2024 5:00 PM | 1 March 2024 5:00 PM | As Soon As Possible | NA | Fri 1/03/24 | Fri 1/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.3 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
38 | 3995 | Yes | Auto Scheduled | Building Approval #02 - Prepare & Submit | 15 d | Fixed Duration | 3 | 15d | 37 | 4 March 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 4/03/24 | Fri 22/03/24 | Mon 4/03/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 4/03/24 | Fri 22/03/24 | 4 March 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
39 | 3996 | Yes | Auto Scheduled | Building Approval #02 - Review Period | 10 d | Fixed Duration | 3 | 10d | 38 | 25 March 2024 8:00 AM | 9 April 2024 5:00 PM | Mon 25/03/24 | Tue 9/04/24 | Mon 25/03/24 | Tue 9/04/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Tue 9/04/24 | 25 March 2024 8:00 AM | 9 April 2024 5:00 PM | As Soon As Possible | NA | Tue 9/04/24 | Tue 9/04/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
40 | 3997 | Yes | Auto Scheduled | Building Approval #02 - Approved | 0 d | Fixed Duration | 3 | 0d | 39 | 9 April 2024 8:00 AM | 9 April 2024 8:00 AM | Tue 9/04/24 | Tue 9/04/24 | Tue 9/04/24 | Tue 9/04/24 | 0d | 0d | 0ed | 1 | Tue 9/04/24 | Tue 9/04/24 | 9 April 2024 5:00 PM | 9 April 2024 5:00 PM | As Soon As Possible | NA | Tue 9/04/24 | Tue 9/04/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.3.6 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
41 | 3944 | Yes | Auto Scheduled | TENDERING & PROCUREMENT | 227 d | Fixed Duration | 2 | 227d |  | 4 October 2023 8:00 AM | 5 September 2024 5:00 PM | Wed 4/10/23 | Thu 5/09/24 | Wed 4/10/23 | Mon 9/11/26 | 538d | 538d | 0ed | 0.65000000000000002 | Wed 4/10/23 | NA | 4 October 2023 8:00 AM | 5 September 2024 5:00 PM | As Soon As Possible | NA | Tue 24/10/23 | Tue 24/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
42 | 3945 | Yes | Auto Scheduled | Demolition - Tender, Evaluation & Award | 15 d | Fixed Duration | 3 | 15d | 21FS-53d | 4 October 2023 8:00 AM | 24 October 2023 5:00 PM | Wed 4/10/23 | Tue 24/10/23 | Wed 4/10/23 | Tue 24/10/23 | 0d | 0d | 0ed | 1 | Wed 4/10/23 | Tue 24/10/23 | 4 October 2023 8:00 AM | 24 October 2023 5:00 PM | As Soon As Possible | NA | Tue 24/10/23 | Tue 24/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
43 | 3948 | Yes | Auto Scheduled | Demolition - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 42 | 25 October 2023 8:00 AM | 25 October 2023 5:00 PM | Wed 25/10/23 | Wed 25/10/23 | Wed 25/10/23 | Wed 25/10/23 | 0d | 0d | 0ed | 1 | Wed 25/10/23 | Wed 25/10/23 | 25 October 2023 8:00 AM | 25 October 2023 5:00 PM | As Soon As Possible | NA | Wed 25/10/23 | Wed 25/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
44 | 3946 | Yes | Auto Scheduled | Bulk & detail earthworks - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 33 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 12/02/24 | Fri 22/03/24 | Mon 12/02/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 22/03/24 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
45 | 3949 | Yes | Auto Scheduled | Bulk & detail earthworks - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 44 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
46 | 3947 | Yes | Auto Scheduled | Screw Pile Foundations - Tender Evaluation & Award | 20 d | Fixed Duration | 3 | 20d | 33 | 12 February 2024 8:00 AM | 8 March 2024 5:00 PM | Mon 12/02/24 | Fri 8/03/24 | Mon 12/02/24 | Fri 8/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 8/03/24 | 12 February 2024 8:00 AM | 8 March 2024 5:00 PM | As Soon As Possible | NA | Fri 8/03/24 | Fri 8/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
47 | 3950 | Yes | Auto Scheduled | Screw Pile Foundations - Design & Engineering | 10 d | Fixed Duration | 3 | 10d | 46 | 11 March 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 11/03/24 | Fri 22/03/24 | Mon 11/03/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 11/03/24 | Fri 22/03/24 | 11 March 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
48 | 3951 | Yes | Auto Scheduled | Screw Pile Foundations - Fabrication & Mobilisation | 1 d | Fixed Duration | 3 | 1d | 47 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
49 | 3952 | Yes | Auto Scheduled | Hydraulic & Civil Services - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 33 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 12/02/24 | Fri 22/03/24 | Mon 12/02/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 22/03/24 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
50 | 3953 | Yes | Auto Scheduled | Hydraulic & Civil Services - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 49 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
51 | 3954 | Yes | Auto Scheduled | Electrical Services - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 33 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 12/02/24 | Fri 22/03/24 | Mon 12/02/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 22/03/24 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
52 | 3955 | Yes | Auto Scheduled | Electrical Services - Mobilsation to Site | 1 d | Fixed Duration | 3 | 1d | 51 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
53 | 3956 | Yes | Auto Scheduled | Wet Fire Services - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 33 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 12/02/24 | Fri 22/03/24 | Mon 12/02/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 22/03/24 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
54 | 3957 | Yes | Auto Scheduled | Wet Fire Services - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 53 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
55 | 3958 | Yes | Auto Scheduled | Mechanical & Ventilation Services - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 33 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | Mon 12/02/24 | Fri 22/03/24 | Mon 12/02/24 | Fri 22/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 22/03/24 | 12 February 2024 8:00 AM | 22 March 2024 5:00 PM | As Soon As Possible | NA | Fri 22/03/24 | Fri 22/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
56 | 3959 | Yes | Auto Scheduled | Mechanical & Ventilation Services - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 55 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | Mon 25/03/24 | 0d | 0d | 0ed | 1 | Mon 25/03/24 | Mon 25/03/24 | 25 March 2024 8:00 AM | 25 March 2024 5:00 PM | As Soon As Possible | NA | Mon 25/03/24 | Mon 25/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
57 | 4820 | Yes | Auto Scheduled | Lift Services - Tender Evaluation & Award | 20 d | Fixed Duration | 3 | 20d | 33 | 12 February 2024 8:00 AM | 8 March 2024 5:00 PM | Mon 12/02/24 | Fri 8/03/24 | Mon 12/02/24 | Fri 8/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 8/03/24 | 12 February 2024 8:00 AM | 8 March 2024 5:00 PM | As Soon As Possible | NA | Fri 8/03/24 | Fri 8/03/24 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.16 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
58 | 4819 | Yes | Auto Scheduled | Lift Services - Design & Engineering | 30 d | Fixed Duration | 3 | 30d | 57 | 11 March 2024 8:00 AM | 23 April 2024 5:00 PM | Mon 11/03/24 | Tue 23/04/24 | Mon 11/03/24 | Tue 23/04/24 | 0d | 0d | 0ed | 1 | Mon 11/03/24 | Tue 23/04/24 | 11 March 2024 8:00 AM | 23 April 2024 5:00 PM | As Soon As Possible | NA | Tue 23/04/24 | Tue 23/04/24 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.17 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
59 | 4818 | Yes | Auto Scheduled | Lift Services - Manufacturing & Shipping | 95 d | Fixed Duration | 3 | 95d | 58 | 24 April 2024 8:00 AM | 5 September 2024 5:00 PM | Wed 24/04/24 | Thu 5/09/24 | Wed 24/04/24 | Thu 5/09/24 | 0d | 0d | 0ed | 1 | Wed 24/04/24 | Thu 5/09/24 | 24 April 2024 8:00 AM | 5 September 2024 5:00 PM | As Soon As Possible | NA | Thu 5/09/24 | Thu 5/09/24 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.18 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
60 | 3960 | Yes | Auto Scheduled | Structure, Form/Reo/Pour - Tender Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 33 | 12 February 2024 8:00 AM | 15 March 2024 5:00 PM | Mon 12/02/24 | Fri 15/03/24 | Mon 12/02/24 | Fri 15/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 15/03/24 | 12 February 2024 8:00 AM | 15 March 2024 5:00 PM | As Soon As Possible | NA | Fri 15/03/24 | Fri 15/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.19 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
61 | 3961 | Yes | Auto Scheduled | Structure, Form/Reo/Pour - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 60 | 18 March 2024 8:00 AM | 18 March 2024 5:00 PM | Mon 18/03/24 | Mon 18/03/24 | Mon 18/03/24 | Mon 18/03/24 | 0d | 0d | 0ed | 1 | Mon 18/03/24 | Mon 18/03/24 | 18 March 2024 8:00 AM | 18 March 2024 5:00 PM | As Soon As Possible | NA | Mon 18/03/24 | Mon 18/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.20 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
62 | 3970 | Yes | Auto Scheduled | Party Walls, Masonry - Tender, Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 33 | 12 February 2024 8:00 AM | 15 March 2024 5:00 PM | Mon 12/02/24 | Fri 15/03/24 | Mon 12/02/24 | Fri 15/03/24 | 0d | 0d | 0ed | 1 | Mon 12/02/24 | Fri 15/03/24 | 12 February 2024 8:00 AM | 15 March 2024 5:00 PM | As Soon As Possible | NA | Fri 15/03/24 | Fri 15/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.21 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
63 | 3971 | Yes | Auto Scheduled | Party Walls, Masonry - Mobilisation to Site | 1 d | Fixed Duration | 3 | 1d | 62 | 18 March 2024 8:00 AM | 18 March 2024 5:00 PM | Mon 18/03/24 | Mon 18/03/24 | Mon 18/03/24 | Mon 18/03/24 | 0d | 0d | 0ed | 1 | Mon 18/03/24 | Mon 18/03/24 | 18 March 2024 8:00 AM | 18 March 2024 5:00 PM | As Soon As Possible | NA | Mon 18/03/24 | Mon 18/03/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.22 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
64 | 3962 | Yes | Auto Scheduled | Structure, Roof Framing - Tender, Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 45 | 26 March 2024 8:00 AM | 2 May 2024 5:00 PM | Tue 26/03/24 | Thu 2/05/24 | Tue 26/03/24 | Thu 2/05/24 | 0d | 0d | 0ed | 1 | Tue 26/03/24 | Thu 2/05/24 | 26 March 2024 8:00 AM | 2 May 2024 5:00 PM | As Soon As Possible | NA | Thu 2/05/24 | Thu 2/05/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.23 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
65 | 3963 | Yes | Auto Scheduled | Structure, Roof Framing - Design & Engineering | 10 d | Fixed Duration | 3 | 10d | 64 | 3 May 2024 8:00 AM | 17 May 2024 5:00 PM | Fri 3/05/24 | Fri 17/05/24 | Fri 3/05/24 | Fri 17/05/24 | 0d | 0d | 0ed | 1 | Fri 3/05/24 | Fri 17/05/24 | 3 May 2024 8:00 AM | 17 May 2024 5:00 PM | As Soon As Possible | NA | Fri 17/05/24 | Fri 17/05/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.24 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
66 | 3964 | Yes | Auto Scheduled | Structure, Roof Framing - Fabrication & Mobilisation | 30 d | Fixed Duration | 3 | 30d | 65 | 20 May 2024 8:00 AM | 28 June 2024 5:00 PM | Mon 20/05/24 | Fri 28/06/24 | Mon 20/05/24 | Fri 28/06/24 | 0d | 0d | 0ed | 1 | Mon 20/05/24 | Fri 28/06/24 | 20 May 2024 8:00 AM | 28 June 2024 5:00 PM | As Soon As Possible | NA | Fri 28/06/24 | Fri 28/06/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.25 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
67 | 3965 | Yes | Auto Scheduled | Roofing & Cladding - Tender, Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 45 | 26 March 2024 8:00 AM | 2 May 2024 5:00 PM | Tue 26/03/24 | Thu 2/05/24 | Mon 14/09/26 | Mon 19/10/26 | 0d | 612d | 0ed | 0 | NA | NA | 26 March 2024 8:00 AM | 2 May 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.26 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
68 | 3966 | Yes | Auto Scheduled | Roofing & Cladding - Mobilisation to Site | 15 d | Fixed Duration | 3 | 15d | 67 | 3 May 2024 8:00 AM | 24 May 2024 5:00 PM | Fri 3/05/24 | Fri 24/05/24 | Tue 20/10/26 | Mon 9/11/26 | 612d | 612d | 0ed | 0 | NA | NA | 3 May 2024 8:00 AM | 24 May 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.27 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
69 | 3967 | Yes | Auto Scheduled | Windows & Glazing - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 45 | 26 March 2024 8:00 AM | 10 May 2024 5:00 PM | Tue 26/03/24 | Fri 10/05/24 | Mon 22/06/26 | Fri 31/07/26 | 0d | 552d | 0ed | 0 | NA | NA | 26 March 2024 8:00 AM | 10 May 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.28 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
70 | 3968 | Yes | Auto Scheduled | Windows & Glazing - Design & Engineering | 15 d | Fixed Duration | 3 | 15d | 69 | 13 May 2024 8:00 AM | 31 May 2024 5:00 PM | Mon 13/05/24 | Fri 31/05/24 | Mon 7/09/26 | Fri 25/09/26 | 0d | 577d | 0ed | 0 | NA | NA | 13 May 2024 8:00 AM | 31 May 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.29 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
71 | 4737 | Yes | Auto Scheduled | Windows & Glazing - Fabrication & Mobilisation | 30 d | Fixed Duration | 3 | 30d | 70 | 3 June 2024 8:00 AM | 12 July 2024 5:00 PM | Mon 3/06/24 | Fri 12/07/24 | Mon 28/09/26 | Mon 9/11/26 | 577d | 577d | 0ed | 0 | NA | NA | 3 June 2024 8:00 AM | 12 July 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.30 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
72 | 3969 | Yes | Auto Scheduled | Joinery - Tender, Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 69 | 13 May 2024 8:00 AM | 14 June 2024 5:00 PM | Mon 13/05/24 | Fri 14/06/24 | Mon 17/08/26 | Fri 18/09/26 | 0d | 562d | 0ed | 0 | NA | NA | 13 May 2024 8:00 AM | 14 June 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.31 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
73 | 3972 | Yes | Auto Scheduled | Joinery - Design | 15 d | Fixed Duration | 3 | 15d | 72 | 17 June 2024 8:00 AM | 5 July 2024 5:00 PM | Mon 17/06/24 | Fri 5/07/24 | Mon 21/09/26 | Mon 12/10/26 | 0d | 562d | 0ed | 0 | NA | NA | 17 June 2024 8:00 AM | 5 July 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.32 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
74 | 3973 | Yes | Auto Scheduled | Joinery - Fabrication & Mobilisation | 20 d | Fixed Duration | 3 | 20d | 73 | 8 July 2024 8:00 AM | 2 August 2024 5:00 PM | Mon 8/07/24 | Fri 2/08/24 | Tue 13/10/26 | Mon 9/11/26 | 562d | 562d | 0ed | 0 | NA | NA | 8 July 2024 8:00 AM | 2 August 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.33 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
75 | 3974 | Yes | Auto Scheduled | Internal Finishes - Tender, Evaluation & Award | 25 d | Fixed Duration | 3 | 25d | 69 | 13 May 2024 8:00 AM | 14 June 2024 5:00 PM | Mon 13/05/24 | Fri 14/06/24 | Mon 3/08/26 | Fri 4/09/26 | 0d | 552d | 0ed | 0 | NA | NA | 13 May 2024 8:00 AM | 14 June 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.34 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
76 | 3975 | Yes | Auto Scheduled | Internal Finishes - Mobilisation to Site | 10 d | Fixed Duration | 3 | 10d | 75 | 17 June 2024 8:00 AM | 28 June 2024 5:00 PM | Mon 17/06/24 | Fri 28/06/24 | Tue 27/10/26 | Mon 9/11/26 | 587d | 587d | 0ed | 0 | NA | NA | 17 June 2024 8:00 AM | 28 June 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.35 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
77 | 3976 | Yes | Auto Scheduled | External Road Works - Tender, Evaluation & Award | 30 d | Fixed Duration | 3 | 30d | 75 | 17 June 2024 8:00 AM | 26 July 2024 5:00 PM | Mon 17/06/24 | Fri 26/07/24 | Mon 7/09/26 | Mon 19/10/26 | 0d | 552d | 0ed | 0 | NA | NA | 17 June 2024 8:00 AM | 26 July 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.36 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
78 | 3977 | Yes | Auto Scheduled | External Road Works - Mobilisation to Site | 15 d | Fixed Duration | 3 | 15d | 77 | 29 July 2024 8:00 AM | 16 August 2024 5:00 PM | Mon 29/07/24 | Fri 16/08/24 | Tue 20/10/26 | Mon 9/11/26 | 552d | 552d | 0ed | 0 | NA | NA | 29 July 2024 8:00 AM | 16 August 2024 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.4.37 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
79 | 4894 | Yes | Auto Scheduled | DEVELOPMENT SERVICES AGREEMENT | 40 d | Fixed Duration | 2 | 40d |  | 16 October 2024 8:00 AM | 10 December 2024 5:00 PM | Wed 16/10/24 | Tue 10/12/24 | Wed 16/10/24 | Tue 10/12/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Tue 10/12/24 | 16 October 2024 8:00 AM | 10 December 2024 5:00 PM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
80 | 4895 | Yes | Auto Scheduled | Condition Precedent - Executed DSA Counter Part | 1 d | Fixed Duration | 3 | 1d |  | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Start No Earlier Than | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
81 | 4896 | Yes | Auto Scheduled | Condition Precedent - Parent Company Guarantee | 1 d | Fixed Duration | 3 | 1d | 80SS | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
82 | 4897 | Yes | Auto Scheduled | Condition Precedent - Building Contract | 1 d | Fixed Duration | 3 | 1d | 80SS | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
83 | 4898 | Yes | Auto Scheduled | Condition Precedent - Performance Bond | 1 d | Fixed Duration | 3 | 1d | 80SS | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
84 | 4899 | Yes | Auto Scheduled | Condition Precedent - Builder Tripartite | 1 d | Fixed Duration | 3 | 1d | 80SS | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 5:00 PM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
85 | 4900 | Yes | Auto Scheduled | Development Services Agreement - Effective Date | 0 d | Fixed Duration | 3 | 0d | 80SS | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 7/02/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.6 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
86 | 4901 | Yes | Auto Scheduled | Land Settlement | 0 d | Fixed Duration | 3 | 0d | 85 | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | Wed 16/10/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Wed 16/10/24 | 16 October 2024 8:00 AM | 16 October 2024 8:00 AM | As Soon As Possible | NA | Wed 16/10/24 | Wed 16/10/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.7 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
87 | 4902 | Yes | Auto Scheduled | Construction Commencement Lead In (8 weeks from Land Settlement) | 40 d | Fixed Duration | 3 | 40d | 86 | 16 October 2024 8:00 AM | 10 December 2024 5:00 PM | Wed 16/10/24 | Tue 10/12/24 | Wed 16/10/24 | Tue 10/12/24 | 0d | 0d | 0ed | 1 | Wed 16/10/24 | Tue 10/12/24 | 16 October 2024 8:00 AM | 10 December 2024 5:00 PM | As Soon As Possible | NA | Tue 10/12/24 | Tue 10/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
88 | 4903 | Yes | Auto Scheduled | Construction Commencement | 0 d | Fixed Duration | 3 | 0d | 87 | 10 December 2024 8:00 AM | 10 December 2024 8:00 AM | Tue 10/12/24 | Tue 10/12/24 | Tue 10/12/24 | Tue 10/12/24 | 0d | 0d | 0ed | 1 | Tue 10/12/24 | Tue 10/12/24 | 10 December 2024 5:00 PM | 10 December 2024 5:00 PM | As Soon As Possible | NA | Tue 10/12/24 | Tue 10/12/24 | Fri 7/06/24 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 2.5.9 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
89 | 4914 | Yes | Auto Scheduled | INCLEMENT WEATHER/ONSITE DELAYS | 63 d | Fixed Duration | 1 | 0d |  | 2 December 2024 8:00 AM | 11 March 2025 5:00 PM | Mon 2/12/24 | Tue 11/03/25 | Mon 2/12/24 | Tue 11/03/25 | 0d | 0d | 0ed | 1 | Mon 2/12/24 | Tue 11/03/25 | NA | NA | As Soon As Possible | NA | Tue 3/12/24 | Tue 3/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
90 | 4922 | Yes | Auto Scheduled | EOT - December Inclement Weather (2nd) | 2 d | Fixed Duration | 2 | 0d |  | 2 December 2024 8:00 AM | 3 December 2024 5:00 PM | Mon 2/12/24 | Tue 3/12/24 | Mon 2/12/24 | Tue 3/12/24 | 0d | 0d | 0ed | 1 | Mon 2/12/24 | Tue 3/12/24 | NA | NA | Start No Earlier Than | Mon 2/12/24 | Tue 3/12/24 | Tue 3/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
91 | 4923 | Yes | Auto Scheduled | EOT - December Inclement Weather (5th) | 2 d | Fixed Duration | 2 | 0d |  | 5 December 2024 8:00 AM | 6 December 2024 5:00 PM | Thu 5/12/24 | Fri 6/12/24 | Thu 5/12/24 | Fri 6/12/24 | 0d | 0d | 0ed | 1 | Thu 5/12/24 | Fri 6/12/24 | NA | NA | Start No Earlier Than | Thu 5/12/24 | Fri 6/12/24 | Fri 6/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
92 | 4924 | Yes | Auto Scheduled | EOT - December Inclement Weather (11th-12th) | 2 d | Fixed Duration | 2 | 0d |  | 11 December 2024 8:00 AM | 12 December 2024 5:00 PM | Wed 11/12/24 | Thu 12/12/24 | Wed 11/12/24 | Thu 12/12/24 | 0d | 0d | 0ed | 1 | Wed 11/12/24 | Thu 12/12/24 | NA | NA | Start No Earlier Than | Wed 11/12/24 | Thu 12/12/24 | Thu 12/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
93 | 4925 | Yes | Auto Scheduled | EOT - December Inclement Weather (16th-18th) | 3 d | Fixed Duration | 2 | 0d |  | 16 December 2024 8:00 AM | 18 December 2024 5:00 PM | Mon 16/12/24 | Wed 18/12/24 | Mon 16/12/24 | Wed 18/12/24 | 0d | 0d | 0ed | 1 | Mon 16/12/24 | Wed 18/12/24 | NA | NA | Start No Earlier Than | Mon 16/12/24 | Wed 18/12/24 | Wed 18/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
94 | 4918 | Yes | Auto Scheduled | EOT - December Inclement Weather (20th) | 1 d | Fixed Duration | 2 | 0d |  | 20 December 2024 8:00 AM | 20 December 2024 5:00 PM | Fri 20/12/24 | Fri 20/12/24 | Fri 20/12/24 | Fri 20/12/24 | 0d | 0d | 0ed | 1 | Fri 20/12/24 | Fri 20/12/24 | NA | NA | Start No Earlier Than | Fri 20/12/24 | Fri 20/12/24 | Fri 20/12/24 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
95 | 4919 | Yes | Auto Scheduled | EOT - January Inclement Weather (13th-14th) | 2 d | Fixed Duration | 2 | 0d |  | 13 January 2025 8:00 AM | 14 January 2025 5:00 PM | Mon 13/01/25 | Tue 14/01/25 | Mon 13/01/25 | Tue 14/01/25 | 0d | 0d | 0ed | 1 | Mon 13/01/25 | Tue 14/01/25 | NA | NA | Start No Earlier Than | Mon 13/01/25 | Tue 14/01/25 | Tue 14/01/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
96 | 4920 | Yes | Auto Scheduled | EOT - January Inclement Weather (20th) | 1 d | Fixed Duration | 2 | 0d |  | 20 January 2025 8:00 AM | 20 January 2025 5:00 PM | Mon 20/01/25 | Mon 20/01/25 | Mon 20/01/25 | Mon 20/01/25 | 0d | 0d | 0ed | 1 | Mon 20/01/25 | Mon 20/01/25 | NA | NA | Start No Earlier Than | Mon 20/01/25 | Mon 20/01/25 | Mon 20/01/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
97 | 4921 | Yes | Auto Scheduled | EOT - February Inclement Weather (5th) | 2 d | Fixed Duration | 2 | 0d |  | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | Wed 5/02/25 | Thu 6/02/25 | Wed 5/02/25 | Thu 6/02/25 | 0d | 0d | 0ed | 1 | Wed 5/02/25 | Thu 6/02/25 | NA | NA | Start No Earlier Than | Wed 5/02/25 | Thu 6/02/25 | Thu 6/02/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
98 | 4916 | Yes | Auto Scheduled | EOT - Asbestos In Soils | 10 d | Fixed Duration | 2 | 0d |  | 20 February 2025 8:00 AM | 5 March 2025 5:00 PM | Thu 20/02/25 | Wed 5/03/25 | Thu 20/02/25 | Wed 5/03/25 | 0d | 0d | 0ed | 1 | Thu 20/02/25 | Wed 5/03/25 | NA | NA | Finish No Earlier Than | Wed 5/03/25 | Wed 5/03/25 | Wed 5/03/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
99 | 4917 | Yes | Auto Scheduled | EOT - February Inclement Weather (18th-19th) | 2 d | Fixed Duration | 2 | 0d |  | 18 February 2025 8:00 AM | 19 February 2025 5:00 PM | Tue 18/02/25 | Wed 19/02/25 | Tue 18/02/25 | Wed 19/02/25 | 0d | 0d | 0ed | 1 | Tue 18/02/25 | Wed 19/02/25 | NA | NA | Start No Earlier Than | Tue 18/02/25 | Wed 19/02/25 | Wed 19/02/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
100 | 4915 | Yes | Auto Scheduled | EOT - February Inclement Weather (25th) | 2 d | Fixed Duration | 2 | 0d |  | 25 February 2025 8:00 AM | 26 February 2025 5:00 PM | Tue 25/02/25 | Wed 26/02/25 | Tue 25/02/25 | Wed 26/02/25 | 0d | 0d | 0ed | 1 | Tue 25/02/25 | Wed 26/02/25 | NA | NA | Start No Earlier Than | Tue 25/02/25 | Wed 26/02/25 | Wed 26/02/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
101 | 4913 | Yes | Auto Scheduled | EOT - March Inclement Weather (Cyclone Alfred - 6th-8th) | 4 d | Fixed Duration | 2 | 0d |  | 6 March 2025 8:00 AM | 11 March 2025 5:00 PM | Thu 6/03/25 | Tue 11/03/25 | Thu 6/03/25 | Tue 11/03/25 | 0d | 0d | 0ed | 1 | Thu 6/03/25 | Tue 11/03/25 | NA | NA | Start No Earlier Than | Thu 6/03/25 | Tue 11/03/25 | Tue 11/03/25 | Wed 9/04/25 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 3.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
102 | 3979 | Yes | Auto Scheduled | EARLY WORKS | 34 d | Fixed Duration | 1 | 33d |  | 25 October 2023 8:00 AM | 11 December 2023 5:00 PM | Wed 25/10/23 | Mon 11/12/23 | Wed 25/10/23 | Mon 11/12/23 | 0d | 0d | 0ed | 1 | Wed 25/10/23 | Mon 11/12/23 | 25 October 2023 5:00 PM | 11 December 2023 5:00 PM | As Soon As Possible | NA | Wed 25/10/23 | Wed 25/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
103 | 3980 | Yes | Manually Scheduled | SITE ESTABLISHMENT | 6 d | Fixed Duration | 2 | 6d |  | 25 October 2023 8:00 AM | 1 November 2023 5:00 PM | Wed 25/10/23 | Wed 1/11/23 | Wed 25/10/23 | Thu 2/11/23 | 0d | 0d | 0ed | 1 | Wed 25/10/23 | Thu 2/11/23 | 25 October 2023 5:00 PM | 2 November 2023 5:00 PM | As Soon As Possible | NA | Wed 25/10/23 | Wed 25/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
104 | 3984 | Yes | Auto Scheduled | Commence On Site Works | 0 d | Fixed Duration | 3 | 0d | 43 | 25 October 2023 8:00 AM | 25 October 2023 8:00 AM | Wed 25/10/23 | Wed 25/10/23 | Wed 25/10/23 | Wed 25/10/23 | 0d | 0d | 0ed | 1 | Wed 25/10/23 | Wed 25/10/23 | 25 October 2023 5:00 PM | 25 October 2023 5:00 PM | As Soon As Possible | NA | Wed 25/10/23 | Wed 25/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.1.1 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
105 | 3985 | Yes | Auto Scheduled | Temporary Fence Install | 1 d | Fixed Duration | 3 | 1d | 104 | 26 October 2023 8:00 AM | 26 October 2023 5:00 PM | Thu 26/10/23 | Thu 26/10/23 | Thu 26/10/23 | Thu 26/10/23 | 0d | 0d | 0ed | 1 | Thu 26/10/23 | Thu 26/10/23 | 26 October 2023 8:00 AM | 26 October 2023 5:00 PM | As Soon As Possible | NA | Thu 26/10/23 | Thu 26/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
106 | 3986 | Yes | Auto Scheduled | Site Accommodation Establishment | 2 d | Fixed Duration | 3 | 2d | 105 | 27 October 2023 8:00 AM | 30 October 2023 5:00 PM | Fri 27/10/23 | Mon 30/10/23 | Fri 27/10/23 | Mon 30/10/23 | 0d | 0d | 0ed | 1 | Fri 27/10/23 | Mon 30/10/23 | 27 October 2023 8:00 AM | 30 October 2023 5:00 PM | As Soon As Possible | NA | Mon 30/10/23 | Mon 30/10/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
107 | 3987 | Yes | Auto Scheduled | Temporary Service Connections | 3 d | Fixed Duration | 3 | 3d | 106 | 31 October 2023 8:00 AM | 2 November 2023 5:00 PM | Tue 31/10/23 | Thu 2/11/23 | Tue 31/10/23 | Thu 2/11/23 | 0d | 0d | 0ed | 1 | Tue 31/10/23 | Thu 2/11/23 | 31 October 2023 8:00 AM | 2 November 2023 5:00 PM | As Soon As Possible | NA | Thu 2/11/23 | Thu 2/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
108 | 3981 | Yes | Auto Scheduled | DEMOLITION & TREE REMOVAL | 27 d | Fixed Duration | 2 | 27d |  | 3 November 2023 8:00 AM | 11 December 2023 5:00 PM | Fri 3/11/23 | Mon 11/12/23 | Fri 3/11/23 | Mon 11/12/23 | 0d | 0d | 0ed | 1 | Fri 3/11/23 | Mon 11/12/23 | 3 November 2023 8:00 AM | 11 December 2023 5:00 PM | As Soon As Possible | NA | Fri 3/11/23 | Fri 3/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
109 | 3982 | Yes | Auto Scheduled | Service Disconnections to Houses - Water & Power | 1 d | Fixed Duration | 3 | 1d | 107 | 3 November 2023 8:00 AM | 3 November 2023 5:00 PM | Fri 3/11/23 | Fri 3/11/23 | Fri 3/11/23 | Fri 3/11/23 | 0d | 0d | 0ed | 1 | Fri 3/11/23 | Fri 3/11/23 | 3 November 2023 8:00 AM | 3 November 2023 5:00 PM | As Soon As Possible | NA | Fri 3/11/23 | Fri 3/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
110 | 4004 | Yes | Auto Scheduled | Establishment of Hazmat Site Controls | 2 d | Fixed Duration | 3 | 2d | 109 | 6 November 2023 8:00 AM | 7 November 2023 5:00 PM | Mon 6/11/23 | Tue 7/11/23 | Mon 6/11/23 | Tue 7/11/23 | 0d | 0d | 0ed | 1 | Mon 6/11/23 | Tue 7/11/23 | 6 November 2023 8:00 AM | 7 November 2023 5:00 PM | As Soon As Possible | NA | Tue 7/11/23 | Tue 7/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
111 | 4005 | Yes | Auto Scheduled | Asbestos Removal No.45 Beerwah Pde | 5 d | Fixed Duration | 3 | 5d | 110 | 8 November 2023 8:00 AM | 14 November 2023 5:00 PM | Wed 8/11/23 | Tue 14/11/23 | Wed 8/11/23 | Tue 14/11/23 | 0d | 0d | 0ed | 1 | Wed 8/11/23 | Tue 14/11/23 | 8 November 2023 8:00 AM | 14 November 2023 5:00 PM | As Soon As Possible | NA | Tue 14/11/23 | Tue 14/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
112 | 4006 | Yes | Auto Scheduled | Asbestos Removal No.43 Beerwah Pde | 3 d | Fixed Duration | 3 | 3d | 111 | 15 November 2023 8:00 AM | 17 November 2023 5:00 PM | Wed 15/11/23 | Fri 17/11/23 | Wed 15/11/23 | Fri 17/11/23 | 0d | 0d | 0ed | 1 | Wed 15/11/23 | Fri 17/11/23 | 15 November 2023 8:00 AM | 17 November 2023 5:00 PM | As Soon As Possible | NA | Fri 17/11/23 | Fri 17/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
113 | 4007 | Yes | Auto Scheduled | Timber Framing & Cladding Demolition | 5 d | Fixed Duration | 3 | 5d | 112 | 20 November 2023 8:00 AM | 24 November 2023 5:00 PM | Mon 20/11/23 | Fri 24/11/23 | Mon 20/11/23 | Fri 24/11/23 | 0d | 0d | 0ed | 1 | Mon 20/11/23 | Fri 24/11/23 | 20 November 2023 8:00 AM | 24 November 2023 5:00 PM | As Soon As Possible | NA | Fri 24/11/23 | Fri 24/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
114 | 4008 | Yes | Auto Scheduled | Concrete Pavement & Masonry Demolition | 3 d | Fixed Duration | 3 | 3d | 113 | 27 November 2023 8:00 AM | 29 November 2023 5:00 PM | Mon 27/11/23 | Wed 29/11/23 | Mon 27/11/23 | Wed 29/11/23 | 0d | 0d | 0ed | 1 | Mon 27/11/23 | Wed 29/11/23 | 27 November 2023 8:00 AM | 29 November 2023 5:00 PM | As Soon As Possible | NA | Wed 29/11/23 | Wed 29/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
115 | 4009 | Yes | Auto Scheduled | Septic Tank Removal | 3 d | Fixed Duration | 3 | 1d | 114 | 27 November 2023 8:00 AM | 29 November 2023 5:00 PM | Mon 27/11/23 | Wed 29/11/23 | Mon 27/11/23 | Wed 29/11/23 | 0d | 0d | 0ed | 1 | Mon 27/11/23 | Wed 29/11/23 | 30 November 2023 8:00 AM | 30 November 2023 5:00 PM | As Soon As Possible | NA | Wed 29/11/23 | Wed 29/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
116 | 4010 | Yes | Auto Scheduled | Timber Fencing & Site Waste Removal | 1 d | Fixed Duration | 3 | 3d | 113 | 30 November 2023 8:00 AM | 30 November 2023 5:00 PM | Thu 30/11/23 | Thu 30/11/23 | Thu 30/11/23 | Thu 30/11/23 | 0d | 0d | 0ed | 1 | Thu 30/11/23 | Thu 30/11/23 | 27 November 2023 8:00 AM | 29 November 2023 5:00 PM | As Soon As Possible | NA | Thu 30/11/23 | Thu 30/11/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
117 | 4012 | Yes | Auto Scheduled | Site Wide Waste Removal | 2 d | Fixed Duration | 3 | 2d | 114,115,116 | 1 December 2023 8:00 AM | 4 December 2023 5:00 PM | Fri 1/12/23 | Mon 4/12/23 | Fri 1/12/23 | Mon 4/12/23 | 0d | 0d | 0ed | 1 | Fri 1/12/23 | Mon 4/12/23 | 1 December 2023 8:00 AM | 4 December 2023 5:00 PM | As Soon As Possible | NA | Mon 4/12/23 | Mon 4/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
118 | 4011 | Yes | Auto Scheduled | Site Clearance Certificate | 1 d | Fixed Duration | 3 | 1d | 116,115,117 | 5 December 2023 8:00 AM | 5 December 2023 5:00 PM | Tue 5/12/23 | Tue 5/12/23 | Tue 5/12/23 | Tue 5/12/23 | 0d | 0d | 0ed | 1 | Tue 5/12/23 | Tue 5/12/23 | 5 December 2023 8:00 AM | 5 December 2023 5:00 PM | As Soon As Possible | NA | Tue 5/12/23 | Tue 5/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
119 | 4013 | Yes | Auto Scheduled | Tree, Shrub & Vegetation Removal | 4 d | Fixed Duration | 3 | 4d | 118 | 6 December 2023 8:00 AM | 11 December 2023 5:00 PM | Wed 6/12/23 | Mon 11/12/23 | Wed 6/12/23 | Mon 11/12/23 | 0d | 0d | 0ed | 1 | Wed 6/12/23 | Mon 11/12/23 | 6 December 2023 8:00 AM | 11 December 2023 5:00 PM | As Soon As Possible | NA | Mon 11/12/23 | Mon 11/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
120 | 4014 | Yes | Auto Scheduled | Demolition & Tree Removal Complete | 1 d | Fixed Duration | 3 | 0d | 119 | 11 December 2023 8:00 AM | 11 December 2023 5:00 PM | Mon 11/12/23 | Mon 11/12/23 | Mon 11/12/23 | Mon 11/12/23 | 0d | 0d | 0ed | 1 | Mon 11/12/23 | Mon 11/12/23 | 11 December 2023 5:00 PM | 11 December 2023 5:00 PM | As Soon As Possible | NA | Mon 11/12/23 | Mon 11/12/23 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 4.2.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
121 | 4851 | Yes | Auto Scheduled | MAIN BUILD | 470 d | Fixed Duration | 1 | 446d |  | 13 December 2024 8:00 AM | 9 November 2026 5:00 PM | Fri 13/12/24 | Mon 9/11/26 | Fri 13/12/24 | Mon 9/11/26 | 0d | 0d | 0ed | 8.0000000000000002E-2 | Fri 13/12/24 | NA | 11 December 2024 8:00 AM | 1 October 2026 5:00 PM | As Soon As Possible | NA | Fri 13/12/24 | Fri 13/12/24 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
122 | 4015 | Yes | Auto Scheduled | EARTHWORKS, FOUNDATIONS & IN-GROUND SERVICES | 281 d | Fixed Duration | 2 | 257d |  | 13 December 2024 8:00 AM | 10 February 2026 5:00 PM | Fri 13/12/24 | Tue 10/02/26 | Fri 13/12/24 | Mon 9/11/26 | 189d | 189d | 0ed | 0.46999999999999997 | Fri 13/12/24 | NA | 11 December 2024 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | Fri 13/12/24 | Fri 13/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
123 | 4021 | Yes | Auto Scheduled | Building Approval #01 Required | 0 d | Fixed Duration | 3 | 0d | 124SS | 13 December 2024 8:00 AM | 13 December 2024 8:00 AM | Fri 13/12/24 | Fri 13/12/24 | Fri 13/12/24 | Fri 13/12/24 | 0d | 0d | 0ed | 1 | Fri 13/12/24 | Fri 13/12/24 | 11 December 2024 8:00 AM | 11 December 2024 8:00 AM | As Soon As Possible | NA | Fri 13/12/24 | Fri 13/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.1 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
124 | 4016 | Yes | Auto Scheduled | Establishment of Erosion & Sedimentation Controls | 1 d | Fixed Duration | 3 | 1d | 120,37,45,88 | 13 December 2024 8:00 AM | 13 December 2024 5:00 PM | Fri 13/12/24 | Fri 13/12/24 | Fri 13/12/24 | Fri 13/12/24 | 0d | 0d | 0ed | 1 | Fri 13/12/24 | Fri 13/12/24 | 11 December 2024 8:00 AM | 11 December 2024 5:00 PM | As Soon As Possible | NA | Fri 13/12/24 | Fri 13/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
125 | 4017 | Yes | Auto Scheduled | Construction of Site Entry & Exit, incl. Shaker Grid & Truck Wash Bay | 1 d | Fixed Duration | 3 | 1d | 124 | 19 December 2024 8:00 AM | 19 December 2024 5:00 PM | Thu 19/12/24 | Thu 19/12/24 | Thu 19/12/24 | Thu 19/12/24 | 0d | 0d | 0ed | 1 | Thu 19/12/24 | Thu 19/12/24 | 12 December 2024 8:00 AM | 12 December 2024 5:00 PM | As Soon As Possible | NA | Thu 19/12/24 | Thu 19/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
126 | 4018 | Yes | Auto Scheduled | Site Strip of Top Soil & Cart from Site | 1 d | Fixed Duration | 3 | 1d | 125 | 23 December 2024 8:00 AM | 23 December 2024 5:00 PM | Mon 23/12/24 | Mon 23/12/24 | Mon 23/12/24 | Mon 23/12/24 | 0d | 0d | 0ed | 1 | Mon 23/12/24 | Mon 23/12/24 | 13 December 2024 8:00 AM | 13 December 2024 5:00 PM | As Soon As Possible | NA | Mon 23/12/24 | Mon 23/12/24 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
127 | 4019 | Yes | Auto Scheduled | Bulk Exacavation to BEL | 9 d | Fixed Duration | 3 | 7d | 126 | 24 December 2024 8:00 AM | 15 January 2025 5:00 PM | Tue 24/12/24 | Wed 15/01/25 | Tue 24/12/24 | Wed 15/01/25 | 0d | 0d | 0ed | 1 | Tue 24/12/24 | Wed 15/01/25 | 16 December 2024 8:00 AM | 24 December 2024 5:00 PM | As Soon As Possible | NA | Wed 15/01/25 | Wed 15/01/25 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
128 | 4063 | Yes | Auto Scheduled | CRANE BASE | 265 d | Fixed Duration | 3 | 247d |  | 16 January 2025 8:00 AM | 10 February 2026 5:00 PM | Thu 16/01/25 | Tue 10/02/26 | Thu 16/01/25 | Mon 9/11/26 | 189d | 189d | 0ed | 0.25 | Thu 16/01/25 | NA | 6 January 2025 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | Fri 17/01/25 | Fri 17/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
129 | 4060 | Yes | Auto Scheduled | Detail Excavation to Crane Base | 2 d | Fixed Duration | 4 | 2d | 127 | 16 January 2025 8:00 AM | 17 January 2025 5:00 PM | Thu 16/01/25 | Fri 17/01/25 | Thu 16/01/25 | Fri 17/01/25 | 0d | 0d | 0ed | 1 | Thu 16/01/25 | Fri 17/01/25 | 6 January 2025 8:00 AM | 7 January 2025 5:00 PM | As Soon As Possible | NA | Fri 17/01/25 | Fri 17/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
130 | 4869 | Yes | Auto Scheduled | Crane Piles | 1 d | Fixed Duration | 4 | 1d | 129 | 21 January 2025 8:00 AM | 21 January 2025 5:00 PM | Tue 21/01/25 | Tue 21/01/25 | Tue 21/01/25 | Tue 21/01/25 | 0d | 0d | 0ed | 1 | Tue 21/01/25 | Tue 21/01/25 | 8 January 2025 8:00 AM | 8 January 2025 5:00 PM | As Soon As Possible | NA | Tue 21/01/25 | Tue 21/01/25 | Thu 9/11/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
131 | 4061 | Yes | Auto Scheduled | Formwork Shutters | 2 d | Fixed Duration | 4 | 2d | 130 | 22 January 2025 8:00 AM | 23 January 2025 5:00 PM | Wed 22/01/25 | Thu 23/01/25 | Wed 22/01/25 | Thu 23/01/25 | 0d | 0d | 0ed | 1 | Wed 22/01/25 | Thu 23/01/25 | 9 January 2025 8:00 AM | 10 January 2025 5:00 PM | As Soon As Possible | NA | Thu 23/01/25 | Thu 23/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
132 | 4062 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 131 | 24 January 2025 8:00 AM | 29 January 2025 5:00 PM | Fri 24/01/25 | Wed 29/01/25 | Fri 24/01/25 | Wed 29/01/25 | 0d | 0d | 0ed | 1 | Fri 24/01/25 | Wed 29/01/25 | 13 January 2025 8:00 AM | 15 January 2025 5:00 PM | As Soon As Possible | NA | Wed 29/01/25 | Wed 29/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
133 | 4064 | Yes | Auto Scheduled | Hold Down Bolt Installation | 1 d | Fixed Duration | 4 | 1d | 132 | 30 January 2025 8:00 AM | 30 January 2025 5:00 PM | Thu 30/01/25 | Thu 30/01/25 | Thu 30/01/25 | Thu 30/01/25 | 0d | 0d | 0ed | 1 | Thu 30/01/25 | Thu 30/01/25 | 16 January 2025 8:00 AM | 16 January 2025 5:00 PM | As Soon As Possible | NA | Thu 30/01/25 | Thu 30/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
134 | 4065 | Yes | Auto Scheduled | Pre-Pour Engineering Sign Off | 1 d | Fixed Duration | 4 | 1d | 133 | 31 January 2025 8:00 AM | 31 January 2025 5:00 PM | Fri 31/01/25 | Fri 31/01/25 | Fri 31/01/25 | Fri 31/01/25 | 0d | 0d | 0ed | 1 | Fri 31/01/25 | Fri 31/01/25 | 17 January 2025 8:00 AM | 17 January 2025 5:00 PM | As Soon As Possible | NA | Fri 31/01/25 | Fri 31/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
135 | 4066 | Yes | Auto Scheduled | Concrete Place & Finish | 1 d | Fixed Duration | 4 | 1d | 134 | 3 February 2025 8:00 AM | 3 February 2025 5:00 PM | Mon 3/02/25 | Mon 3/02/25 | Mon 3/02/25 | Mon 3/02/25 | 0d | 0d | 0ed | 1 | Mon 3/02/25 | Mon 3/02/25 | 20 January 2025 8:00 AM | 20 January 2025 5:00 PM | As Soon As Possible | NA | Mon 3/02/25 | Mon 3/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
136 | 4067 | Yes | Auto Scheduled | Curing to Full Strength | 45 d | Fixed Duration | 4 | 28d | 135 | 4 February 2025 8:00 AM | 7 April 2025 5:00 PM | Tue 4/02/25 | Mon 7/04/25 | Tue 4/02/25 | Mon 7/04/25 | 0d | 0d | 0ed | 1 | Tue 4/02/25 | Mon 7/04/25 | 21 January 2025 8:00 AM | 28 February 2025 5:00 PM | As Soon As Possible | NA | Mon 7/04/25 | Mon 7/04/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
137 | 4068 | Yes | Auto Scheduled | Crane Erection | 1 d | Fixed Duration | 4 | 1d | 136 | 8 April 2025 8:00 AM | 8 April 2025 5:00 PM | Tue 8/04/25 | Tue 8/04/25 | Tue 8/04/25 | Tue 8/04/25 | 0d | 0d | 0ed | 1 | Tue 8/04/25 | Tue 8/04/25 | 3 March 2025 8:00 AM | 3 March 2025 5:00 PM | As Soon As Possible | NA | Tue 8/04/25 | Tue 8/04/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
138 | 4842 | Yes | Auto Scheduled | Crane Use | 205 d | Fixed Duration | 4 | 205d | 137 | 9 April 2025 8:00 AM | 6 February 2026 5:00 PM | Wed 9/04/25 | Fri 6/02/26 | Wed 9/04/25 | Thu 5/11/26 | 0d | 189d | 0ed | 5.0000000000000003E-2 | Wed 9/04/25 | NA | 4 March 2025 8:00 AM | 23 December 2025 5:00 PM | As Soon As Possible | NA | Mon 28/04/25 | Mon 28/04/25 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
139 | 4841 | Yes | Auto Scheduled | Crane Dismantle & Removal | 1 d | Fixed Duration | 4 | 1d | 138 | 9 February 2026 8:00 AM | 9 February 2026 5:00 PM | Mon 9/02/26 | Mon 9/02/26 | Fri 6/11/26 | Fri 6/11/26 | 0d | 189d | 0ed | 0 | NA | NA | 24 December 2025 8:00 AM | 24 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
140 | 4843 | Yes | Auto Scheduled | In-Fill Crane Penetration | 1 d | Fixed Duration | 4 | 1d | 139 | 10 February 2026 8:00 AM | 10 February 2026 5:00 PM | Tue 10/02/26 | Tue 10/02/26 | Mon 9/11/26 | Mon 9/11/26 | 189d | 189d | 0ed | 0 | NA | NA | 2 January 2026 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.6.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
141 | 4022 | Yes | Auto Scheduled | POUR 1 | 37 d | Fixed Duration | 3 | 20d |  | 21 January 2025 8:00 AM | 13 March 2025 5:00 PM | Tue 21/01/25 | Thu 13/03/25 | Tue 21/01/25 | Thu 13/03/25 | 0d | 0d | 0ed | 1 | Tue 21/01/25 | Thu 13/03/25 | 8 January 2025 8:00 AM | 5 February 2025 5:00 PM | As Soon As Possible | NA | Tue 28/01/25 | Tue 28/01/25 | Wed 21/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
142 | 4023 | Yes | Auto Scheduled | Detail Excavation - Pad & Strip Footings | 5 d | Fixed Duration | 4 | 5d | 127,129 | 21 January 2025 8:00 AM | 28 January 2025 5:00 PM | Tue 21/01/25 | Tue 28/01/25 | Tue 21/01/25 | Tue 28/01/25 | 0d | 0d | 0ed | 1 | Tue 21/01/25 | Tue 28/01/25 | 8 January 2025 8:00 AM | 14 January 2025 5:00 PM | As Soon As Possible | NA | Tue 28/01/25 | Tue 28/01/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
143 | 4024 | Yes | Auto Scheduled | Screw Pile Foundations (73 piles) | 4 d | Fixed Duration | 4 | 4d | 142,48 | 29 January 2025 8:00 AM | 3 February 2025 5:00 PM | Wed 29/01/25 | Mon 3/02/25 | Wed 29/01/25 | Mon 3/02/25 | 0d | 0d | 0ed | 1 | Wed 29/01/25 | Mon 3/02/25 | 15 January 2025 8:00 AM | 20 January 2025 5:00 PM | As Soon As Possible | NA | Mon 3/02/25 | Mon 3/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
144 | 4025 | Yes | Auto Scheduled | In-Ground Services | 14 d | Fixed Duration | 4 | 3d | 143 | 4 February 2025 8:00 AM | 21 February 2025 5:00 PM | Tue 4/02/25 | Fri 21/02/25 | Tue 4/02/25 | Fri 21/02/25 | 0d | 0d | 0ed | 1 | Tue 4/02/25 | Fri 21/02/25 | 21 January 2025 8:00 AM | 23 January 2025 5:00 PM | As Soon As Possible | NA | Fri 21/02/25 | Fri 21/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
145 | 4026 | Yes | Auto Scheduled | Re-Excavate - Pad & Strip Footings | 4 d | Fixed Duration | 4 | 2d | 144 | 24 February 2025 8:00 AM | 27 February 2025 5:00 PM | Mon 24/02/25 | Thu 27/02/25 | Mon 24/02/25 | Thu 27/02/25 | 0d | 0d | 0ed | 1 | Mon 24/02/25 | Thu 27/02/25 | 24 January 2025 8:00 AM | 28 January 2025 5:00 PM | As Soon As Possible | NA | Thu 27/02/25 | Thu 27/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
146 | 4027 | Yes | Auto Scheduled | Reinforcement Place - Pad & Strip Footings | 3 d | Fixed Duration | 4 | 3d | 145 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | Fri 28/02/25 | Tue 4/03/25 | Fri 28/02/25 | Tue 4/03/25 | 0d | 0d | 0ed | 1 | Fri 28/02/25 | Tue 4/03/25 | 29 January 2025 8:00 AM | 31 January 2025 5:00 PM | As Soon As Possible | NA | Tue 4/03/25 | Tue 4/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
147 | 4028 | Yes | Auto Scheduled | Concrete Place - Pad & Strip Footings | 1 d | Fixed Duration | 4 | 1d | 146 | 5 March 2025 8:00 AM | 5 March 2025 5:00 PM | Wed 5/03/25 | Wed 5/03/25 | Wed 5/03/25 | Wed 5/03/25 | 0d | 0d | 0ed | 1 | Wed 5/03/25 | Wed 5/03/25 | 3 February 2025 8:00 AM | 3 February 2025 5:00 PM | As Soon As Possible | NA | Wed 5/03/25 | Wed 5/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
148 | 4029 | Yes | Auto Scheduled | Subgrade Preparation - Engineered Fill | 2 d | Fixed Duration | 4 | 2d | 147 | 12 March 2025 8:00 AM | 13 March 2025 5:00 PM | Wed 12/03/25 | Thu 13/03/25 | Wed 12/03/25 | Thu 13/03/25 | 0d | 0d | 0ed | 1 | Wed 12/03/25 | Thu 13/03/25 | 4 February 2025 8:00 AM | 5 February 2025 5:00 PM | As Soon As Possible | NA | Thu 13/03/25 | Thu 13/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.7.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
149 | 4030 | Yes | Auto Scheduled | POUR 2 | 37 d | Fixed Duration | 3 | 20d |  | 29 January 2025 8:00 AM | 20 March 2025 5:00 PM | Wed 29/01/25 | Thu 20/03/25 | Wed 29/01/25 | Thu 20/03/25 | 0d | 0d | 0ed | 1 | Wed 29/01/25 | Thu 20/03/25 | 15 January 2025 8:00 AM | 12 February 2025 5:00 PM | As Soon As Possible | NA | Tue 4/02/25 | Tue 4/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
150 | 4031 | Yes | Auto Scheduled | Detail Excavation - Pad & Strip Footings | 5 d | Fixed Duration | 4 | 5d | 142 | 29 January 2025 8:00 AM | 4 February 2025 5:00 PM | Wed 29/01/25 | Tue 4/02/25 | Wed 29/01/25 | Tue 4/02/25 | 0d | 0d | 0ed | 1 | Wed 29/01/25 | Tue 4/02/25 | 15 January 2025 8:00 AM | 21 January 2025 5:00 PM | As Soon As Possible | NA | Tue 4/02/25 | Tue 4/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
151 | 4032 | Yes | Auto Scheduled | Screw Pile Foundations (75 piles) | 6 d | Fixed Duration | 4 | 4d | 143,150 | 20 February 2025 8:00 AM | 27 February 2025 5:00 PM | Thu 20/02/25 | Thu 27/02/25 | Thu 20/02/25 | Thu 27/02/25 | 0d | 0d | 0ed | 1 | Thu 20/02/25 | Thu 27/02/25 | 22 January 2025 8:00 AM | 28 January 2025 5:00 PM | As Soon As Possible | NA | Thu 27/02/25 | Thu 27/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
152 | 4033 | Yes | Auto Scheduled | In-Ground Services | 3 d | Fixed Duration | 4 | 3d | 144,151 | 28 February 2025 8:00 AM | 4 March 2025 5:00 PM | Fri 28/02/25 | Tue 4/03/25 | Fri 28/02/25 | Tue 4/03/25 | 0d | 0d | 0ed | 1 | Fri 28/02/25 | Tue 4/03/25 | 29 January 2025 8:00 AM | 31 January 2025 5:00 PM | As Soon As Possible | NA | Tue 4/03/25 | Tue 4/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
153 | 4034 | Yes | Auto Scheduled | Re-Excavate - Pad & Strip Footings | 6 d | Fixed Duration | 4 | 2d | 145,152 | 5 March 2025 8:00 AM | 12 March 2025 5:00 PM | Wed 5/03/25 | Wed 12/03/25 | Wed 5/03/25 | Wed 12/03/25 | 0d | 0d | 0ed | 1 | Wed 5/03/25 | Wed 12/03/25 | 3 February 2025 8:00 AM | 4 February 2025 5:00 PM | As Soon As Possible | NA | Wed 12/03/25 | Wed 12/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
154 | 4035 | Yes | Auto Scheduled | Reinforcement Place - Pad & Strip Footings | 3 d | Fixed Duration | 4 | 3d | 146,153 | 13 March 2025 8:00 AM | 17 March 2025 5:00 PM | Thu 13/03/25 | Mon 17/03/25 | Thu 13/03/25 | Mon 17/03/25 | 0d | 0d | 0ed | 1 | Thu 13/03/25 | Mon 17/03/25 | 5 February 2025 8:00 AM | 7 February 2025 5:00 PM | As Soon As Possible | NA | Mon 17/03/25 | Mon 17/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
155 | 4036 | Yes | Auto Scheduled | Concrete Place - Pad & Strip Footings | 1 d | Fixed Duration | 4 | 1d | 147,154 | 18 March 2025 8:00 AM | 18 March 2025 5:00 PM | Tue 18/03/25 | Tue 18/03/25 | Tue 18/03/25 | Tue 18/03/25 | 0d | 0d | 0ed | 1 | Tue 18/03/25 | Tue 18/03/25 | 10 February 2025 8:00 AM | 10 February 2025 5:00 PM | As Soon As Possible | NA | Tue 18/03/25 | Tue 18/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
156 | 4037 | Yes | Auto Scheduled | Subgrade Preparation - Engineered Fill | 2 d | Fixed Duration | 4 | 2d | 148,155 | 19 March 2025 8:00 AM | 20 March 2025 5:00 PM | Wed 19/03/25 | Thu 20/03/25 | Wed 19/03/25 | Thu 20/03/25 | 0d | 0d | 0ed | 1 | Wed 19/03/25 | Thu 20/03/25 | 11 February 2025 8:00 AM | 12 February 2025 5:00 PM | As Soon As Possible | NA | Thu 20/03/25 | Thu 20/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.8.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
157 | 4038 | Yes | Auto Scheduled | POUR 3 | 33 d | Fixed Duration | 3 | 27d |  | 20 February 2025 8:00 AM | 7 April 2025 5:00 PM | Thu 20/02/25 | Mon 7/04/25 | Thu 20/02/25 | Mon 19/05/25 | 26d | 26d | 0ed | 0.82999999999999996 | Thu 20/02/25 | NA | 22 January 2025 8:00 AM | 28 February 2025 5:00 PM | As Soon As Possible | NA | Fri 28/02/25 | Fri 28/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
158 | 4039 | Yes | Auto Scheduled | Detail Excavation - Lift Pit, Pad & Strip Footings | 7 d | Fixed Duration | 4 | 5d | 142,150 | 20 February 2025 8:00 AM | 28 February 2025 5:00 PM | Thu 20/02/25 | Fri 28/02/25 | Thu 20/02/25 | Fri 28/02/25 | 0d | 0d | 0ed | 1 | Thu 20/02/25 | Fri 28/02/25 | 22 January 2025 8:00 AM | 29 January 2025 5:00 PM | As Soon As Possible | NA | Fri 28/02/25 | Fri 28/02/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
159 | 4040 | Yes | Auto Scheduled | Screw Pile Foundations (63 piles) | 3 d | Fixed Duration | 4 | 3d | 143,151,158 | 3 March 2025 8:00 AM | 5 March 2025 5:00 PM | Mon 3/03/25 | Wed 5/03/25 | Mon 3/03/25 | Wed 5/03/25 | 0d | 0d | 0ed | 1 | Mon 3/03/25 | Wed 5/03/25 | 30 January 2025 8:00 AM | 3 February 2025 5:00 PM | As Soon As Possible | NA | Wed 5/03/25 | Wed 5/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
160 | 4041 | Yes | Auto Scheduled | In-Ground Services | 3 d | Fixed Duration | 4 | 3d | 144,152,159 | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | Wed 12/03/25 | Fri 14/03/25 | Wed 12/03/25 | Fri 14/03/25 | 0d | 0d | 0ed | 1 | Wed 12/03/25 | Fri 14/03/25 | 4 February 2025 8:00 AM | 6 February 2025 5:00 PM | As Soon As Possible | NA | Fri 14/03/25 | Fri 14/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
161 | 4042 | Yes | Auto Scheduled | Re-Excavate - Lift Pit, Pad & Strip Footings | 2 d | Fixed Duration | 4 | 2d | 145,153,160 | 17 March 2025 8:00 AM | 18 March 2025 5:00 PM | Mon 17/03/25 | Tue 18/03/25 | Mon 17/03/25 | Tue 18/03/25 | 0d | 0d | 0ed | 1 | Mon 17/03/25 | Tue 18/03/25 | 7 February 2025 8:00 AM | 10 February 2025 5:00 PM | As Soon As Possible | NA | Tue 18/03/25 | Tue 18/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
162 | 4054 | Yes | Auto Scheduled | Blinding Slab to Lift Pit | 1 d | Fixed Duration | 4 | 1d | 161 | 19 March 2025 8:00 AM | 19 March 2025 5:00 PM | Wed 19/03/25 | Wed 19/03/25 | Wed 19/03/25 | Wed 19/03/25 | 0d | 0d | 0ed | 1 | Wed 19/03/25 | Wed 19/03/25 | 11 February 2025 8:00 AM | 11 February 2025 5:00 PM | As Soon As Possible | NA | Wed 19/03/25 | Wed 19/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
163 | 4055 | Yes | Auto Scheduled | Formwork to Lift Pit | 2 d | Fixed Duration | 4 | 2d | 162 | 20 March 2025 8:00 AM | 21 March 2025 5:00 PM | Thu 20/03/25 | Fri 21/03/25 | Thu 20/03/25 | Fri 21/03/25 | 0d | 0d | 0ed | 1 | Thu 20/03/25 | Fri 21/03/25 | 12 February 2025 8:00 AM | 13 February 2025 5:00 PM | As Soon As Possible | NA | Fri 21/03/25 | Fri 21/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
164 | 4043 | Yes | Auto Scheduled | Reinforcement Place - Lift Pit, Pad & Strip Footings | 4 d | Fixed Duration | 4 | 4d | 146,154,161,163 | 24 March 2025 8:00 AM | 27 March 2025 5:00 PM | Mon 24/03/25 | Thu 27/03/25 | Mon 24/03/25 | Thu 27/03/25 | 0d | 0d | 0ed | 1 | Mon 24/03/25 | Thu 27/03/25 | 14 February 2025 8:00 AM | 19 February 2025 5:00 PM | As Soon As Possible | NA | Thu 27/03/25 | Thu 27/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
165 | 4044 | Yes | Auto Scheduled | Concrete Place - Lift Pit, Pad & Strip Footings | 2 d | Fixed Duration | 4 | 2d | 147,155,164 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | Fri 28/03/25 | Mon 31/03/25 | Fri 28/03/25 | Mon 31/03/25 | 0d | 0d | 0ed | 1 | Fri 28/03/25 | Mon 31/03/25 | 20 February 2025 8:00 AM | 21 February 2025 5:00 PM | As Soon As Possible | NA | Mon 31/03/25 | Mon 31/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
166 | 4056 | Yes | Auto Scheduled | Water Proofing to Lift Pit, plus Curing & Protection Board | 3 d | Fixed Duration | 4 | 3d | 165 | 1 April 2025 8:00 AM | 3 April 2025 5:00 PM | Tue 1/04/25 | Thu 3/04/25 | Tue 13/05/25 | Thu 15/05/25 | 0d | 26d | 0ed | 0 | NA | NA | 24 February 2025 8:00 AM | 26 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
167 | 4045 | Yes | Auto Scheduled | Subgrade Preparation - Engineered Fill & Lift Pit Backfill | 2 d | Fixed Duration | 4 | 2d | 148,156,165,166 | 4 April 2025 8:00 AM | 7 April 2025 5:00 PM | Fri 4/04/25 | Mon 7/04/25 | Fri 16/05/25 | Mon 19/05/25 | 0d | 26d | 0ed | 0 | NA | NA | 27 February 2025 8:00 AM | 28 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.9.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
168 | 4046 | Yes | Auto Scheduled | POUR 4 | 27 d | Fixed Duration | 3 | 23d |  | 3 March 2025 8:00 AM | 8 April 2025 5:00 PM | Mon 3/03/25 | Tue 8/04/25 | Mon 3/03/25 | Mon 9/11/26 | 396d | 396d | 0ed | 0.35999999999999999 | Mon 3/03/25 | NA | 30 January 2025 8:00 AM | 3 March 2025 5:00 PM | As Soon As Possible | NA | Thu 6/03/25 | Thu 6/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
169 | 4047 | Yes | Auto Scheduled | Detail Excavation - Pad & Strip Footings | 4 d | Fixed Duration | 4 | 4d | 142,150,158 | 3 March 2025 8:00 AM | 6 March 2025 5:00 PM | Mon 3/03/25 | Thu 6/03/25 | Mon 3/03/25 | Mon 9/11/26 | 419d | 419d | 0ed | 0.84999999999999998 | Mon 3/03/25 | NA | 30 January 2025 8:00 AM | 4 February 2025 5:00 PM | As Soon As Possible | NA | Thu 6/03/25 | Thu 6/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
170 | 4048 | Yes | Auto Scheduled | Screw Pile Foundations (27 piles) | 2 d | Fixed Duration | 4 | 2d | 143,151,159,169 | 13 March 2025 8:00 AM | 14 March 2025 5:00 PM | Thu 13/03/25 | Fri 14/03/25 | Thu 13/03/25 | Fri 14/03/25 | 0d | 0d | 0ed | 1 | Thu 13/03/25 | Fri 14/03/25 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | As Soon As Possible | NA | Fri 14/03/25 | Fri 14/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
171 | 4049 | Yes | Auto Scheduled | In-Ground Services | 3 d | Fixed Duration | 4 | 3d | 144,152,160,170 | 17 March 2025 8:00 AM | 19 March 2025 5:00 PM | Mon 17/03/25 | Wed 19/03/25 | Thu 15/10/26 | Mon 19/10/26 | 0d | 395d | 0ed | 0 | NA | NA | 7 February 2025 8:00 AM | 11 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
172 | 4050 | Yes | Auto Scheduled | Re-Excavate - Pad & Strip Footings | 2 d | Fixed Duration | 4 | 2d | 145,153,161,171 | 20 March 2025 8:00 AM | 21 March 2025 5:00 PM | Thu 20/03/25 | Fri 21/03/25 | Tue 20/10/26 | Wed 21/10/26 | 4d | 395d | 0ed | 0 | NA | NA | 12 February 2025 8:00 AM | 13 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
173 | 4051 | Yes | Auto Scheduled | Reinforcement Place - Pad & Strip Footings | 2 d | Fixed Duration | 4 | 2d | 146,154,164,172 | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | Fri 28/03/25 | Mon 31/03/25 | Thu 22/10/26 | Fri 23/10/26 | 0d | 391d | 0ed | 0 | NA | NA | 20 February 2025 8:00 AM | 21 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
174 | 4052 | Yes | Auto Scheduled | Concrete Place - Pad & Strip Footings | 1 d | Fixed Duration | 4 | 1d | 147,155,165,173 | 1 April 2025 8:00 AM | 1 April 2025 5:00 PM | Tue 1/04/25 | Tue 1/04/25 | Mon 26/10/26 | Mon 26/10/26 | 4d | 391d | 0ed | 0 | NA | NA | 24 February 2025 8:00 AM | 24 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
175 | 4053 | Yes | Auto Scheduled | Subgrade Preparation - Engineered Fill | 1 d | Fixed Duration | 4 | 1d | 148,156,167,174 | 8 April 2025 8:00 AM | 8 April 2025 5:00 PM | Tue 8/04/25 | Tue 8/04/25 | Tue 27/10/26 | Tue 27/10/26 | 11d | 387d | 0ed | 0 | NA | NA | 3 March 2025 8:00 AM | 3 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.10.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
176 | 4059 | Yes | Auto Scheduled | DETENTION TANK | 17 d | Fixed Duration | 3 | 17d |  | 13 March 2025 8:00 AM | 4 April 2025 5:00 PM | Thu 13/03/25 | Fri 4/04/25 | Thu 13/03/25 | Fri 4/04/25 | 0d | 0d | 0ed | 1 | Thu 13/03/25 | Fri 4/04/25 | 5 February 2025 8:00 AM | 27 February 2025 5:00 PM | As Soon As Possible | NA | Fri 14/03/25 | Fri 14/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
177 | 4069 | Yes | Auto Scheduled | Detail Excavation - Detention Tank | 2 d | Fixed Duration | 4 | 2d | 169 | 13 March 2025 8:00 AM | 14 March 2025 5:00 PM | Thu 13/03/25 | Fri 14/03/25 | Thu 13/03/25 | Fri 14/03/25 | 0d | 0d | 0ed | 1 | Thu 13/03/25 | Fri 14/03/25 | 5 February 2025 8:00 AM | 6 February 2025 5:00 PM | As Soon As Possible | NA | Fri 14/03/25 | Fri 14/03/25 | Thu 22/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
178 | 4070 | Yes | Auto Scheduled | Formwork - Base Slab Edge & Sump | 1 d | Fixed Duration | 4 | 1d | 177 | 17 March 2025 8:00 AM | 17 March 2025 5:00 PM | Mon 17/03/25 | Mon 17/03/25 | Mon 17/03/25 | Mon 17/03/25 | 0d | 0d | 0ed | 1 | Mon 17/03/25 | Mon 17/03/25 | 7 February 2025 8:00 AM | 7 February 2025 5:00 PM | As Soon As Possible | NA | Mon 17/03/25 | Mon 17/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
179 | 4071 | Yes | Auto Scheduled | Reinforcement Place - Base Slab | 2 d | Fixed Duration | 4 | 2d | 178 | 18 March 2025 8:00 AM | 19 March 2025 5:00 PM | Tue 18/03/25 | Wed 19/03/25 | Tue 18/03/25 | Wed 19/03/25 | 0d | 0d | 0ed | 1 | Tue 18/03/25 | Wed 19/03/25 | 10 February 2025 8:00 AM | 11 February 2025 5:00 PM | As Soon As Possible | NA | Wed 19/03/25 | Wed 19/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
180 | 4072 | Yes | Auto Scheduled | Concrete Place - Base Slab | 1 d | Fixed Duration | 4 | 1d | 179 | 20 March 2025 8:00 AM | 20 March 2025 5:00 PM | Thu 20/03/25 | Thu 20/03/25 | Thu 20/03/25 | Thu 20/03/25 | 0d | 0d | 0ed | 1 | Thu 20/03/25 | Thu 20/03/25 | 12 February 2025 8:00 AM | 12 February 2025 5:00 PM | As Soon As Possible | NA | Thu 20/03/25 | Thu 20/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
181 | 4073 | Yes | Auto Scheduled | Core-Filled Block Work Walls | 4 d | Fixed Duration | 4 | 4d | 180 | 21 March 2025 8:00 AM | 26 March 2025 5:00 PM | Fri 21/03/25 | Wed 26/03/25 | Fri 21/03/25 | Wed 26/03/25 | 0d | 0d | 0ed | 1 | Fri 21/03/25 | Wed 26/03/25 | 13 February 2025 8:00 AM | 18 February 2025 5:00 PM | As Soon As Possible | NA | Wed 26/03/25 | Wed 26/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
182 | 4074 | Yes | Auto Scheduled | Formwork - Lid | 2 d | Fixed Duration | 4 | 2d | 181 | 27 March 2025 8:00 AM | 28 March 2025 5:00 PM | Thu 27/03/25 | Fri 28/03/25 | Thu 27/03/25 | Fri 28/03/25 | 0d | 0d | 0ed | 1 | Thu 27/03/25 | Fri 28/03/25 | 19 February 2025 8:00 AM | 20 February 2025 5:00 PM | As Soon As Possible | NA | Fri 28/03/25 | Fri 28/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
183 | 4075 | Yes | Auto Scheduled | Reinforcement Place - Lid | 1 d | Fixed Duration | 4 | 1d | 182 | 31 March 2025 8:00 AM | 31 March 2025 5:00 PM | Mon 31/03/25 | Mon 31/03/25 | Mon 31/03/25 | Mon 31/03/25 | 0d | 0d | 0ed | 1 | Mon 31/03/25 | Mon 31/03/25 | 21 February 2025 8:00 AM | 21 February 2025 5:00 PM | As Soon As Possible | NA | Mon 31/03/25 | Mon 31/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
184 | 4076 | Yes | Auto Scheduled | Concrete Place - Lid | 1 d | Fixed Duration | 4 | 1d | 183 | 1 April 2025 8:00 AM | 1 April 2025 5:00 PM | Tue 1/04/25 | Tue 1/04/25 | Tue 1/04/25 | Tue 1/04/25 | 0d | 0d | 0ed | 1 | Tue 1/04/25 | Tue 1/04/25 | 24 February 2025 8:00 AM | 24 February 2025 5:00 PM | As Soon As Possible | NA | Tue 1/04/25 | Tue 1/04/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
185 | 4077 | Yes | Auto Scheduled | Upstream & Downstream Stormwater Connections | 3 d | Fixed Duration | 4 | 3d | 184 | 2 April 2025 8:00 AM | 4 April 2025 5:00 PM | Wed 2/04/25 | Fri 4/04/25 | Wed 2/04/25 | Fri 4/04/25 | 0d | 0d | 0ed | 1 | Wed 2/04/25 | Fri 4/04/25 | 25 February 2025 8:00 AM | 27 February 2025 5:00 PM | As Soon As Possible | NA | Fri 4/04/25 | Fri 4/04/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.1.11.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
186 | 4078 | Yes | Auto Scheduled | CONCRETE STRUCTURE | 231 d | Fixed Duration | 2 | 231d |  | 14 March 2025 8:00 AM | 18 February 2026 5:00 PM | Fri 14/03/25 | Wed 18/02/26 | Fri 14/03/25 | Mon 9/11/26 | 183d | 183d | 0ed | 2.9999999999999999E-2 | Fri 14/03/25 | NA | 6 February 2025 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | Thu 20/03/25 | Thu 20/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
187 | 4079 | Yes | Auto Scheduled | LEVEL 1 - POUR 1 | 19 d | Fixed Duration | 3 | 19d |  | 14 March 2025 8:00 AM | 9 April 2025 5:00 PM | Fri 14/03/25 | Wed 9/04/25 | Fri 14/03/25 | Thu 10/04/25 | 1d | 1d | 0ed | 0.23999999999999999 | Fri 14/03/25 | NA | 6 February 2025 8:00 AM | 4 March 2025 5:00 PM | As Soon As Possible | NA | Thu 20/03/25 | Thu 20/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
188 | 4080 | Yes | Auto Scheduled | Core-Filled Block Work to South & East | 9 d | Fixed Duration | 4 | 9d | 147,148 | 14 March 2025 8:00 AM | 26 March 2025 5:00 PM | Fri 14/03/25 | Wed 26/03/25 | Fri 14/03/25 | Thu 27/03/25 | 0d | 1d | 0ed | 0.5 | Fri 14/03/25 | NA | 6 February 2025 8:00 AM | 18 February 2025 5:00 PM | As Soon As Possible | NA | Thu 20/03/25 | Thu 20/03/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
189 | 4081 | Yes | Auto Scheduled | Sand Blinding/ Levelling Layer | 2 d | Fixed Duration | 4 | 2d | 188 | 27 March 2025 8:00 AM | 28 March 2025 5:00 PM | Thu 27/03/25 | Fri 28/03/25 | Fri 28/03/25 | Mon 31/03/25 | 0d | 1d | 0ed | 0 | NA | NA | 19 February 2025 8:00 AM | 20 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
190 | 4085 | Yes | Auto Scheduled | Formwork Edgeboards | 3 d | Fixed Duration | 4 | 3d | 189 | 31 March 2025 8:00 AM | 2 April 2025 5:00 PM | Mon 31/03/25 | Wed 2/04/25 | Tue 1/04/25 | Thu 3/04/25 | 0d | 1d | 0ed | 0 | NA | NA | 21 February 2025 8:00 AM | 25 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
191 | 4082 | Yes | Auto Scheduled | Vapour Proof Membrane | 1 d | Fixed Duration | 4 | 1d | 190 | 3 April 2025 8:00 AM | 3 April 2025 5:00 PM | Thu 3/04/25 | Thu 3/04/25 | Fri 4/04/25 | Fri 4/04/25 | 0d | 1d | 0ed | 0 | NA | NA | 26 February 2025 8:00 AM | 26 February 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
192 | 4083 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 191 | 4 April 2025 8:00 AM | 8 April 2025 5:00 PM | Fri 4/04/25 | Tue 8/04/25 | Mon 7/04/25 | Wed 9/04/25 | 0d | 1d | 0ed | 0 | NA | NA | 27 February 2025 8:00 AM | 3 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
193 | 4086 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 192 | 9 April 2025 8:00 AM | 9 April 2025 5:00 PM | Wed 9/04/25 | Wed 9/04/25 | Thu 10/04/25 | Thu 10/04/25 | 0d | 1d | 0ed | 0 | NA | NA | 4 March 2025 8:00 AM | 4 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.1.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
194 | 4087 | Yes | Auto Scheduled | LEVEL 1 - POUR 2 | 19 d | Fixed Duration | 3 | 19d |  | 27 March 2025 8:00 AM | 24 April 2025 5:00 PM | Thu 27/03/25 | Thu 24/04/25 | Thu 27/03/25 | Thu 24/04/25 | 0d | 0d | 0ed | 0.46999999999999997 | Thu 27/03/25 | NA | 19 February 2025 8:00 AM | 17 March 2025 5:00 PM | As Soon As Possible | NA | Tue 8/04/25 | Tue 8/04/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
195 | 4088 | Yes | Auto Scheduled | Core-Filled Block Work to North & West | 9 d | Fixed Duration | 4 | 9d | 188,155,156 | 27 March 2025 8:00 AM | 8 April 2025 5:00 PM | Thu 27/03/25 | Tue 8/04/25 | Thu 27/03/25 | Tue 8/04/25 | 0d | 0d | 0ed | 1 | Thu 27/03/25 | Tue 8/04/25 | 19 February 2025 8:00 AM | 3 March 2025 5:00 PM | As Soon As Possible | NA | Tue 8/04/25 | Tue 8/04/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
196 | 4089 | Yes | Auto Scheduled | Sand Blinding/ Levelling Layer | 2 d | Fixed Duration | 4 | 2d | 189,195 | 9 April 2025 8:00 AM | 10 April 2025 5:00 PM | Wed 9/04/25 | Thu 10/04/25 | Wed 9/04/25 | Thu 10/04/25 | 0d | 0d | 0ed | 0 | NA | NA | 4 March 2025 8:00 AM | 5 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
197 | 4090 | Yes | Auto Scheduled | Formwork Edgeboards | 3 d | Fixed Duration | 4 | 3d | 190,196 | 11 April 2025 8:00 AM | 15 April 2025 5:00 PM | Fri 11/04/25 | Tue 15/04/25 | Fri 11/04/25 | Tue 15/04/25 | 0d | 0d | 0ed | 0 | NA | NA | 6 March 2025 8:00 AM | 10 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
198 | 4091 | Yes | Auto Scheduled | Vapour Proof Membrane | 1 d | Fixed Duration | 4 | 1d | 191,197 | 16 April 2025 8:00 AM | 16 April 2025 5:00 PM | Wed 16/04/25 | Wed 16/04/25 | Wed 16/04/25 | Wed 16/04/25 | 0d | 0d | 0ed | 0 | NA | NA | 11 March 2025 8:00 AM | 11 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
199 | 4092 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 192,198 | 17 April 2025 8:00 AM | 23 April 2025 5:00 PM | Thu 17/04/25 | Wed 23/04/25 | Thu 17/04/25 | Wed 23/04/25 | 0d | 0d | 0ed | 0 | NA | NA | 12 March 2025 8:00 AM | 14 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
200 | 4093 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 193,199 | 24 April 2025 8:00 AM | 24 April 2025 5:00 PM | Thu 24/04/25 | Thu 24/04/25 | Thu 24/04/25 | Thu 24/04/25 | 0d | 0d | 0ed | 0 | NA | NA | 17 March 2025 8:00 AM | 17 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
201 | 4094 | Yes | Auto Scheduled | LEVEL 1 - POUR 3 | 17 d | Fixed Duration | 3 | 17d |  | 9 April 2025 8:00 AM | 7 May 2025 5:00 PM | Wed 9/04/25 | Wed 7/05/25 | Tue 20/05/25 | Wed 11/06/25 | 25d | 25d | 0ed | 0 | NA | NA | 4 March 2025 8:00 AM | 26 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
202 | 4095 | Yes | Auto Scheduled | Core-Filled Block Work to Cores & Service Rooms | 9 d | Fixed Duration | 4 | 9d | 165,167,195 | 9 April 2025 8:00 AM | 23 April 2025 5:00 PM | Wed 9/04/25 | Wed 23/04/25 | Tue 20/05/25 | Fri 30/05/25 | 0d | 25d | 0ed | 0 | NA | NA | 4 March 2025 8:00 AM | 14 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
203 | 4096 | Yes | Auto Scheduled | Sand Blinding/ Levelling Layer | 2 d | Fixed Duration | 4 | 2d | 196,202 | 24 April 2025 8:00 AM | 28 April 2025 5:00 PM | Thu 24/04/25 | Mon 28/04/25 | Mon 2/06/25 | Tue 3/06/25 | 0d | 25d | 0ed | 0 | NA | NA | 17 March 2025 8:00 AM | 18 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
204 | 4097 | Yes | Auto Scheduled | Formwork Edgeboards | 2 d | Fixed Duration | 4 | 2d | 197,203 | 29 April 2025 8:00 AM | 30 April 2025 5:00 PM | Tue 29/04/25 | Wed 30/04/25 | Wed 4/06/25 | Thu 5/06/25 | 0d | 25d | 0ed | 0 | NA | NA | 19 March 2025 8:00 AM | 20 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
205 | 4098 | Yes | Auto Scheduled | Vapour Proof Membrane | 1 d | Fixed Duration | 4 | 1d | 198,204 | 1 May 2025 8:00 AM | 1 May 2025 5:00 PM | Thu 1/05/25 | Thu 1/05/25 | Fri 6/06/25 | Fri 6/06/25 | 0d | 25d | 0ed | 0 | NA | NA | 21 March 2025 8:00 AM | 21 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
206 | 4099 | Yes | Auto Scheduled | Reinforcement Place | 2 d | Fixed Duration | 4 | 2d | 199,205 | 2 May 2025 8:00 AM | 6 May 2025 5:00 PM | Fri 2/05/25 | Tue 6/05/25 | Mon 9/06/25 | Tue 10/06/25 | 0d | 25d | 0ed | 0 | NA | NA | 24 March 2025 8:00 AM | 25 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
207 | 4100 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 206,200 | 7 May 2025 8:00 AM | 7 May 2025 5:00 PM | Wed 7/05/25 | Wed 7/05/25 | Wed 11/06/25 | Wed 11/06/25 | 1d | 25d | 0ed | 0 | NA | NA | 26 March 2025 8:00 AM | 26 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
208 | 4101 | Yes | Auto Scheduled | LEVEL 1 - POUR 4 | 9 d | Fixed Duration | 3 | 9d |  | 29 April 2025 8:00 AM | 12 May 2025 5:00 PM | Tue 29/04/25 | Mon 12/05/25 | Wed 28/10/26 | Mon 9/11/26 | 376d | 376d | 0ed | 0 | NA | NA | 19 March 2025 8:00 AM | 31 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
209 | 4102 | Yes | Auto Scheduled | Sand Blinding/ Levelling Layer | 2 d | Fixed Duration | 4 | 2d | 175,185,203 | 29 April 2025 8:00 AM | 30 April 2025 5:00 PM | Tue 29/04/25 | Wed 30/04/25 | Wed 28/10/26 | Thu 29/10/26 | 0d | 376d | 0ed | 0 | NA | NA | 19 March 2025 8:00 AM | 20 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
210 | 4103 | Yes | Auto Scheduled | Formwork Edgeboards | 3 d | Fixed Duration | 4 | 3d | 204,209 | 1 May 2025 8:00 AM | 6 May 2025 5:00 PM | Thu 1/05/25 | Tue 6/05/25 | Fri 30/10/26 | Tue 3/11/26 | 0d | 376d | 0ed | 0 | NA | NA | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
211 | 4104 | Yes | Auto Scheduled | Vapour Proof Membrane | 1 d | Fixed Duration | 4 | 1d | 205,210 | 7 May 2025 8:00 AM | 7 May 2025 5:00 PM | Wed 7/05/25 | Wed 7/05/25 | Wed 4/11/26 | Wed 4/11/26 | 0d | 376d | 0ed | 0 | NA | NA | 26 March 2025 8:00 AM | 26 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
212 | 4105 | Yes | Auto Scheduled | Reinforcement Place | 2 d | Fixed Duration | 4 | 2d | 206,211 | 8 May 2025 8:00 AM | 9 May 2025 5:00 PM | Thu 8/05/25 | Fri 9/05/25 | Thu 5/11/26 | Fri 6/11/26 | 0d | 376d | 0ed | 0 | NA | NA | 27 March 2025 8:00 AM | 28 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
213 | 4106 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 207,212 | 12 May 2025 8:00 AM | 12 May 2025 5:00 PM | Mon 12/05/25 | Mon 12/05/25 | Mon 9/11/26 | Mon 9/11/26 | 376d | 376d | 0ed | 0 | NA | NA | 31 March 2025 8:00 AM | 31 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
214 | 4107 | Yes | Auto Scheduled | LEVEL 2 - BUILDING A, POUR 1 | 26 d | Fixed Duration | 3 | 25d |  | 9 April 2025 8:00 AM | 20 May 2025 5:00 PM | Wed 9/04/25 | Tue 20/05/25 | Wed 9/04/25 | Thu 22/05/25 | 2d | 2d | 0ed | 0 | Wed 9/04/25 | NA | 4 March 2025 5:00 PM | 8 April 2025 5:00 PM | As Soon As Possible | NA | Wed 9/04/25 | Wed 9/04/25 | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
215 | 4845 | Yes | Auto Scheduled | Building Approval #02 - Required | 0 d | Fixed Duration | 4 | 0d | 193 | 9 April 2025 8:00 AM | 9 April 2025 8:00 AM | Wed 9/04/25 | Wed 9/04/25 | Wed 9/04/25 | Wed 9/04/25 | 0d | 0d | 0ed | 1 | Wed 9/04/25 | Wed 9/04/25 | 4 March 2025 5:00 PM | 4 March 2025 5:00 PM | As Soon As Possible | NA | Wed 9/04/25 | Wed 9/04/25 | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.1 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
216 | 4108 | Yes | Auto Scheduled | Formwork Deck, incl. Columns (3 sides) | 8 d | Fixed Duration | 4 | 8d | 193 | 10 April 2025 8:00 AM | 23 April 2025 5:00 PM | Thu 10/04/25 | Wed 23/04/25 | Fri 11/04/25 | Thu 24/04/25 | 0d | 1d | 0ed | 0 | NA | NA | 5 March 2025 8:00 AM | 14 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
217 | 4109 | Yes | Auto Scheduled | Reinforcement Place - Columns | 2 d | Fixed Duration | 4 | 2d | 216 | 24 April 2025 8:00 AM | 28 April 2025 5:00 PM | Thu 24/04/25 | Mon 28/04/25 | Tue 29/04/25 | Wed 30/04/25 | 0d | 2d | 0ed | 0 | NA | NA | 17 March 2025 8:00 AM | 18 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
218 | 4110 | Yes | Auto Scheduled | Formwork - Close Columns | 1 d | Fixed Duration | 4 | 1d | 217 | 29 April 2025 8:00 AM | 29 April 2025 5:00 PM | Tue 29/04/25 | Tue 29/04/25 | Thu 1/05/25 | Thu 1/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 19 March 2025 8:00 AM | 19 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
219 | 4111 | Yes | Auto Scheduled | Concrete Place - Columns | 1 d | Fixed Duration | 4 | 1d | 218 | 30 April 2025 8:00 AM | 30 April 2025 5:00 PM | Wed 30/04/25 | Wed 30/04/25 | Fri 2/05/25 | Fri 2/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 20 March 2025 8:00 AM | 20 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
220 | 4127 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 219 | 1 May 2025 8:00 AM | 6 May 2025 5:00 PM | Thu 1/05/25 | Tue 6/05/25 | Tue 6/05/25 | Thu 8/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 21 March 2025 8:00 AM | 25 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
221 | 4112 | Yes | Auto Scheduled | Reinforcement Place - Deck incl. Beams | 6 d | Fixed Duration | 4 | 6d | 220 | 7 May 2025 8:00 AM | 14 May 2025 5:00 PM | Wed 7/05/25 | Wed 14/05/25 | Fri 9/05/25 | Fri 16/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 26 March 2025 8:00 AM | 2 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
222 | 4113 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 3 d | Fixed Duration | 4 | 3d | 221 | 15 May 2025 8:00 AM | 19 May 2025 5:00 PM | Thu 15/05/25 | Mon 19/05/25 | Mon 19/05/25 | Wed 21/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 3 April 2025 8:00 AM | 7 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
223 | 4114 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 222 | 20 May 2025 8:00 AM | 20 May 2025 5:00 PM | Tue 20/05/25 | Tue 20/05/25 | Thu 22/05/25 | Thu 22/05/25 | 0d | 2d | 0ed | 0 | NA | NA | 8 April 2025 8:00 AM | 8 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.5.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
224 | 4115 | Yes | Auto Scheduled | LEVEL 2 - BUILDING B, POUR 2 | 25 d | Fixed Duration | 3 | 25d |  | 28 April 2025 8:00 AM | 2 June 2025 5:00 PM | Mon 28/04/25 | Mon 2/06/25 | Mon 28/04/25 | Mon 2/06/25 | 0d | 0d | 0ed | 0 | NA | NA | 18 March 2025 8:00 AM | 23 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
225 | 4116 | Yes | Auto Scheduled | Formwork Deck, incl. Columns (3 sides) | 8 d | Fixed Duration | 4 | 8d | 200,216 | 28 April 2025 8:00 AM | 8 May 2025 5:00 PM | Mon 28/04/25 | Thu 8/05/25 | Mon 28/04/25 | Thu 8/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 18 March 2025 8:00 AM | 27 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
226 | 4117 | Yes | Auto Scheduled | Reinforcement Place - Columns | 2 d | Fixed Duration | 4 | 2d | 217,225 | 9 May 2025 8:00 AM | 12 May 2025 5:00 PM | Fri 9/05/25 | Mon 12/05/25 | Fri 9/05/25 | Mon 12/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 28 March 2025 8:00 AM | 31 March 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
227 | 4118 | Yes | Auto Scheduled | Formwork - Close Columns | 1 d | Fixed Duration | 4 | 1d | 218,226 | 13 May 2025 8:00 AM | 13 May 2025 5:00 PM | Tue 13/05/25 | Tue 13/05/25 | Tue 13/05/25 | Tue 13/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 1 April 2025 8:00 AM | 1 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
228 | 4119 | Yes | Auto Scheduled | Concrete Place - Columns | 1 d | Fixed Duration | 4 | 1d | 219,227 | 14 May 2025 8:00 AM | 14 May 2025 5:00 PM | Wed 14/05/25 | Wed 14/05/25 | Wed 14/05/25 | Wed 14/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 2 April 2025 8:00 AM | 2 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
229 | 4128 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 220,228 | 15 May 2025 8:00 AM | 19 May 2025 5:00 PM | Thu 15/05/25 | Mon 19/05/25 | Thu 15/05/25 | Mon 19/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 3 April 2025 8:00 AM | 7 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
230 | 4120 | Yes | Auto Scheduled | Reinforcement Place - Deck incl. Beams | 6 d | Fixed Duration | 4 | 6d | 221,229 | 20 May 2025 8:00 AM | 27 May 2025 5:00 PM | Tue 20/05/25 | Tue 27/05/25 | Tue 20/05/25 | Tue 27/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 8 April 2025 8:00 AM | 15 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
231 | 4121 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 3 d | Fixed Duration | 4 | 3d | 222,230 | 28 May 2025 8:00 AM | 30 May 2025 5:00 PM | Wed 28/05/25 | Fri 30/05/25 | Wed 28/05/25 | Fri 30/05/25 | 0d | 0d | 0ed | 0 | NA | NA | 16 April 2025 8:00 AM | 22 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
232 | 4122 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 223,231 | 2 June 2025 8:00 AM | 2 June 2025 5:00 PM | Mon 2/06/25 | Mon 2/06/25 | Mon 2/06/25 | Mon 2/06/25 | 0d | 0d | 0ed | 0 | NA | NA | 23 April 2025 8:00 AM | 23 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.6.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
233 | 4123 | Yes | Auto Scheduled | LEVEL 2 - BUILDING C, POUR 3 | 22 d | Fixed Duration | 3 | 22d |  | 9 May 2025 8:00 AM | 9 June 2025 5:00 PM | Fri 9/05/25 | Mon 9/06/25 | Thu 12/06/25 | Thu 10/07/25 | 22d | 22d | 0ed | 0 | NA | NA | 28 March 2025 8:00 AM | 1 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
234 | 4124 | Yes | Auto Scheduled | Formwork Deck, incl. Columns (3 sides) | 6 d | Fixed Duration | 4 | 6d | 207,225 | 9 May 2025 8:00 AM | 16 May 2025 5:00 PM | Fri 9/05/25 | Fri 16/05/25 | Thu 12/06/25 | Fri 20/06/25 | 0d | 24d | 0ed | 0 | NA | NA | 28 March 2025 8:00 AM | 4 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
235 | 4125 | Yes | Auto Scheduled | Reinforcement Place - Columns | 1 d | Fixed Duration | 4 | 1d | 226,234 | 19 May 2025 8:00 AM | 19 May 2025 5:00 PM | Mon 19/05/25 | Mon 19/05/25 | Mon 23/06/25 | Mon 23/06/25 | 0d | 24d | 0ed | 0 | NA | NA | 7 April 2025 8:00 AM | 7 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
236 | 4126 | Yes | Auto Scheduled | Formwork - Close Columns | 1 d | Fixed Duration | 4 | 1d | 227,235 | 20 May 2025 8:00 AM | 20 May 2025 5:00 PM | Tue 20/05/25 | Tue 20/05/25 | Tue 24/06/25 | Tue 24/06/25 | 0d | 24d | 0ed | 0 | NA | NA | 8 April 2025 8:00 AM | 8 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
237 | 4129 | Yes | Auto Scheduled | Concrete Place - Columns | 1 d | Fixed Duration | 4 | 1d | 228,236 | 21 May 2025 8:00 AM | 21 May 2025 5:00 PM | Wed 21/05/25 | Wed 21/05/25 | Wed 25/06/25 | Wed 25/06/25 | 0d | 24d | 0ed | 0 | NA | NA | 9 April 2025 8:00 AM | 9 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
238 | 4130 | Yes | Auto Scheduled | Service Deck Work | 2 d | Fixed Duration | 4 | 2d | 229,237 | 22 May 2025 8:00 AM | 23 May 2025 5:00 PM | Thu 22/05/25 | Fri 23/05/25 | Thu 26/06/25 | Fri 27/06/25 | 2d | 24d | 0ed | 0 | NA | NA | 10 April 2025 8:00 AM | 11 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
239 | 4131 | Yes | Auto Scheduled | Reinforcement Plan - Deck incl. Beams | 5 d | Fixed Duration | 4 | 5d | 230,238 | 28 May 2025 8:00 AM | 3 June 2025 5:00 PM | Wed 28/05/25 | Tue 3/06/25 | Mon 30/06/25 | Fri 4/07/25 | 0d | 22d | 0ed | 0 | NA | NA | 16 April 2025 8:00 AM | 24 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
240 | 4132 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 3 d | Fixed Duration | 4 | 3d | 231,239 | 4 June 2025 8:00 AM | 6 June 2025 5:00 PM | Wed 4/06/25 | Fri 6/06/25 | Mon 7/07/25 | Wed 9/07/25 | 0d | 22d | 0ed | 0 | NA | NA | 28 April 2025 8:00 AM | 30 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
241 | 4133 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 232,240 | 9 June 2025 8:00 AM | 9 June 2025 5:00 PM | Mon 9/06/25 | Mon 9/06/25 | Thu 10/07/25 | Thu 10/07/25 | 0d | 22d | 0ed | 0 | NA | NA | 1 May 2025 8:00 AM | 1 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.7.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
242 | 4134 | Yes | Auto Scheduled | LEVEL 3 - BUILDING A, POUR 1 | 19 d | Fixed Duration | 3 | 19d |  | 21 May 2025 8:00 AM | 17 June 2025 5:00 PM | Wed 21/05/25 | Tue 17/06/25 | Fri 23/05/25 | Tue 1/07/25 | 2d | 2d | 0ed | 0 | NA | NA | 9 April 2025 8:00 AM | 9 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
243 | 4135 | Yes | Auto Scheduled | Core-Filled Block Walls | 7 d | Fixed Duration | 4 | 7d | 223 | 21 May 2025 8:00 AM | 29 May 2025 5:00 PM | Wed 21/05/25 | Thu 29/05/25 | Fri 23/05/25 | Mon 2/06/25 | 0d | 2d | 0ed | 0 | NA | NA | 9 April 2025 8:00 AM | 17 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
244 | 4136 | Yes | Auto Scheduled | Formwork Deck | 5 d | Fixed Duration | 4 | 5d | 243 | 30 May 2025 8:00 AM | 5 June 2025 5:00 PM | Fri 30/05/25 | Thu 5/06/25 | Mon 9/06/25 | Fri 13/06/25 | 0d | 6d | 0ed | 0 | NA | NA | 22 April 2025 8:00 AM | 29 April 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
245 | 4138 | Yes | Auto Scheduled | Service Deck Work | 2 d | Fixed Duration | 4 | 2d | 244 | 6 June 2025 8:00 AM | 9 June 2025 5:00 PM | Fri 6/06/25 | Mon 9/06/25 | Mon 23/06/25 | Tue 24/06/25 | 0d | 10d | 0ed | 0 | NA | NA | 30 April 2025 8:00 AM | 1 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
246 | 4137 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 245 | 10 June 2025 8:00 AM | 12 June 2025 5:00 PM | Tue 10/06/25 | Thu 12/06/25 | Wed 25/06/25 | Fri 27/06/25 | 0d | 10d | 0ed | 0 | NA | NA | 2 May 2025 8:00 AM | 7 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
247 | 4139 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 1 d | Fixed Duration | 4 | 1d | 246 | 13 June 2025 8:00 AM | 13 June 2025 5:00 PM | Fri 13/06/25 | Fri 13/06/25 | Mon 30/06/25 | Mon 30/06/25 | 0d | 10d | 0ed | 0 | NA | NA | 8 May 2025 8:00 AM | 8 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
248 | 4140 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 247 | 17 June 2025 8:00 AM | 17 June 2025 5:00 PM | Tue 17/06/25 | Tue 17/06/25 | Tue 1/07/25 | Tue 1/07/25 | 0d | 10d | 0ed | 0 | NA | NA | 9 May 2025 8:00 AM | 9 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.8.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
249 | 4141 | Yes | Auto Scheduled | LEVEL 3 - BUILDING B, POUR 2 | 27 d | Fixed Duration | 3 | 27d |  | 3 June 2025 8:00 AM | 10 July 2025 5:00 PM | Tue 3/06/25 | Thu 10/07/25 | Tue 3/06/25 | Thu 10/07/25 | 0d | 0d | 0ed | 0 | NA | NA | 24 April 2025 8:00 AM | 3 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
250 | 4142 | Yes | Auto Scheduled | Core-Filled Block Walls | 9 d | Fixed Duration | 4 | 9d | 232,243 | 3 June 2025 8:00 AM | 13 June 2025 5:00 PM | Tue 3/06/25 | Fri 13/06/25 | Tue 3/06/25 | Fri 13/06/25 | 0d | 0d | 0ed | 0 | NA | NA | 24 April 2025 8:00 AM | 8 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
251 | 4143 | Yes | Auto Scheduled | Formwork Deck | 7 d | Fixed Duration | 4 | 7d | 244,250 | 17 June 2025 8:00 AM | 25 June 2025 5:00 PM | Tue 17/06/25 | Wed 25/06/25 | Tue 17/06/25 | Wed 25/06/25 | 0d | 0d | 0ed | 0 | NA | NA | 9 May 2025 8:00 AM | 19 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
252 | 4144 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 245,251 | 26 June 2025 8:00 AM | 30 June 2025 5:00 PM | Thu 26/06/25 | Mon 30/06/25 | Thu 26/06/25 | Mon 30/06/25 | 0d | 0d | 0ed | 0 | NA | NA | 20 May 2025 8:00 AM | 22 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
253 | 4145 | Yes | Auto Scheduled | Reinforcement Place | 5 d | Fixed Duration | 4 | 5d | 246,252 | 1 July 2025 8:00 AM | 7 July 2025 5:00 PM | Tue 1/07/25 | Mon 7/07/25 | Tue 1/07/25 | Mon 7/07/25 | 0d | 0d | 0ed | 0 | NA | NA | 23 May 2025 8:00 AM | 29 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
254 | 4146 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 247,253 | 8 July 2025 8:00 AM | 9 July 2025 5:00 PM | Tue 8/07/25 | Wed 9/07/25 | Tue 8/07/25 | Wed 9/07/25 | 0d | 0d | 0ed | 0 | NA | NA | 30 May 2025 8:00 AM | 2 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
255 | 4147 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 248,254 | 10 July 2025 8:00 AM | 10 July 2025 5:00 PM | Thu 10/07/25 | Thu 10/07/25 | Thu 10/07/25 | Thu 10/07/25 | 0d | 0d | 0ed | 0 | NA | NA | 3 June 2025 8:00 AM | 3 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.9.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
256 | 4148 | Yes | Auto Scheduled | LEVEL 3 - BUILDING C, POUR 3 | 27 d | Fixed Duration | 3 | 27d |  | 17 June 2025 8:00 AM | 23 July 2025 5:00 PM | Tue 17/06/25 | Wed 23/07/25 | Fri 11/07/25 | Mon 18/08/25 | 18d | 18d | 0ed | 0 | NA | NA | 9 May 2025 8:00 AM | 17 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
257 | 4149 | Yes | Auto Scheduled | Core-Filled Block Walls | 9 d | Fixed Duration | 4 | 9d | 241,250 | 17 June 2025 8:00 AM | 27 June 2025 5:00 PM | Tue 17/06/25 | Fri 27/06/25 | Fri 11/07/25 | Wed 23/07/25 | 0d | 18d | 0ed | 0 | NA | NA | 9 May 2025 8:00 AM | 21 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
258 | 4150 | Yes | Auto Scheduled | Formwork Deck | 7 d | Fixed Duration | 4 | 7d | 251,257 | 30 June 2025 8:00 AM | 8 July 2025 5:00 PM | Mon 30/06/25 | Tue 8/07/25 | Thu 24/07/25 | Fri 1/08/25 | 0d | 18d | 0ed | 0 | NA | NA | 22 May 2025 8:00 AM | 30 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
259 | 4151 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 252,258 | 9 July 2025 8:00 AM | 11 July 2025 5:00 PM | Wed 9/07/25 | Fri 11/07/25 | Mon 4/08/25 | Wed 6/08/25 | 0d | 18d | 0ed | 0 | NA | NA | 2 June 2025 8:00 AM | 4 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
260 | 4152 | Yes | Auto Scheduled | Reinforcement Place | 5 d | Fixed Duration | 4 | 5d | 253,259 | 14 July 2025 8:00 AM | 18 July 2025 5:00 PM | Mon 14/07/25 | Fri 18/07/25 | Thu 7/08/25 | Wed 13/08/25 | 0d | 18d | 0ed | 0 | NA | NA | 5 June 2025 8:00 AM | 11 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
261 | 4153 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 254,260 | 21 July 2025 8:00 AM | 22 July 2025 5:00 PM | Mon 21/07/25 | Tue 22/07/25 | Thu 14/08/25 | Fri 15/08/25 | 0d | 18d | 0ed | 0 | NA | NA | 12 June 2025 8:00 AM | 13 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
262 | 4154 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 255,261 | 23 July 2025 8:00 AM | 23 July 2025 5:00 PM | Wed 23/07/25 | Wed 23/07/25 | Mon 18/08/25 | Mon 18/08/25 | 0d | 18d | 0ed | 0 | NA | NA | 17 June 2025 8:00 AM | 17 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.10.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
263 | 4155 | Yes | Auto Scheduled | LEVEL 3 - COMMON AREAS, POUR 4 | 26 d | Fixed Duration | 3 | 26d |  | 30 June 2025 8:00 AM | 4 August 2025 5:00 PM | Mon 30/06/25 | Mon 4/08/25 | Thu 26/03/26 | Tue 5/05/26 | 185d | 185d | 0ed | 0 | NA | NA | 22 May 2025 8:00 AM | 27 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
264 | 4156 | Yes | Auto Scheduled | Core-Filled Block Walls, incl. Lift & Stair Core | 7 d | Fixed Duration | 4 | 7d | 241,257 | 30 June 2025 8:00 AM | 8 July 2025 5:00 PM | Mon 30/06/25 | Tue 8/07/25 | Thu 26/03/26 | Tue 7/04/26 | 0d | 185d | 0ed | 0 | NA | NA | 22 May 2025 8:00 AM | 30 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
265 | 4157 | Yes | Auto Scheduled | Formwork Deck & Stairs | 7 d | Fixed Duration | 4 | 7d | 258,264 | 9 July 2025 8:00 AM | 17 July 2025 5:00 PM | Wed 9/07/25 | Thu 17/07/25 | Wed 8/04/26 | Thu 16/04/26 | 0d | 185d | 0ed | 0 | NA | NA | 2 June 2025 8:00 AM | 10 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
266 | 4158 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 259,265 | 18 July 2025 8:00 AM | 22 July 2025 5:00 PM | Fri 18/07/25 | Tue 22/07/25 | Fri 17/04/26 | Tue 21/04/26 | 0d | 185d | 0ed | 0 | NA | NA | 11 June 2025 8:00 AM | 13 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
267 | 4159 | Yes | Auto Scheduled | Reinforcement Place | 6 d | Fixed Duration | 4 | 6d | 260,266 | 23 July 2025 8:00 AM | 30 July 2025 5:00 PM | Wed 23/07/25 | Wed 30/07/25 | Wed 22/04/26 | Wed 29/04/26 | 0d | 185d | 0ed | 0 | NA | NA | 17 June 2025 8:00 AM | 24 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
268 | 4160 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 261,267 | 31 July 2025 8:00 AM | 1 August 2025 5:00 PM | Thu 31/07/25 | Fri 1/08/25 | Thu 30/04/26 | Fri 1/05/26 | 0d | 185d | 0ed | 0 | NA | NA | 25 June 2025 8:00 AM | 26 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
269 | 4161 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 262,268 | 4 August 2025 8:00 AM | 4 August 2025 5:00 PM | Mon 4/08/25 | Mon 4/08/25 | Tue 5/05/26 | Tue 5/05/26 | 22d | 185d | 0ed | 0 | NA | NA | 27 June 2025 8:00 AM | 27 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.11.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
270 | 4183 | Yes | Auto Scheduled | LEVEL 4 - BUILDING A, POUR 1 | 20 d | Fixed Duration | 3 | 20d |  | 18 June 2025 8:00 AM | 15 July 2025 5:00 PM | Wed 18/06/25 | Tue 15/07/25 | Wed 2/07/25 | Thu 7/08/25 | 10d | 10d | 0ed | 0 | NA | NA | 12 May 2025 8:00 AM | 6 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
271 | 4184 | Yes | Auto Scheduled | Core-Filled Block Walls | 7 d | Fixed Duration | 4 | 7d | 248 | 18 June 2025 8:00 AM | 26 June 2025 5:00 PM | Wed 18/06/25 | Thu 26/06/25 | Wed 2/07/25 | Thu 10/07/25 | 0d | 10d | 0ed | 0 | NA | NA | 12 May 2025 8:00 AM | 20 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
272 | 4185 | Yes | Auto Scheduled | Formwork Deck | 5 d | Fixed Duration | 4 | 5d | 271 | 27 June 2025 8:00 AM | 3 July 2025 5:00 PM | Fri 27/06/25 | Thu 3/07/25 | Thu 17/07/25 | Wed 23/07/25 | 0d | 14d | 0ed | 0 | NA | NA | 21 May 2025 8:00 AM | 27 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
273 | 4186 | Yes | Auto Scheduled | Service Deck Work | 2 d | Fixed Duration | 4 | 2d | 272 | 4 July 2025 8:00 AM | 7 July 2025 5:00 PM | Fri 4/07/25 | Mon 7/07/25 | Tue 29/07/25 | Wed 30/07/25 | 0d | 17d | 0ed | 0 | NA | NA | 28 May 2025 8:00 AM | 29 May 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
274 | 4187 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 273 | 8 July 2025 8:00 AM | 10 July 2025 5:00 PM | Tue 8/07/25 | Thu 10/07/25 | Thu 31/07/25 | Mon 4/08/25 | 0d | 17d | 0ed | 0 | NA | NA | 30 May 2025 8:00 AM | 3 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
275 | 4188 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 274 | 11 July 2025 8:00 AM | 14 July 2025 5:00 PM | Fri 11/07/25 | Mon 14/07/25 | Tue 5/08/25 | Wed 6/08/25 | 0d | 17d | 0ed | 0 | NA | NA | 4 June 2025 8:00 AM | 5 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
276 | 4189 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 275 | 15 July 2025 8:00 AM | 15 July 2025 5:00 PM | Tue 15/07/25 | Tue 15/07/25 | Thu 7/08/25 | Thu 7/08/25 | 0d | 17d | 0ed | 0 | NA | NA | 6 June 2025 8:00 AM | 6 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.12.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
277 | 4190 | Yes | Auto Scheduled | LEVEL 4 - BUILDING B, POUR 2 | 27 d | Fixed Duration | 3 | 27d |  | 11 July 2025 8:00 AM | 18 August 2025 5:00 PM | Fri 11/07/25 | Mon 18/08/25 | Fri 11/07/25 | Mon 18/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 4 June 2025 8:00 AM | 11 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
278 | 4191 | Yes | Auto Scheduled | Core-Filled Block Walls | 9 d | Fixed Duration | 4 | 9d | 271,255 | 11 July 2025 8:00 AM | 23 July 2025 5:00 PM | Fri 11/07/25 | Wed 23/07/25 | Fri 11/07/25 | Wed 23/07/25 | 0d | 0d | 0ed | 0 | NA | NA | 4 June 2025 8:00 AM | 17 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
279 | 4192 | Yes | Auto Scheduled | Formwork Deck | 7 d | Fixed Duration | 4 | 7d | 272,278 | 24 July 2025 8:00 AM | 1 August 2025 5:00 PM | Thu 24/07/25 | Fri 1/08/25 | Thu 24/07/25 | Fri 1/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 18 June 2025 8:00 AM | 26 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
280 | 4193 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 273,279 | 4 August 2025 8:00 AM | 6 August 2025 5:00 PM | Mon 4/08/25 | Wed 6/08/25 | Mon 4/08/25 | Wed 6/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 27 June 2025 8:00 AM | 1 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
281 | 4194 | Yes | Auto Scheduled | Reinforcement Place | 5 d | Fixed Duration | 4 | 5d | 274,280 | 7 August 2025 8:00 AM | 13 August 2025 5:00 PM | Thu 7/08/25 | Wed 13/08/25 | Thu 7/08/25 | Wed 13/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 2 July 2025 8:00 AM | 8 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
282 | 4195 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 275,281 | 14 August 2025 8:00 AM | 15 August 2025 5:00 PM | Thu 14/08/25 | Fri 15/08/25 | Thu 14/08/25 | Fri 15/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 9 July 2025 8:00 AM | 10 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
283 | 4196 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 276,282 | 18 August 2025 8:00 AM | 18 August 2025 5:00 PM | Mon 18/08/25 | Mon 18/08/25 | Mon 18/08/25 | Mon 18/08/25 | 0d | 0d | 0ed | 0 | NA | NA | 11 July 2025 8:00 AM | 11 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.13.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
284 | 4197 | Yes | Auto Scheduled | LEVEL 4 - BUILDING C, POUR 3 | 30 d | Fixed Duration | 3 | 30d |  | 24 July 2025 8:00 AM | 3 September 2025 5:00 PM | Thu 24/07/25 | Wed 3/09/25 | Tue 19/08/25 | Mon 29/09/25 | 18d | 18d | 0ed | 0 | NA | NA | 18 June 2025 8:00 AM | 29 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
285 | 4198 | Yes | Auto Scheduled | Core-Filled Block Walls | 10 d | Fixed Duration | 4 | 10d | 278,262 | 24 July 2025 8:00 AM | 6 August 2025 5:00 PM | Thu 24/07/25 | Wed 6/08/25 | Tue 19/08/25 | Mon 1/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 18 June 2025 8:00 AM | 1 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
286 | 4199 | Yes | Auto Scheduled | Formwork Deck | 8 d | Fixed Duration | 4 | 8d | 279,285 | 7 August 2025 8:00 AM | 18 August 2025 5:00 PM | Thu 7/08/25 | Mon 18/08/25 | Tue 2/09/25 | Thu 11/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 2 July 2025 8:00 AM | 11 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
287 | 4200 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 280,286 | 19 August 2025 8:00 AM | 21 August 2025 5:00 PM | Tue 19/08/25 | Thu 21/08/25 | Fri 12/09/25 | Tue 16/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 14 July 2025 8:00 AM | 16 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
288 | 4201 | Yes | Auto Scheduled | Reinforcement Place | 6 d | Fixed Duration | 4 | 6d | 281,287 | 22 August 2025 8:00 AM | 29 August 2025 5:00 PM | Fri 22/08/25 | Fri 29/08/25 | Wed 17/09/25 | Wed 24/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 17 July 2025 8:00 AM | 24 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
289 | 4202 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 282,288 | 1 September 2025 8:00 AM | 2 September 2025 5:00 PM | Mon 1/09/25 | Tue 2/09/25 | Thu 25/09/25 | Fri 26/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 25 July 2025 8:00 AM | 28 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
290 | 4203 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 283,289 | 3 September 2025 8:00 AM | 3 September 2025 5:00 PM | Wed 3/09/25 | Wed 3/09/25 | Mon 29/09/25 | Mon 29/09/25 | 0d | 18d | 0ed | 0 | NA | NA | 29 July 2025 8:00 AM | 29 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.14.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
291 | 4204 | Yes | Auto Scheduled | LEVEL 4 - COMMON AREA, POUR 4 | 26 d | Fixed Duration | 3 | 26d |  | 4 September 2025 8:00 AM | 10 October 2025 5:00 PM | Thu 4/09/25 | Fri 10/10/25 | Wed 6/05/26 | Wed 10/06/26 | 163d | 163d | 0ed | 0 | NA | NA | 30 July 2025 8:00 AM | 3 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
292 | 4205 | Yes | Auto Scheduled | Core-Filled Block Walls, incl. Lift & Stair Core | 7 d | Fixed Duration | 4 | 7d | 269,290 | 4 September 2025 8:00 AM | 12 September 2025 5:00 PM | Thu 4/09/25 | Fri 12/09/25 | Wed 6/05/26 | Thu 14/05/26 | 0d | 163d | 0ed | 0 | NA | NA | 30 July 2025 8:00 AM | 7 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
293 | 4206 | Yes | Auto Scheduled | Formwork Deck & Stairs | 7 d | Fixed Duration | 4 | 7d | 292,286 | 15 September 2025 8:00 AM | 23 September 2025 5:00 PM | Mon 15/09/25 | Tue 23/09/25 | Fri 15/05/26 | Mon 25/05/26 | 0d | 163d | 0ed | 0 | NA | NA | 8 August 2025 8:00 AM | 18 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
294 | 4207 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 293,287 | 24 September 2025 8:00 AM | 26 September 2025 5:00 PM | Wed 24/09/25 | Fri 26/09/25 | Tue 26/05/26 | Thu 28/05/26 | 0d | 163d | 0ed | 0 | NA | NA | 19 August 2025 8:00 AM | 21 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
295 | 4208 | Yes | Auto Scheduled | Reinforcement Place | 6 d | Fixed Duration | 4 | 6d | 294,288 | 29 September 2025 8:00 AM | 7 October 2025 5:00 PM | Mon 29/09/25 | Tue 7/10/25 | Fri 29/05/26 | Fri 5/06/26 | 0d | 163d | 0ed | 0 | NA | NA | 22 August 2025 8:00 AM | 29 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
296 | 4209 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 295,289 | 8 October 2025 8:00 AM | 9 October 2025 5:00 PM | Wed 8/10/25 | Thu 9/10/25 | Mon 8/06/26 | Tue 9/06/26 | 0d | 163d | 0ed | 0 | NA | NA | 1 September 2025 8:00 AM | 2 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
297 | 4210 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 296,290 | 10 October 2025 8:00 AM | 10 October 2025 5:00 PM | Fri 10/10/25 | Fri 10/10/25 | Wed 10/06/26 | Wed 10/06/26 | 19d | 163d | 0ed | 0 | NA | NA | 3 September 2025 8:00 AM | 3 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.15.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
298 | 4211 | Yes | Auto Scheduled | LEVEL 5 - BUILDING A, POUR 1 | 20 d | Fixed Duration | 3 | 20d |  | 16 July 2025 8:00 AM | 12 August 2025 5:00 PM | Wed 16/07/25 | Tue 12/08/25 | Fri 8/08/25 | Fri 26/09/25 | 17d | 17d | 0ed | 0 | NA | NA | 9 June 2025 8:00 AM | 7 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
299 | 4212 | Yes | Auto Scheduled | Core-Filled Block Walls | 7 d | Fixed Duration | 4 | 7d | 276 | 16 July 2025 8:00 AM | 24 July 2025 5:00 PM | Wed 16/07/25 | Thu 24/07/25 | Fri 8/08/25 | Mon 18/08/25 | 0d | 17d | 0ed | 0 | NA | NA | 9 June 2025 8:00 AM | 18 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
300 | 4213 | Yes | Auto Scheduled | Formwork Deck | 5 d | Fixed Duration | 4 | 5d | 299 | 25 July 2025 8:00 AM | 31 July 2025 5:00 PM | Fri 25/07/25 | Thu 31/07/25 | Tue 26/08/25 | Mon 1/09/25 | 0d | 22d | 0ed | 0 | NA | NA | 19 June 2025 8:00 AM | 25 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
301 | 4214 | Yes | Auto Scheduled | Service Deck Work | 2 d | Fixed Duration | 4 | 2d | 300 | 1 August 2025 8:00 AM | 4 August 2025 5:00 PM | Fri 1/08/25 | Mon 4/08/25 | Wed 10/09/25 | Thu 11/09/25 | 0d | 28d | 0ed | 0 | NA | NA | 26 June 2025 8:00 AM | 27 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
302 | 4215 | Yes | Auto Scheduled | Reinforcement Place | 3 d | Fixed Duration | 4 | 3d | 301 | 5 August 2025 8:00 AM | 7 August 2025 5:00 PM | Tue 5/08/25 | Thu 7/08/25 | Fri 12/09/25 | Tue 16/09/25 | 0d | 28d | 0ed | 0 | NA | NA | 30 June 2025 8:00 AM | 2 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
303 | 4216 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 302 | 8 August 2025 8:00 AM | 11 August 2025 5:00 PM | Fri 8/08/25 | Mon 11/08/25 | Tue 23/09/25 | Wed 24/09/25 | 0d | 32d | 0ed | 0 | NA | NA | 3 July 2025 8:00 AM | 4 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
304 | 4217 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 303 | 12 August 2025 8:00 AM | 12 August 2025 5:00 PM | Tue 12/08/25 | Tue 12/08/25 | Fri 26/09/25 | Fri 26/09/25 | 0d | 33d | 0ed | 0 | NA | NA | 7 July 2025 8:00 AM | 7 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.16.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
305 | 4218 | Yes | Auto Scheduled | LEVEL 5 - BUILDING B, POUR 2 | 30 d | Fixed Duration | 3 | 30d |  | 19 August 2025 8:00 AM | 29 September 2025 5:00 PM | Tue 19/08/25 | Mon 29/09/25 | Tue 19/08/25 | Mon 29/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 14 July 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
306 | 4219 | Yes | Auto Scheduled | Core-Filled Block Walls | 10 d | Fixed Duration | 4 | 10d | 283,299 | 19 August 2025 8:00 AM | 1 September 2025 5:00 PM | Tue 19/08/25 | Mon 1/09/25 | Tue 19/08/25 | Mon 1/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 14 July 2025 8:00 AM | 25 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
307 | 4220 | Yes | Auto Scheduled | Formwork Deck | 8 d | Fixed Duration | 4 | 8d | 300,306 | 2 September 2025 8:00 AM | 11 September 2025 5:00 PM | Tue 2/09/25 | Thu 11/09/25 | Tue 2/09/25 | Thu 11/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 28 July 2025 8:00 AM | 6 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
308 | 4221 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 301,307 | 12 September 2025 8:00 AM | 16 September 2025 5:00 PM | Fri 12/09/25 | Tue 16/09/25 | Fri 12/09/25 | Tue 16/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 7 August 2025 8:00 AM | 11 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
309 | 4222 | Yes | Auto Scheduled | Reinforcement Place | 6 d | Fixed Duration | 4 | 6d | 302,308 | 17 September 2025 8:00 AM | 24 September 2025 5:00 PM | Wed 17/09/25 | Wed 24/09/25 | Wed 17/09/25 | Wed 24/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 12 August 2025 8:00 AM | 19 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
310 | 4223 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 303,309 | 25 September 2025 8:00 AM | 26 September 2025 5:00 PM | Thu 25/09/25 | Fri 26/09/25 | Thu 25/09/25 | Fri 26/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 20 August 2025 8:00 AM | 21 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
311 | 4224 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 304,310 | 29 September 2025 8:00 AM | 29 September 2025 5:00 PM | Mon 29/09/25 | Mon 29/09/25 | Mon 29/09/25 | Mon 29/09/25 | 0d | 0d | 0ed | 0 | NA | NA | 22 August 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.17.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
312 | 4225 | Yes | Auto Scheduled | LEVEL 5 - BUILDING C, POUR 3 | 27 d | Fixed Duration | 3 | 27d |  | 30 September 2025 8:00 AM | 6 November 2025 5:00 PM | Tue 30/09/25 | Thu 6/11/25 | Tue 30/09/25 | Thu 6/11/25 | 0d | 0d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
313 | 4226 | Yes | Auto Scheduled | Core-Filled Block Walls | 9 d | Fixed Duration | 4 | 9d | 290,311 | 30 September 2025 8:00 AM | 13 October 2025 5:00 PM | Tue 30/09/25 | Mon 13/10/25 | Tue 30/09/25 | Mon 13/10/25 | 0d | 0d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 4 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
314 | 4227 | Yes | Auto Scheduled | Formwork Deck | 7 d | Fixed Duration | 4 | 7d | 307,313 | 14 October 2025 8:00 AM | 22 October 2025 5:00 PM | Tue 14/10/25 | Wed 22/10/25 | Tue 14/10/25 | Wed 22/10/25 | 0d | 0d | 0ed | 0 | NA | NA | 5 September 2025 8:00 AM | 15 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
315 | 4228 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 308,314 | 23 October 2025 8:00 AM | 27 October 2025 5:00 PM | Thu 23/10/25 | Mon 27/10/25 | Thu 23/10/25 | Mon 27/10/25 | 0d | 0d | 0ed | 0 | NA | NA | 16 September 2025 8:00 AM | 18 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
316 | 4229 | Yes | Auto Scheduled | Reinforcement Place | 5 d | Fixed Duration | 4 | 5d | 309,315 | 28 October 2025 8:00 AM | 3 November 2025 5:00 PM | Tue 28/10/25 | Mon 3/11/25 | Tue 28/10/25 | Mon 3/11/25 | 0d | 0d | 0ed | 0 | NA | NA | 19 September 2025 8:00 AM | 25 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
317 | 4230 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 310,316 | 4 November 2025 8:00 AM | 5 November 2025 5:00 PM | Tue 4/11/25 | Wed 5/11/25 | Tue 4/11/25 | Wed 5/11/25 | 0d | 0d | 0ed | 0 | NA | NA | 26 September 2025 8:00 AM | 29 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
318 | 4231 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 311,317 | 6 November 2025 8:00 AM | 6 November 2025 5:00 PM | Thu 6/11/25 | Thu 6/11/25 | Thu 6/11/25 | Thu 6/11/25 | 0d | 0d | 0ed | 0 | NA | NA | 30 September 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.18.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
319 | 4232 | Yes | Auto Scheduled | LEVEL 5 - COMMON AREA, POUR 4 | 26 d | Fixed Duration | 3 | 26d |  | 7 November 2025 8:00 AM | 12 December 2025 5:00 PM | Fri 7/11/25 | Fri 12/12/25 | Thu 11/06/26 | Fri 17/07/26 | 144d | 144d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 6 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
320 | 4233 | Yes | Auto Scheduled | Core-Filled Block Walls, incl. Lift & Stair Core | 7 d | Fixed Duration | 4 | 7d | 297,318 | 7 November 2025 8:00 AM | 17 November 2025 5:00 PM | Fri 7/11/25 | Mon 17/11/25 | Thu 11/06/26 | Mon 22/06/26 | 0d | 144d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 10 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
321 | 4234 | Yes | Auto Scheduled | Formwork Deck & Stairs | 7 d | Fixed Duration | 4 | 7d | 314,320 | 18 November 2025 8:00 AM | 26 November 2025 5:00 PM | Tue 18/11/25 | Wed 26/11/25 | Tue 23/06/26 | Wed 1/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 13 October 2025 8:00 AM | 21 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
322 | 4235 | Yes | Auto Scheduled | Service Deck Work | 3 d | Fixed Duration | 4 | 3d | 315,321 | 27 November 2025 8:00 AM | 1 December 2025 5:00 PM | Thu 27/11/25 | Mon 1/12/25 | Thu 2/07/26 | Mon 6/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 22 October 2025 8:00 AM | 24 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
323 | 4236 | Yes | Auto Scheduled | Reinforcement Place | 6 d | Fixed Duration | 4 | 6d | 316,322 | 2 December 2025 8:00 AM | 9 December 2025 5:00 PM | Tue 2/12/25 | Tue 9/12/25 | Tue 7/07/26 | Tue 14/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 27 October 2025 8:00 AM | 3 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
324 | 4237 | Yes | Auto Scheduled | Formwork Set Downs & Hobs | 2 d | Fixed Duration | 4 | 2d | 317,323 | 10 December 2025 8:00 AM | 11 December 2025 5:00 PM | Wed 10/12/25 | Thu 11/12/25 | Wed 15/07/26 | Thu 16/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 4 November 2025 8:00 AM | 5 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
325 | 4238 | Yes | Auto Scheduled | Concrete Place | 1 d | Fixed Duration | 4 | 1d | 318,324 | 12 December 2025 8:00 AM | 12 December 2025 5:00 PM | Fri 12/12/25 | Fri 12/12/25 | Fri 17/07/26 | Fri 17/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 6 November 2025 8:00 AM | 6 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.19.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
326 | 4239 | Yes | Auto Scheduled | ROOF STRUCTURE | 104 d | Fixed Duration | 3 | 104d |  | 13 August 2025 8:00 AM | 14 January 2026 5:00 PM | Wed 13/08/25 | Wed 14/01/26 | Tue 30/06/26 | Wed 12/08/26 | 144d | 144d | 0ed | 0 | NA | NA | 8 July 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
327 | 4248 | Yes | Auto Scheduled | Building A, Pour 1 - Core-Filled Block Work | 5 d | Fixed Duration | 4 | 5d | 304 | 13 August 2025 8:00 AM | 19 August 2025 5:00 PM | Wed 13/08/25 | Tue 19/08/25 | Tue 30/06/26 | Mon 6/07/26 | 0d | 217d | 0ed | 0 | NA | NA | 8 July 2025 8:00 AM | 14 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
328 | 4240 | Yes | Auto Scheduled | Building A, Pour 1 - Frame & Truss Installation | 5 d | Fixed Duration | 4 | 5d | 327 | 20 August 2025 8:00 AM | 26 August 2025 5:00 PM | Wed 20/08/25 | Tue 26/08/25 | Thu 9/07/26 | Wed 15/07/26 | 0d | 219d | 0ed | 0 | NA | NA | 15 July 2025 8:00 AM | 21 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
329 | 4249 | Yes | Auto Scheduled | Building B, Pour 2 - Core-Filled Block Work | 7 d | Fixed Duration | 4 | 7d | 311,327 | 30 September 2025 8:00 AM | 9 October 2025 5:00 PM | Tue 30/09/25 | Thu 9/10/25 | Tue 7/07/26 | Wed 15/07/26 | 0d | 188d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 2 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
330 | 4241 | Yes | Auto Scheduled | Building B, Pour 2 - Frame & Truss Installation | 7 d | Fixed Duration | 4 | 7d | 328,329 | 10 October 2025 8:00 AM | 20 October 2025 5:00 PM | Fri 10/10/25 | Mon 20/10/25 | Thu 16/07/26 | Fri 24/07/26 | 0d | 188d | 0ed | 0 | NA | NA | 3 September 2025 8:00 AM | 11 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
331 | 4250 | Yes | Auto Scheduled | Building C, Pour 3 - Core-Filled Block Work | 7 d | Fixed Duration | 4 | 7d | 318,329 | 7 November 2025 8:00 AM | 17 November 2025 5:00 PM | Fri 7/11/25 | Mon 17/11/25 | Thu 16/07/26 | Fri 24/07/26 | 0d | 168d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 10 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
332 | 4242 | Yes | Auto Scheduled | Building C, Pour 3 - Frame & Truss Installation | 7 d | Fixed Duration | 4 | 7d | 330,331 | 18 November 2025 8:00 AM | 26 November 2025 5:00 PM | Tue 18/11/25 | Wed 26/11/25 | Mon 27/07/26 | Tue 4/08/26 | 0d | 168d | 0ed | 0 | NA | NA | 13 October 2025 8:00 AM | 21 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
333 | 4243 | Yes | Auto Scheduled | Building D, Pour 4 - Core-Filled Block Work - Lift & Stair Core | 5 d | Fixed Duration | 4 | 5d | 325 | 15 December 2025 8:00 AM | 19 December 2025 5:00 PM | Mon 15/12/25 | Fri 19/12/25 | Mon 20/07/26 | Fri 24/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 7 November 2025 8:00 AM | 13 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
334 | 4244 | Yes | Auto Scheduled | Building D, Pour 4 - Formwork - Lift & Stair Overrun | 3 d | Fixed Duration | 4 | 3d | 333 | 22 December 2025 8:00 AM | 24 December 2025 5:00 PM | Mon 22/12/25 | Wed 24/12/25 | Mon 27/07/26 | Wed 29/07/26 | 0d | 144d | 0ed | 0 | NA | NA | 14 November 2025 8:00 AM | 18 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
335 | 4245 | Yes | Auto Scheduled | Building D, Pour 4 - Reinforcement Place - Lift & Stair Overrun | 3 d | Fixed Duration | 4 | 3d | 334 | 2 January 2026 8:00 AM | 6 January 2026 5:00 PM | Fri 2/01/26 | Tue 6/01/26 | Thu 30/07/26 | Mon 3/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 21 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
336 | 4246 | Yes | Auto Scheduled | Building D, Pour 4 - Concrete Place - Lift Overrun | 1 d | Fixed Duration | 4 | 1d | 335 | 7 January 2026 8:00 AM | 7 January 2026 5:00 PM | Wed 7/01/26 | Wed 7/01/26 | Tue 4/08/26 | Tue 4/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 24 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
337 | 4247 | Yes | Auto Scheduled | Building D, Pour 4 - Frame & Truss Installation - Pour 4 | 5 d | Fixed Duration | 4 | 5d | 332,336 | 8 January 2026 8:00 AM | 14 January 2026 5:00 PM | Thu 8/01/26 | Wed 14/01/26 | Wed 5/08/26 | Tue 11/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 25 November 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
338 | 4275 | Yes | Auto Scheduled | Structure Complete | 0 d | Fixed Duration | 4 | 0d | 337 | 14 January 2026 5:00 PM | 14 January 2026 5:00 PM | Wed 14/01/26 | Wed 14/01/26 | Wed 12/08/26 | Wed 12/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 1 December 2025 5:00 PM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.20.12 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
339 | 4251 | Yes | Auto Scheduled | FORMWORK STRIPPING | 216 d | Fixed Duration | 3 | 216d |  | 18 July 2025 8:00 AM | 18 February 2026 5:00 PM | Fri 18/07/25 | Wed 18/02/26 | Mon 15/12/25 | Mon 9/11/26 | 150d | 150d | 0ed | 0 | NA | NA | 11 June 2025 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
340 | 4313 | Yes | Auto Scheduled | LEVEL 2 | 37 d | Fixed Duration | 4 | 37d |  | 18 July 2025 8:00 AM | 8 September 2025 5:00 PM | Fri 18/07/25 | Mon 8/09/25 | Mon 17/08/26 | Tue 18/08/26 | 234d | 234d | 0ed | 0 | NA | NA | 11 June 2025 8:00 AM | 1 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
341 | 4310 | Yes | Auto Scheduled | Level 2 - Building A (Pour 1) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 276SF+4d | 18 July 2025 8:00 AM | 18 July 2025 5:00 PM | Fri 18/07/25 | Fri 18/07/25 | Tue 18/08/26 | Tue 18/08/26 | 31d | 270d | 0ed | 0 | NA | NA | 11 June 2025 8:00 AM | 11 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
342 | 4311 | Yes | Auto Scheduled | Level 2 - Building B (Pour 2) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 283SF+4d | 21 August 2025 8:00 AM | 21 August 2025 5:00 PM | Thu 21/08/25 | Thu 21/08/25 | Tue 18/08/26 | Tue 18/08/26 | 12d | 246d | 0ed | 0 | NA | NA | 16 July 2025 8:00 AM | 16 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
343 | 4312 | Yes | Auto Scheduled | Level 2 - Building C (Pour 3) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 290SF+4d | 8 September 2025 8:00 AM | 8 September 2025 5:00 PM | Mon 8/09/25 | Mon 8/09/25 | Mon 17/08/26 | Mon 17/08/26 | 0d | 233d | 0ed | 0 | NA | NA | 1 August 2025 8:00 AM | 1 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
344 | 4314 | Yes | Auto Scheduled | LEVEL 3 | 100 d | Fixed Duration | 4 | 100d |  | 15 August 2025 8:00 AM | 12 January 2026 5:00 PM | Fri 15/08/25 | Mon 12/01/26 | Mon 17/08/26 | Mon 9/11/26 | 209d | 209d | 0ed | 0 | NA | NA | 10 July 2025 8:00 AM | 27 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
345 | 4317 | Yes | Auto Scheduled | Level 3 - Building A (Pour 1) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 304SF+4d | 15 August 2025 8:00 AM | 15 August 2025 5:00 PM | Fri 15/08/25 | Fri 15/08/25 | Tue 18/08/26 | Tue 18/08/26 | 56d | 250d | 0ed | 0 | NA | NA | 10 July 2025 8:00 AM | 10 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
346 | 4318 | Yes | Auto Scheduled | Level 3 - Building B (Pour 2) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 311SF+4d | 2 October 2025 8:00 AM | 2 October 2025 5:00 PM | Thu 2/10/25 | Thu 2/10/25 | Tue 18/08/26 | Tue 18/08/26 | 27d | 216d | 0ed | 0 | NA | NA | 27 August 2025 8:00 AM | 27 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
347 | 4319 | Yes | Auto Scheduled | Level 3 - Building C (Pour 3) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 318SF+4d | 11 November 2025 8:00 AM | 11 November 2025 5:00 PM | Tue 11/11/25 | Tue 11/11/25 | Mon 17/08/26 | Mon 17/08/26 | 0d | 188d | 0ed | 0 | NA | NA | 3 October 2025 8:00 AM | 3 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
348 | 4323 | Yes | Auto Scheduled | Level 3 - Common Area (Pour 4) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 336SF+4d | 12 January 2026 8:00 AM | 12 January 2026 5:00 PM | Mon 12/01/26 | Mon 12/01/26 | Mon 9/11/26 | Mon 9/11/26 | 209d | 209d | 0ed | 0 | NA | NA | 27 November 2025 8:00 AM | 27 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
349 | 4315 | Yes | Auto Scheduled | LEVEL 4 | 88 d | Fixed Duration | 4 | 88d |  | 18 September 2025 8:00 AM | 29 January 2026 5:00 PM | Thu 18/09/25 | Thu 29/01/26 | Mon 15/12/25 | Mon 9/11/26 | 61d | 61d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
350 | 4320 | Yes | Auto Scheduled | Level 4 - Building A (Pour 1) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 304SF+28d | 18 September 2025 8:00 AM | 18 September 2025 5:00 PM | Thu 18/09/25 | Thu 18/09/25 | Tue 11/08/26 | Tue 11/08/26 | 56d | 221d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 13 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
351 | 4321 | Yes | Auto Scheduled | Level 4 - Building B (Pour 2) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 311SF+28d | 6 November 2025 8:00 AM | 6 November 2025 5:00 PM | Thu 6/11/25 | Thu 6/11/25 | Tue 11/08/26 | Tue 11/08/26 | 27d | 187d | 0ed | 0 | NA | NA | 30 September 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
352 | 4322 | Yes | Auto Scheduled | Level 4 - Building C (Pour 3) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 318SF+28d | 15 December 2025 8:00 AM | 15 December 2025 5:00 PM | Mon 15/12/25 | Mon 15/12/25 | Mon 15/12/25 | Mon 15/12/25 | 0d | 0d | 0ed | 0 | NA | NA | 7 November 2025 8:00 AM | 7 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
353 | 4324 | Yes | Auto Scheduled | Level 4 - Common Areas (Pour 4) Formwork Propping for Slab Over | 1 d | Fixed Duration | 5 | 1d | 325SF+28d | 29 January 2026 8:00 AM | 29 January 2026 5:00 PM | Thu 29/01/26 | Thu 29/01/26 | Mon 9/11/26 | Mon 9/11/26 | 197d | 197d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
354 | 4316 | Yes | Auto Scheduled | LEVEL 5 | 102 d | Fixed Duration | 4 | 102d |  | 18 September 2025 8:00 AM | 18 February 2026 5:00 PM | Thu 18/09/25 | Wed 18/02/26 | Tue 13/01/26 | Mon 9/11/26 | 76d | 76d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
355 | 4325 | Yes | Auto Scheduled | Level 5 - Building A (Pour 1) Formwork Propping | 1 d | Fixed Duration | 5 | 1d | 304SF+28d | 18 September 2025 8:00 AM | 18 September 2025 5:00 PM | Thu 18/09/25 | Thu 18/09/25 | Tue 18/08/26 | Tue 18/08/26 | 71d | 226d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 13 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
356 | 4326 | Yes | Auto Scheduled | Level 5 - Building B (Pour 2) Formwork Propping | 1 d | Fixed Duration | 5 | 1d | 311SF+28d | 6 November 2025 8:00 AM | 6 November 2025 5:00 PM | Thu 6/11/25 | Thu 6/11/25 | Tue 18/08/26 | Tue 18/08/26 | 42d | 192d | 0ed | 0 | NA | NA | 30 September 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
357 | 4327 | Yes | Auto Scheduled | Level 5 - Building C (Pour 3) Formwork Propping | 1 d | Fixed Duration | 5 | 1d | 318SF+28d | 15 December 2025 8:00 AM | 15 December 2025 5:00 PM | Mon 15/12/25 | Mon 15/12/25 | Tue 13/01/26 | Tue 13/01/26 | 15d | 15d | 0ed | 0 | NA | NA | 7 November 2025 8:00 AM | 7 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
358 | 4328 | Yes | Auto Scheduled | Level 5 - Common Areas (Pour 4) Formwork Propping | 1 d | Fixed Duration | 5 | 1d | 325SF+28d | 29 January 2026 8:00 AM | 29 January 2026 5:00 PM | Thu 29/01/26 | Thu 29/01/26 | Mon 9/11/26 | Mon 9/11/26 | 197d | 197d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
359 | 4329 | Yes | Auto Scheduled | Roof - Lift & Stair Overrun Formwork Propping | 1 d | Fixed Duration | 5 | 1d | 336FS+28d | 18 February 2026 8:00 AM | 18 February 2026 5:00 PM | Wed 18/02/26 | Wed 18/02/26 | Mon 9/11/26 | Mon 9/11/26 | 183d | 183d | 0ed | 0 | NA | NA | 12 January 2026 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.2.21.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
360 | 4268 | Yes | Auto Scheduled | BUILDING ENVELOPE | 205 d | Fixed Duration | 2 | 205d |  | 25 June 2025 8:00 AM | 21 April 2026 5:00 PM | Wed 25/06/25 | Tue 21/04/26 | Tue 16/12/25 | Mon 9/11/26 | 123d | 123d | 0ed | 0 | NA | NA | 19 May 2025 8:00 AM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
361 | 4276 | Yes | Auto Scheduled | ROOFING | 104 d | Fixed Duration | 3 | 104d |  | 27 August 2025 8:00 AM | 29 January 2026 5:00 PM | Wed 27/08/25 | Thu 29/01/26 | Tue 27/10/26 | Mon 9/11/26 | 197d | 197d | 0ed | 0 | NA | NA | 22 July 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
362 | 4269 | Yes | Auto Scheduled | Building A (Pour 1) - Roof Installation | 5 d | Fixed Duration | 4 | 5d | 328 | 27 August 2025 8:00 AM | 2 September 2025 5:00 PM | Wed 27/08/25 | Tue 2/09/25 | Tue 3/11/26 | Mon 9/11/26 | 296d | 296d | 0ed | 0 | NA | NA | 22 July 2025 8:00 AM | 28 July 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
363 | 4270 | Yes | Auto Scheduled | Building B (Pour 2) - Roof Installation | 7 d | Fixed Duration | 4 | 7d | 330 | 21 October 2025 8:00 AM | 29 October 2025 5:00 PM | Tue 21/10/25 | Wed 29/10/25 | Fri 30/10/26 | Mon 9/11/26 | 256d | 256d | 0ed | 0 | NA | NA | 12 September 2025 8:00 AM | 22 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
364 | 4271 | Yes | Auto Scheduled | Building C (Pour 3) - Roof Installation | 7 d | Fixed Duration | 4 | 7d | 332 | 27 November 2025 8:00 AM | 5 December 2025 5:00 PM | Thu 27/11/25 | Fri 5/12/25 | Fri 30/10/26 | Mon 9/11/26 | 229d | 229d | 0ed | 0 | NA | NA | 22 October 2025 8:00 AM | 30 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
365 | 4272 | Yes | Auto Scheduled | Common Area (Pour 4) - Roof Installation | 7 d | Fixed Duration | 4 | 7d | 337 | 15 January 2026 8:00 AM | 23 January 2026 5:00 PM | Thu 15/01/26 | Fri 23/01/26 | Tue 27/10/26 | Wed 4/11/26 | 0d | 197d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 10 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
366 | 4273 | Yes | Auto Scheduled | Lift Overrun - Waterproof Membrane | 3 d | Fixed Duration | 4 | 3d | 365 | 27 January 2026 8:00 AM | 29 January 2026 5:00 PM | Tue 27/01/26 | Thu 29/01/26 | Thu 5/11/26 | Mon 9/11/26 | 197d | 197d | 0ed | 0 | NA | NA | 11 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
367 | 4274 | Yes | Auto Scheduled | WINDOWS | 153 d | Fixed Duration | 3 | 153d |  | 25 June 2025 8:00 AM | 4 February 2026 5:00 PM | Wed 25/06/25 | Wed 4/02/26 | Tue 16/12/25 | Mon 9/11/26 | 123d | 123d | 0ed | 0 | NA | NA | 19 May 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
368 | 4534 | Yes | Auto Scheduled | SITE MEASURE & FABRICATION | 136 d | Fixed Duration | 4 | 136d |  | 25 June 2025 8:00 AM | 9 January 2026 5:00 PM | Wed 25/06/25 | Fri 9/01/26 | Mon 28/09/26 | Mon 9/11/26 | 210d | 210d | 0ed | 0 | NA | NA | 19 May 2025 8:00 AM | 26 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
369 | 4306 | Yes | Auto Scheduled | Level 2 - Site Measure & Fabrication Lead Time | 30 d | Fixed Duration | 5 | 30d | 241FS+10d | 25 June 2025 8:00 AM | 5 August 2025 5:00 PM | Wed 25/06/25 | Tue 5/08/25 | Mon 28/09/26 | Mon 9/11/26 | 316d | 316d | 0ed | 0 | NA | NA | 19 May 2025 8:00 AM | 30 June 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
370 | 4307 | Yes | Auto Scheduled | Level 3 - Site Measure & Fabrication Lead Time | 30 d | Fixed Duration | 5 | 30d | 262FS+10d | 7 August 2025 8:00 AM | 17 September 2025 5:00 PM | Thu 7/08/25 | Wed 17/09/25 | Mon 28/09/26 | Mon 9/11/26 | 285d | 285d | 0ed | 0 | NA | NA | 2 July 2025 8:00 AM | 12 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
371 | 4308 | Yes | Auto Scheduled | Level 4 - Site Measure & Fabrication Lead Time | 30 d | Fixed Duration | 5 | 30d | 290FS+10d | 18 September 2025 8:00 AM | 30 October 2025 5:00 PM | Thu 18/09/25 | Thu 30/10/25 | Mon 28/09/26 | Mon 9/11/26 | 255d | 255d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 23 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
372 | 4309 | Yes | Auto Scheduled | Level 5 - Site Measure & Fabrication Lead Time | 30 d | Fixed Duration | 5 | 30d | 318FS+10d | 21 November 2025 8:00 AM | 9 January 2026 5:00 PM | Fri 21/11/25 | Fri 9/01/26 | Mon 28/09/26 | Mon 9/11/26 | 210d | 210d | 0ed | 0 | NA | NA | 16 October 2025 8:00 AM | 26 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
373 | 4277 | Yes | Auto Scheduled | LEVEL 2 | 18 d | Fixed Duration | 4 | 18d |  | 4 September 2025 8:00 AM | 29 September 2025 5:00 PM | Thu 4/09/25 | Mon 29/09/25 | Tue 18/08/26 | Mon 9/11/26 | 236d | 236d | 0ed | 0 | NA | NA | 30 July 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
374 | 4278 | Yes | Auto Scheduled | Building A, Level 2 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 375SF | 4 September 2025 8:00 AM | 9 September 2025 8:00 AM | Thu 4/09/25 | Tue 9/09/25 | Thu 5/11/26 | Mon 9/11/26 | 292d | 292d | 0ed | 0 | NA | NA | 30 July 2025 8:00 AM | 4 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
375 | 4292 | Yes | Auto Scheduled | Building A, Level 2 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 343 | 9 September 2025 8:00 AM | 15 September 2025 5:00 PM | Tue 9/09/25 | Mon 15/09/25 | Tue 18/08/26 | Mon 24/08/26 | 0d | 233d | 0ed | 0 | NA | NA | 4 August 2025 8:00 AM | 8 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
376 | 4283 | Yes | Auto Scheduled | Building B, Level 2 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 377SF | 11 September 2025 8:00 AM | 16 September 2025 8:00 AM | Thu 11/09/25 | Tue 16/09/25 | Thu 5/11/26 | Mon 9/11/26 | 287d | 287d | 0ed | 0 | NA | NA | 6 August 2025 8:00 AM | 11 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
377 | 4284 | Yes | Auto Scheduled | Building B, Level 2 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 375 | 16 September 2025 8:00 AM | 22 September 2025 5:00 PM | Tue 16/09/25 | Mon 22/09/25 | Tue 25/08/26 | Mon 31/08/26 | 0d | 233d | 0ed | 0 | NA | NA | 11 August 2025 8:00 AM | 15 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
378 | 4297 | Yes | Auto Scheduled | Building C, Level 2 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 379SF | 18 September 2025 8:00 AM | 23 September 2025 8:00 AM | Thu 18/09/25 | Tue 23/09/25 | Thu 5/11/26 | Mon 9/11/26 | 282d | 282d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 18 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
379 | 4298 | Yes | Auto Scheduled | Building C, Level 2 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 377 | 23 September 2025 8:00 AM | 29 September 2025 5:00 PM | Tue 23/09/25 | Mon 29/09/25 | Tue 1/09/26 | Mon 7/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 18 August 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
380 | 4330 | Yes | Auto Scheduled | LEVEL 3 | 18 d | Fixed Duration | 4 | 18d |  | 7 November 2025 8:00 AM | 2 December 2025 5:00 PM | Fri 7/11/25 | Tue 2/12/25 | Tue 18/08/26 | Mon 9/11/26 | 191d | 191d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 27 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
381 | 4333 | Yes | Auto Scheduled | Building A, Level 3 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 382SF | 7 November 2025 8:00 AM | 12 November 2025 8:00 AM | Fri 7/11/25 | Wed 12/11/25 | Thu 5/11/26 | Mon 9/11/26 | 247d | 247d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 7 October 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
382 | 4334 | Yes | Auto Scheduled | Building A, Level 3 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 347 | 12 November 2025 8:00 AM | 18 November 2025 5:00 PM | Wed 12/11/25 | Tue 18/11/25 | Tue 18/08/26 | Mon 24/08/26 | 0d | 188d | 0ed | 0 | NA | NA | 7 October 2025 8:00 AM | 13 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
383 | 4342 | Yes | Auto Scheduled | Building B, Level 3 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 384SF | 14 November 2025 8:00 AM | 19 November 2025 8:00 AM | Fri 14/11/25 | Wed 19/11/25 | Thu 5/11/26 | Mon 9/11/26 | 242d | 242d | 0ed | 0 | NA | NA | 9 October 2025 8:00 AM | 14 October 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
384 | 4343 | Yes | Auto Scheduled | Building B, Level 3 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 382 | 19 November 2025 8:00 AM | 25 November 2025 5:00 PM | Wed 19/11/25 | Tue 25/11/25 | Tue 25/08/26 | Mon 31/08/26 | 0d | 188d | 0ed | 0 | NA | NA | 14 October 2025 8:00 AM | 20 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
385 | 4351 | Yes | Auto Scheduled | Building C, Level 3 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 386SF | 21 November 2025 8:00 AM | 26 November 2025 8:00 AM | Fri 21/11/25 | Wed 26/11/25 | Thu 5/11/26 | Mon 9/11/26 | 237d | 237d | 0ed | 0 | NA | NA | 16 October 2025 8:00 AM | 21 October 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
386 | 4352 | Yes | Auto Scheduled | Building C, Level 3 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 384 | 26 November 2025 8:00 AM | 2 December 2025 5:00 PM | Wed 26/11/25 | Tue 2/12/25 | Tue 1/09/26 | Mon 7/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 21 October 2025 8:00 AM | 27 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
387 | 4357 | Yes | Auto Scheduled | LEVEL 4 | 18 d | Fixed Duration | 4 | 18d |  | 11 December 2025 8:00 AM | 13 January 2026 5:00 PM | Thu 11/12/25 | Tue 13/01/26 | Tue 16/12/25 | Mon 9/11/26 | 3d | 3d | 0ed | 0 | NA | NA | 5 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
388 | 4362 | Yes | Auto Scheduled | Building A, Level 4 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 389SF | 11 December 2025 8:00 AM | 16 December 2025 8:00 AM | Thu 11/12/25 | Tue 16/12/25 | Thu 5/11/26 | Mon 9/11/26 | 223d | 223d | 0ed | 0 | NA | NA | 5 November 2025 8:00 AM | 10 November 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
389 | 4363 | Yes | Auto Scheduled | Building A, Level 4 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 352 | 16 December 2025 8:00 AM | 22 December 2025 5:00 PM | Tue 16/12/25 | Mon 22/12/25 | Tue 16/12/25 | Mon 22/12/25 | 0d | 0d | 0ed | 0 | NA | NA | 10 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
390 | 4371 | Yes | Auto Scheduled | Building B, Level 4 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 391SF | 18 December 2025 8:00 AM | 23 December 2025 8:00 AM | Thu 18/12/25 | Tue 23/12/25 | Thu 5/11/26 | Mon 9/11/26 | 218d | 218d | 0ed | 0 | NA | NA | 12 November 2025 8:00 AM | 17 November 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
391 | 4372 | Yes | Auto Scheduled | Building B, Level 4 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 389 | 23 December 2025 8:00 AM | 6 January 2026 5:00 PM | Tue 23/12/25 | Tue 6/01/26 | Tue 23/12/25 | Tue 6/01/26 | 0d | 0d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 21 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
392 | 4380 | Yes | Auto Scheduled | Building C, Level 4 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 393SF | 2 January 2026 8:00 AM | 7 January 2026 8:00 AM | Fri 2/01/26 | Wed 7/01/26 | Thu 5/11/26 | Mon 9/11/26 | 213d | 213d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 24 November 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
393 | 4381 | Yes | Auto Scheduled | Building C, Level 4 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 391 | 7 January 2026 8:00 AM | 13 January 2026 5:00 PM | Wed 7/01/26 | Tue 13/01/26 | Wed 7/01/26 | Tue 13/01/26 | 0d | 0d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.4.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
394 | 4384 | Yes | Auto Scheduled | LEVEL 5 | 18 d | Fixed Duration | 4 | 18d |  | 9 January 2026 8:00 AM | 4 February 2026 5:00 PM | Fri 9/01/26 | Wed 4/02/26 | Wed 14/01/26 | Mon 9/11/26 | 3d | 3d | 0ed | 0 | NA | NA | 26 November 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
395 | 4391 | Yes | Auto Scheduled | Building A, Level 5 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 396SF | 9 January 2026 8:00 AM | 14 January 2026 8:00 AM | Fri 9/01/26 | Wed 14/01/26 | Thu 5/11/26 | Mon 9/11/26 | 208d | 208d | 0ed | 0 | NA | NA | 26 November 2025 8:00 AM | 1 December 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
396 | 4392 | Yes | Auto Scheduled | Building A, Level 5 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 357,393 | 14 January 2026 8:00 AM | 20 January 2026 5:00 PM | Wed 14/01/26 | Tue 20/01/26 | Wed 14/01/26 | Tue 20/01/26 | 0d | 0d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 5 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
397 | 4400 | Yes | Auto Scheduled | Building B, Level 5 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 398SF | 16 January 2026 8:00 AM | 21 January 2026 8:00 AM | Fri 16/01/26 | Wed 21/01/26 | Thu 5/11/26 | Mon 9/11/26 | 203d | 203d | 0ed | 0 | NA | NA | 3 December 2025 8:00 AM | 8 December 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
398 | 4401 | Yes | Auto Scheduled | Building B, Level 5 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 396 | 21 January 2026 8:00 AM | 28 January 2026 5:00 PM | Wed 21/01/26 | Wed 28/01/26 | Wed 21/01/26 | Wed 28/01/26 | 0d | 0d | 0ed | 0 | NA | NA | 8 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
399 | 4409 | Yes | Auto Scheduled | Building C, Level 5 - Reveal Waterproofing | 3 d | Fixed Duration | 5 | 3d | 400SF | 23 January 2026 8:00 AM | 29 January 2026 8:00 AM | Fri 23/01/26 | Thu 29/01/26 | Thu 5/11/26 | Mon 9/11/26 | 198d | 198d | 0ed | 0 | NA | NA | 10 December 2025 8:00 AM | 15 December 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
400 | 4410 | Yes | Auto Scheduled | Building C, Level 5 - Window Installation | 5 d | Fixed Duration | 5 | 5d | 398 | 29 January 2026 8:00 AM | 4 February 2026 5:00 PM | Thu 29/01/26 | Wed 4/02/26 | Thu 29/01/26 | Wed 4/02/26 | 0d | 0d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 26/06/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
401 | 4531 | Yes | Auto Scheduled | All Buildings Water Tight | 0 d | Fixed Duration | 5 | 0d | 400 | 4 February 2026 5:00 PM | 4 February 2026 5:00 PM | Wed 4/02/26 | Wed 4/02/26 | Mon 9/11/26 | Mon 9/11/26 | 0d | 193d | 0ed | 0 | NA | NA | 19 December 2025 5:00 PM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.2.5.7 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
402 | 4411 | Yes | Auto Scheduled | EXTERNAL FINISHES | 133 d | Fixed Duration | 3 | 133d |  | 26 August 2025 8:00 AM | 10 March 2026 5:00 PM | Tue 26/08/25 | Tue 10/03/26 | Thu 5/02/26 | Mon 9/11/26 | 109d | 109d | 0ed | 0 | NA | NA | 21 July 2025 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
403 | 4436 | Yes | Auto Scheduled | LEVEL 1 | 25 d | Fixed Duration | 4 | 25d |  | 26 August 2025 8:00 AM | 30 September 2025 8:00 AM | Tue 26/08/25 | Tue 30/09/25 | Fri 23/10/26 | Mon 9/11/26 | 277d | 277d | 0ed | 0 | NA | NA | 21 July 2025 8:00 AM | 25 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
404 | 4437 | Yes | Auto Scheduled | Render | 12 d | Fixed Duration | 5 | 12d | 405SF | 26 August 2025 8:00 AM | 11 September 2025 8:00 AM | Tue 26/08/25 | Thu 11/09/25 | Fri 23/10/26 | Mon 9/11/26 | 290d | 290d | 0ed | 0 | NA | NA | 21 July 2025 8:00 AM | 6 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
405 | 4439 | Yes | Auto Scheduled | Paint | 8 d | Fixed Duration | 5 | 8d | 406SF | 11 September 2025 8:00 AM | 23 September 2025 8:00 AM | Thu 11/09/25 | Tue 23/09/25 | Thu 29/10/26 | Mon 9/11/26 | 0d | 282d | 0ed | 0 | NA | NA | 6 August 2025 8:00 AM | 18 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
406 | 4440 | Yes | Auto Scheduled | Awnings & Screens | 5 d | Fixed Duration | 5 | 5d | 408SF | 23 September 2025 8:00 AM | 30 September 2025 8:00 AM | Tue 23/09/25 | Tue 30/09/25 | Tue 3/11/26 | Mon 9/11/26 | 0d | 277d | 0ed | 0 | NA | NA | 18 August 2025 8:00 AM | 25 August 2025 8:00 AM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
407 | 4412 | Yes | Auto Scheduled | LEVEL 2 | 25 d | Fixed Duration | 4 | 25d |  | 30 September 2025 8:00 AM | 4 November 2025 5:00 PM | Tue 30/09/25 | Tue 4/11/25 | Tue 6/10/26 | Mon 9/11/26 | 252d | 252d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 26 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
408 | 4413 | Yes | Auto Scheduled | Building A - Render | 5 d | Fixed Duration | 5 | 5d | 379 | 30 September 2025 8:00 AM | 7 October 2025 5:00 PM | Tue 30/09/25 | Tue 7/10/25 | Tue 6/10/26 | Mon 12/10/26 | 0d | 252d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 29 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
409 | 4449 | Yes | Auto Scheduled | Building B - Render | 5 d | Fixed Duration | 5 | 5d | 377,408 | 8 October 2025 8:00 AM | 14 October 2025 5:00 PM | Wed 8/10/25 | Tue 14/10/25 | Wed 28/10/26 | Tue 3/11/26 | 0d | 263d | 0ed | 0 | NA | NA | 1 September 2025 8:00 AM | 5 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
410 | 4448 | Yes | Auto Scheduled | Building C - Render | 4 d | Fixed Duration | 5 | 4d | 379,409 | 15 October 2025 8:00 AM | 20 October 2025 5:00 PM | Wed 15/10/25 | Mon 20/10/25 | Wed 4/11/26 | Mon 9/11/26 | 263d | 263d | 0ed | 0 | NA | NA | 8 September 2025 8:00 AM | 11 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
411 | 4414 | Yes | Auto Scheduled | Building A - Cladding | 5 d | Fixed Duration | 5 | 5d | 408 | 8 October 2025 8:00 AM | 14 October 2025 5:00 PM | Wed 8/10/25 | Tue 14/10/25 | Tue 13/10/26 | Mon 19/10/26 | 0d | 252d | 0ed | 0 | NA | NA | 1 September 2025 8:00 AM | 5 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
412 | 4450 | Yes | Auto Scheduled | Building B - Cladding | 5 d | Fixed Duration | 5 | 5d | 411 | 15 October 2025 8:00 AM | 21 October 2025 5:00 PM | Wed 15/10/25 | Tue 21/10/25 | Wed 28/10/26 | Tue 3/11/26 | 0d | 258d | 0ed | 0 | NA | NA | 8 September 2025 8:00 AM | 12 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
413 | 4451 | Yes | Auto Scheduled | Building C - Cladding | 4 d | Fixed Duration | 5 | 4d | 412 | 22 October 2025 8:00 AM | 27 October 2025 5:00 PM | Wed 22/10/25 | Mon 27/10/25 | Wed 4/11/26 | Mon 9/11/26 | 258d | 258d | 0ed | 0 | NA | NA | 15 September 2025 8:00 AM | 18 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
414 | 4415 | Yes | Auto Scheduled | Building A - Paint | 4 d | Fixed Duration | 5 | 4d | 411 | 15 October 2025 8:00 AM | 20 October 2025 5:00 PM | Wed 15/10/25 | Mon 20/10/25 | Tue 20/10/26 | Fri 23/10/26 | 0d | 252d | 0ed | 0 | NA | NA | 8 September 2025 8:00 AM | 11 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
415 | 4452 | Yes | Auto Scheduled | Building B - Paint | 4 d | Fixed Duration | 5 | 4d | 414 | 21 October 2025 8:00 AM | 24 October 2025 5:00 PM | Tue 21/10/25 | Fri 24/10/25 | Fri 30/10/26 | Wed 4/11/26 | 0d | 256d | 0ed | 0 | NA | NA | 12 September 2025 8:00 AM | 17 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
416 | 4453 | Yes | Auto Scheduled | Building C - Paint | 3 d | Fixed Duration | 5 | 3d | 415 | 27 October 2025 8:00 AM | 29 October 2025 5:00 PM | Mon 27/10/25 | Wed 29/10/25 | Thu 5/11/26 | Mon 9/11/26 | 256d | 256d | 0ed | 0 | NA | NA | 18 September 2025 8:00 AM | 22 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
417 | 4424 | Yes | Auto Scheduled | Building A - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 414 | 21 October 2025 8:00 AM | 24 October 2025 5:00 PM | Tue 21/10/25 | Fri 24/10/25 | Mon 26/10/26 | Thu 29/10/26 | 0d | 252d | 0ed | 0 | NA | NA | 12 September 2025 8:00 AM | 17 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
418 | 4454 | Yes | Auto Scheduled | Building B - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 417 | 27 October 2025 8:00 AM | 30 October 2025 5:00 PM | Mon 27/10/25 | Thu 30/10/25 | Fri 30/10/26 | Wed 4/11/26 | 0d | 252d | 0ed | 0 | NA | NA | 18 September 2025 8:00 AM | 23 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
419 | 4455 | Yes | Auto Scheduled | Building C - Awnings, Screens & Balustrades | 3 d | Fixed Duration | 5 | 3d | 418 | 31 October 2025 8:00 AM | 4 November 2025 5:00 PM | Fri 31/10/25 | Tue 4/11/25 | Thu 5/11/26 | Mon 9/11/26 | 252d | 252d | 0ed | 0 | NA | NA | 24 September 2025 8:00 AM | 26 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.2.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
420 | 4458 | Yes | Auto Scheduled | LEVEL 3 | 25 d | Fixed Duration | 4 | 25d |  | 3 December 2025 8:00 AM | 14 January 2026 5:00 PM | Wed 3/12/25 | Wed 14/01/26 | Tue 6/10/26 | Mon 9/11/26 | 207d | 207d | 0ed | 0 | NA | NA | 28 October 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
421 | 4459 | Yes | Auto Scheduled | Building A - Render | 5 d | Fixed Duration | 5 | 5d | 386 | 3 December 2025 8:00 AM | 9 December 2025 5:00 PM | Wed 3/12/25 | Tue 9/12/25 | Tue 6/10/26 | Mon 12/10/26 | 0d | 207d | 0ed | 0 | NA | NA | 28 October 2025 8:00 AM | 3 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
422 | 4460 | Yes | Auto Scheduled | Building B - Render | 5 d | Fixed Duration | 5 | 5d | 421,384 | 10 December 2025 8:00 AM | 16 December 2025 5:00 PM | Wed 10/12/25 | Tue 16/12/25 | Wed 28/10/26 | Tue 3/11/26 | 0d | 218d | 0ed | 0 | NA | NA | 4 November 2025 8:00 AM | 10 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
423 | 4461 | Yes | Auto Scheduled | Building C - Render | 4 d | Fixed Duration | 5 | 4d | 422,386 | 17 December 2025 8:00 AM | 22 December 2025 5:00 PM | Wed 17/12/25 | Mon 22/12/25 | Wed 4/11/26 | Mon 9/11/26 | 218d | 218d | 0ed | 0 | NA | NA | 11 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
424 | 4462 | Yes | Auto Scheduled | Building A - Cladding | 5 d | Fixed Duration | 5 | 5d | 421 | 10 December 2025 8:00 AM | 16 December 2025 5:00 PM | Wed 10/12/25 | Tue 16/12/25 | Tue 13/10/26 | Mon 19/10/26 | 0d | 207d | 0ed | 0 | NA | NA | 4 November 2025 8:00 AM | 10 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
425 | 4463 | Yes | Auto Scheduled | Building B - Cladding | 5 d | Fixed Duration | 5 | 5d | 424 | 17 December 2025 8:00 AM | 23 December 2025 5:00 PM | Wed 17/12/25 | Tue 23/12/25 | Wed 28/10/26 | Tue 3/11/26 | 0d | 213d | 0ed | 0 | NA | NA | 11 November 2025 8:00 AM | 17 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
426 | 4464 | Yes | Auto Scheduled | Building C - Cladding | 4 d | Fixed Duration | 5 | 4d | 425 | 24 December 2025 8:00 AM | 6 January 2026 5:00 PM | Wed 24/12/25 | Tue 6/01/26 | Wed 4/11/26 | Mon 9/11/26 | 213d | 213d | 0ed | 0 | NA | NA | 18 November 2025 8:00 AM | 21 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
427 | 4465 | Yes | Auto Scheduled | Building A - Paint | 4 d | Fixed Duration | 5 | 4d | 424 | 17 December 2025 8:00 AM | 22 December 2025 5:00 PM | Wed 17/12/25 | Mon 22/12/25 | Tue 20/10/26 | Fri 23/10/26 | 0d | 207d | 0ed | 0 | NA | NA | 11 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
428 | 4466 | Yes | Auto Scheduled | Building B - Paint | 4 d | Fixed Duration | 5 | 4d | 427 | 23 December 2025 8:00 AM | 5 January 2026 5:00 PM | Tue 23/12/25 | Mon 5/01/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 211d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 20 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
429 | 4467 | Yes | Auto Scheduled | Building C - Paint | 3 d | Fixed Duration | 5 | 3d | 428 | 6 January 2026 8:00 AM | 8 January 2026 5:00 PM | Tue 6/01/26 | Thu 8/01/26 | Thu 5/11/26 | Mon 9/11/26 | 211d | 211d | 0ed | 0 | NA | NA | 21 November 2025 8:00 AM | 25 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
430 | 4468 | Yes | Auto Scheduled | Building A - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 427 | 23 December 2025 8:00 AM | 5 January 2026 5:00 PM | Tue 23/12/25 | Mon 5/01/26 | Mon 26/10/26 | Thu 29/10/26 | 0d | 207d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 20 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
431 | 4469 | Yes | Auto Scheduled | Building B - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 430 | 6 January 2026 8:00 AM | 9 January 2026 5:00 PM | Tue 6/01/26 | Fri 9/01/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 207d | 0ed | 0 | NA | NA | 21 November 2025 8:00 AM | 26 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
432 | 4470 | Yes | Auto Scheduled | Building C - Awnings, Screens & Balustrades | 3 d | Fixed Duration | 5 | 3d | 431 | 12 January 2026 8:00 AM | 14 January 2026 5:00 PM | Mon 12/01/26 | Wed 14/01/26 | Thu 5/11/26 | Mon 9/11/26 | 207d | 207d | 0ed | 0 | NA | NA | 27 November 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.3.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
433 | 4474 | Yes | Auto Scheduled | LEVEL 4 | 24 d | Fixed Duration | 4 | 24d |  | 14 January 2026 8:00 AM | 17 February 2026 5:00 PM | Wed 14/01/26 | Tue 17/02/26 | Wed 7/10/26 | Mon 9/11/26 | 184d | 184d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 9 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
434 | 4475 | Yes | Auto Scheduled | Building A - Render | 4 d | Fixed Duration | 5 | 4d | 393 | 14 January 2026 8:00 AM | 19 January 2026 5:00 PM | Wed 14/01/26 | Mon 19/01/26 | Wed 7/10/26 | Mon 12/10/26 | 0d | 184d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 4 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
435 | 4476 | Yes | Auto Scheduled | Building B - Render | 4 d | Fixed Duration | 5 | 4d | 434 | 20 January 2026 8:00 AM | 23 January 2026 5:00 PM | Tue 20/01/26 | Fri 23/01/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 197d | 0ed | 0 | NA | NA | 5 December 2025 8:00 AM | 10 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
436 | 4477 | Yes | Auto Scheduled | Building C - Render | 3 d | Fixed Duration | 5 | 3d | 435 | 27 January 2026 8:00 AM | 29 January 2026 5:00 PM | Tue 27/01/26 | Thu 29/01/26 | Thu 5/11/26 | Mon 9/11/26 | 197d | 197d | 0ed | 0 | NA | NA | 11 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
437 | 4478 | Yes | Auto Scheduled | Building A - Cladding | 6 d | Fixed Duration | 5 | 6d | 434 | 20 January 2026 8:00 AM | 28 January 2026 5:00 PM | Tue 20/01/26 | Wed 28/01/26 | Tue 13/10/26 | Tue 20/10/26 | 0d | 184d | 0ed | 0 | NA | NA | 5 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
438 | 4479 | Yes | Auto Scheduled | Building B - Cladding | 6 d | Fixed Duration | 5 | 6d | 437 | 29 January 2026 8:00 AM | 5 February 2026 5:00 PM | Thu 29/01/26 | Thu 5/02/26 | Mon 26/10/26 | Mon 2/11/26 | 0d | 187d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 22 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
439 | 4480 | Yes | Auto Scheduled | Building C - Cladding | 5 d | Fixed Duration | 5 | 5d | 438 | 6 February 2026 8:00 AM | 12 February 2026 5:00 PM | Fri 6/02/26 | Thu 12/02/26 | Tue 3/11/26 | Mon 9/11/26 | 187d | 187d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
440 | 4481 | Yes | Auto Scheduled | Building A - Paint | 3 d | Fixed Duration | 5 | 3d | 437 | 29 January 2026 8:00 AM | 2 February 2026 5:00 PM | Thu 29/01/26 | Mon 2/02/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 184d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 17 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
441 | 4482 | Yes | Auto Scheduled | Building B - Paint | 3 d | Fixed Duration | 5 | 3d | 440 | 3 February 2026 8:00 AM | 5 February 2026 5:00 PM | Tue 3/02/26 | Thu 5/02/26 | Tue 3/11/26 | Thu 5/11/26 | 0d | 190d | 0ed | 0 | NA | NA | 18 December 2025 8:00 AM | 22 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
442 | 4483 | Yes | Auto Scheduled | Building C - Paint | 2 d | Fixed Duration | 5 | 2d | 441 | 6 February 2026 8:00 AM | 9 February 2026 5:00 PM | Fri 6/02/26 | Mon 9/02/26 | Fri 6/11/26 | Mon 9/11/26 | 190d | 190d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 24 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
443 | 4484 | Yes | Auto Scheduled | Building A - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 440 | 3 February 2026 8:00 AM | 6 February 2026 5:00 PM | Tue 3/02/26 | Fri 6/02/26 | Mon 26/10/26 | Thu 29/10/26 | 0d | 184d | 0ed | 0 | NA | NA | 18 December 2025 8:00 AM | 23 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
444 | 4485 | Yes | Auto Scheduled | Building B - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 443 | 9 February 2026 8:00 AM | 12 February 2026 5:00 PM | Mon 9/02/26 | Thu 12/02/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 184d | 0ed | 0 | NA | NA | 24 December 2025 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
445 | 4486 | Yes | Auto Scheduled | Building C - Awnings, Screens & Balustrades | 3 d | Fixed Duration | 5 | 3d | 444 | 13 February 2026 8:00 AM | 17 February 2026 5:00 PM | Fri 13/02/26 | Tue 17/02/26 | Thu 5/11/26 | Mon 9/11/26 | 184d | 184d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 9 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.4.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
446 | 4490 | Yes | Auto Scheduled | LEVEL 5 | 24 d | Fixed Duration | 4 | 24d |  | 5 February 2026 8:00 AM | 10 March 2026 5:00 PM | Thu 5/02/26 | Tue 10/03/26 | Thu 5/02/26 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | NA | NA | 22 December 2025 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
447 | 4491 | Yes | Auto Scheduled | Building A - Render | 4 d | Fixed Duration | 5 | 4d | 400 | 5 February 2026 8:00 AM | 10 February 2026 5:00 PM | Thu 5/02/26 | Tue 10/02/26 | Thu 5/02/26 | Tue 10/02/26 | 0d | 0d | 0ed | 0 | NA | NA | 22 December 2025 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
448 | 4492 | Yes | Auto Scheduled | Building B - Render | 4 d | Fixed Duration | 5 | 4d | 447 | 11 February 2026 8:00 AM | 16 February 2026 5:00 PM | Wed 11/02/26 | Mon 16/02/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 182d | 0ed | 0 | NA | NA | 5 January 2026 8:00 AM | 8 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
449 | 4493 | Yes | Auto Scheduled | Building C - Render | 3 d | Fixed Duration | 5 | 3d | 448 | 17 February 2026 8:00 AM | 19 February 2026 5:00 PM | Tue 17/02/26 | Thu 19/02/26 | Thu 5/11/26 | Mon 9/11/26 | 182d | 182d | 0ed | 0 | NA | NA | 9 January 2026 8:00 AM | 13 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
450 | 4494 | Yes | Auto Scheduled | Building A - Cladding | 6 d | Fixed Duration | 5 | 6d | 447 | 11 February 2026 8:00 AM | 18 February 2026 5:00 PM | Wed 11/02/26 | Wed 18/02/26 | Wed 11/02/26 | Wed 18/02/26 | 0d | 0d | 0ed | 0 | NA | NA | 5 January 2026 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
451 | 4495 | Yes | Auto Scheduled | Building B - Cladding | 6 d | Fixed Duration | 5 | 6d | 450 | 19 February 2026 8:00 AM | 26 February 2026 5:00 PM | Thu 19/02/26 | Thu 26/02/26 | Mon 26/10/26 | Mon 2/11/26 | 0d | 172d | 0ed | 0 | NA | NA | 13 January 2026 8:00 AM | 20 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
452 | 4496 | Yes | Auto Scheduled | Building C - Cladding | 5 d | Fixed Duration | 5 | 5d | 451 | 27 February 2026 8:00 AM | 5 March 2026 5:00 PM | Fri 27/02/26 | Thu 5/03/26 | Tue 3/11/26 | Mon 9/11/26 | 172d | 172d | 0ed | 0 | NA | NA | 21 January 2026 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
453 | 4497 | Yes | Auto Scheduled | Building A - Paint | 3 d | Fixed Duration | 5 | 3d | 450 | 19 February 2026 8:00 AM | 23 February 2026 5:00 PM | Thu 19/02/26 | Mon 23/02/26 | Thu 19/02/26 | Mon 23/02/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 January 2026 8:00 AM | 15 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
454 | 4498 | Yes | Auto Scheduled | Building B - Paint | 3 d | Fixed Duration | 5 | 3d | 453 | 24 February 2026 8:00 AM | 26 February 2026 5:00 PM | Tue 24/02/26 | Thu 26/02/26 | Tue 3/11/26 | Thu 5/11/26 | 0d | 175d | 0ed | 0 | NA | NA | 16 January 2026 8:00 AM | 20 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
455 | 4499 | Yes | Auto Scheduled | Building C - Paint | 2 d | Fixed Duration | 5 | 2d | 454 | 27 February 2026 8:00 AM | 2 March 2026 5:00 PM | Fri 27/02/26 | Mon 2/03/26 | Fri 6/11/26 | Mon 9/11/26 | 175d | 175d | 0ed | 0 | NA | NA | 21 January 2026 8:00 AM | 22 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
456 | 4500 | Yes | Auto Scheduled | Building A - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 453 | 24 February 2026 8:00 AM | 27 February 2026 5:00 PM | Tue 24/02/26 | Fri 27/02/26 | Tue 24/02/26 | Fri 27/02/26 | 0d | 0d | 0ed | 0 | NA | NA | 16 January 2026 8:00 AM | 21 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
457 | 4501 | Yes | Auto Scheduled | Building B - Awnings, Screens & Balustrades | 4 d | Fixed Duration | 5 | 4d | 456 | 2 March 2026 8:00 AM | 5 March 2026 5:00 PM | Mon 2/03/26 | Thu 5/03/26 | Mon 2/03/26 | Thu 5/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 22 January 2026 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
458 | 4502 | Yes | Auto Scheduled | Building C - Awnings, Screens & Balustrades | 3 d | Fixed Duration | 5 | 3d | 457 | 6 March 2026 8:00 AM | 10 March 2026 5:00 PM | Fri 6/03/26 | Tue 10/03/26 | Fri 6/03/26 | Tue 10/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 29 January 2026 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
459 | 4532 | Yes | Auto Scheduled | External Façade Finishes Complete | 0 d | Fixed Duration | 5 | 0d | 458 | 10 March 2026 5:00 PM | 10 March 2026 5:00 PM | Tue 10/03/26 | Tue 10/03/26 | Mon 9/11/26 | Mon 9/11/26 | 0d | 169d | 0ed | 0 | NA | NA | 2 February 2026 5:00 PM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.3.5.13 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
460 | 4518 | Yes | Auto Scheduled | SCAFFOLD REMOVAL | 28 d | Fixed Duration | 3 | 28d |  | 11 March 2026 8:00 AM | 21 April 2026 5:00 PM | Wed 11/03/26 | Tue 21/04/26 | Wed 11/03/26 | Wed 22/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
461 | 4519 | Yes | Auto Scheduled | Roof Level - Drop Scaffold/ Remove Ties | 1 d | Fixed Duration | 4 | 1d | 458 | 11 March 2026 8:00 AM | 11 March 2026 5:00 PM | Wed 11/03/26 | Wed 11/03/26 | Wed 11/03/26 | Wed 11/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 3 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
462 | 4520 | Yes | Auto Scheduled | Roof Level - Patch & Paint Tie Locations | 2 d | Fixed Duration | 4 | 2d | 461 | 12 March 2026 8:00 AM | 13 March 2026 5:00 PM | Thu 12/03/26 | Fri 13/03/26 | Thu 12/03/26 | Fri 13/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 4 February 2026 8:00 AM | 5 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
463 | 4521 | Yes | Auto Scheduled | Level 5 - Drop Scaffold/ Remove Ties | 2 d | Fixed Duration | 4 | 2d | 462 | 16 March 2026 8:00 AM | 17 March 2026 5:00 PM | Mon 16/03/26 | Tue 17/03/26 | Mon 16/03/26 | Tue 17/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 6 February 2026 8:00 AM | 9 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
464 | 4522 | Yes | Auto Scheduled | Level 5 - Patch & Paint Tie Locations | 3 d | Fixed Duration | 4 | 3d | 463 | 18 March 2026 8:00 AM | 20 March 2026 5:00 PM | Wed 18/03/26 | Fri 20/03/26 | Wed 18/03/26 | Fri 20/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 10 February 2026 8:00 AM | 12 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
465 | 4523 | Yes | Auto Scheduled | Level 4 - Drop Scaffold/ Remove Ties | 2 d | Fixed Duration | 4 | 2d | 464 | 23 March 2026 8:00 AM | 24 March 2026 5:00 PM | Mon 23/03/26 | Tue 24/03/26 | Mon 23/03/26 | Tue 24/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 February 2026 8:00 AM | 16 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
466 | 4524 | Yes | Auto Scheduled | Level 4 - Patch & Paint Tie Locations | 3 d | Fixed Duration | 4 | 3d | 465 | 25 March 2026 8:00 AM | 27 March 2026 5:00 PM | Wed 25/03/26 | Fri 27/03/26 | Wed 25/03/26 | Fri 27/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 17 February 2026 8:00 AM | 19 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
467 | 4525 | Yes | Auto Scheduled | Level 3 - Drop Scaffold/ Remove Ties | 2 d | Fixed Duration | 4 | 2d | 466 | 30 March 2026 8:00 AM | 31 March 2026 5:00 PM | Mon 30/03/26 | Tue 31/03/26 | Mon 30/03/26 | Tue 31/03/26 | 0d | 0d | 0ed | 0 | NA | NA | 20 February 2026 8:00 AM | 23 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
468 | 4526 | Yes | Auto Scheduled | Level 3 - Patch & Paint Tie Locations | 3 d | Fixed Duration | 4 | 3d | 467 | 1 April 2026 8:00 AM | 7 April 2026 5:00 PM | Wed 1/04/26 | Tue 7/04/26 | Wed 1/04/26 | Tue 7/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 24 February 2026 8:00 AM | 26 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
469 | 4527 | Yes | Auto Scheduled | Level 2 - Drop Scaffold/ Remove Ties | 2 d | Fixed Duration | 4 | 2d | 468 | 8 April 2026 8:00 AM | 9 April 2026 5:00 PM | Wed 8/04/26 | Thu 9/04/26 | Wed 8/04/26 | Thu 9/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 27 February 2026 8:00 AM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
470 | 4528 | Yes | Auto Scheduled | Level 2 - Patch & Paint Tie Locations | 3 d | Fixed Duration | 4 | 3d | 469 | 10 April 2026 8:00 AM | 14 April 2026 5:00 PM | Fri 10/04/26 | Tue 14/04/26 | Fri 10/04/26 | Tue 14/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 3 March 2026 8:00 AM | 5 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
471 | 4529 | Yes | Auto Scheduled | Level 1 - Drop Scaffold/ Remove Ties | 2 d | Fixed Duration | 4 | 2d | 470 | 15 April 2026 8:00 AM | 16 April 2026 5:00 PM | Wed 15/04/26 | Thu 16/04/26 | Wed 15/04/26 | Thu 16/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 6 March 2026 8:00 AM | 9 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
472 | 4530 | Yes | Auto Scheduled | Level 1 - Patch & Paint Tie Locations | 3 d | Fixed Duration | 4 | 3d | 471 | 17 April 2026 8:00 AM | 21 April 2026 5:00 PM | Fri 17/04/26 | Tue 21/04/26 | Fri 17/04/26 | Tue 21/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 10 March 2026 8:00 AM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
473 | 4533 | Yes | Auto Scheduled | Scaffold Removed from Site | 0 d | Fixed Duration | 4 | 0d | 472 | 21 April 2026 5:00 PM | 21 April 2026 5:00 PM | Tue 21/04/26 | Tue 21/04/26 | Wed 22/04/26 | Wed 22/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 12 March 2026 5:00 PM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.3.4.13 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
474 | 4801 | Yes | Auto Scheduled | BUILDING SERVICES | 78 d | Fixed Duration | 2 | 78d |  | 15 January 2026 8:00 AM | 8 May 2026 5:00 PM | Thu 15/01/26 | Fri 8/05/26 | Wed 12/08/26 | Mon 9/11/26 | 129d | 129d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 30 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
475 | 4802 | Yes | Auto Scheduled | LIFT | 63 d | Fixed Duration | 3 | 63d |  | 15 January 2026 8:00 AM | 16 April 2026 5:00 PM | Thu 15/01/26 | Thu 16/04/26 | Wed 12/08/26 | Mon 9/11/26 | 144d | 144d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 9 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
476 | 4803 | Yes | Auto Scheduled | Scaffold to Shaft | 2 d | Fixed Duration | 4 | 2d | 338,59 | 15 January 2026 8:00 AM | 16 January 2026 5:00 PM | Thu 15/01/26 | Fri 16/01/26 | Wed 12/08/26 | Thu 13/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
477 | 4817 | Yes | Auto Scheduled | Lift Cages to Shaft Openings | 1 d | Fixed Duration | 4 | 1d | 476 | 19 January 2026 8:00 AM | 19 January 2026 5:00 PM | Mon 19/01/26 | Mon 19/01/26 | Fri 14/08/26 | Fri 14/08/26 | 0d | 144d | 0ed | 0 | NA | NA | 4 December 2025 8:00 AM | 4 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
478 | 4805 | Yes | Auto Scheduled | Lift Construction | 50 d | Fixed Duration | 4 | 50d | 477 | 20 January 2026 8:00 AM | 31 March 2026 5:00 PM | Tue 20/01/26 | Tue 31/03/26 | Mon 17/08/26 | Mon 26/10/26 | 0d | 144d | 0ed | 0 | NA | NA | 5 December 2025 8:00 AM | 23 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
479 | 4815 | Yes | Auto Scheduled | Lift Test & Commission | 10 d | Fixed Duration | 4 | 10d | 478 | 1 April 2026 8:00 AM | 16 April 2026 5:00 PM | Wed 1/04/26 | Thu 16/04/26 | Tue 27/10/26 | Mon 9/11/26 | 0d | 144d | 0ed | 0 | NA | NA | 24 February 2026 8:00 AM | 9 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
480 | 4816 | Yes | Auto Scheduled | Builder's Lift Available | 0 d | Fixed Duration | 4 | 0d | 479 | 16 April 2026 5:00 PM | 16 April 2026 5:00 PM | Thu 16/04/26 | Thu 16/04/26 | Mon 9/11/26 | Mon 9/11/26 | 144d | 144d | 0ed | 0 | NA | NA | 9 March 2026 5:00 PM | 9 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.1.5 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
481 | 4811 | Yes | Auto Scheduled | PAD MOUNT SUBSTATION | 12 d | Fixed Duration | 3 | 12d |  | 22 April 2026 8:00 AM | 8 May 2026 5:00 PM | Wed 22/04/26 | Fri 8/05/26 | Fri 23/10/26 | Mon 9/11/26 | 129d | 129d | 0ed | 0 | NA | NA | 13 March 2026 8:00 AM | 30 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
482 | 4812 | Yes | Auto Scheduled | Easement Survey & Pegging | 1 d | Fixed Duration | 4 | 1d | 472 | 22 April 2026 8:00 AM | 22 April 2026 5:00 PM | Wed 22/04/26 | Wed 22/04/26 | Fri 23/10/26 | Fri 23/10/26 | 0d | 129d | 0ed | 0 | NA | NA | 13 March 2026 8:00 AM | 13 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
483 | 4813 | Yes | Auto Scheduled | Foundation Installation | 3 d | Fixed Duration | 4 | 3d | 482 | 23 April 2026 8:00 AM | 27 April 2026 5:00 PM | Thu 23/04/26 | Mon 27/04/26 | Mon 26/10/26 | Wed 28/10/26 | 0d | 129d | 0ed | 0 | NA | NA | 16 March 2026 8:00 AM | 18 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
484 | 4814 | Yes | Auto Scheduled | Pad Mount Substation Landing | 2 d | Fixed Duration | 4 | 2d | 483 | 28 April 2026 8:00 AM | 29 April 2026 5:00 PM | Tue 28/04/26 | Wed 29/04/26 | Thu 29/10/26 | Fri 30/10/26 | 0d | 129d | 0ed | 0 | NA | NA | 19 March 2026 8:00 AM | 20 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
485 | 4806 | Yes | Auto Scheduled | Network Connection | 5 d | Fixed Duration | 4 | 5d | 484 | 30 April 2026 8:00 AM | 7 May 2026 5:00 PM | Thu 30/04/26 | Thu 7/05/26 | Mon 2/11/26 | Fri 6/11/26 | 0d | 129d | 0ed | 0 | NA | NA | 23 March 2026 8:00 AM | 27 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
486 | 4800 | Yes | Auto Scheduled | Energisation | 1 d | Fixed Duration | 4 | 1d | 485 | 8 May 2026 8:00 AM | 8 May 2026 5:00 PM | Fri 8/05/26 | Fri 8/05/26 | Mon 9/11/26 | Mon 9/11/26 | 129d | 129d | 0ed | 0 | NA | NA | 30 March 2026 8:00 AM | 30 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
487 | 4846 | Yes | Auto Scheduled | Permanent Power Available | 0 d | Fixed Duration | 4 | 0d | 485 | 7 May 2026 5:00 PM | 7 May 2026 5:00 PM | Thu 7/05/26 | Thu 7/05/26 | Mon 9/11/26 | Mon 9/11/26 | 130d | 130d | 0ed | 0 | NA | NA | 27 March 2026 5:00 PM | 27 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.4.2.6 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
488 | 4535 | Yes | Auto Scheduled | INTERNAL FINISHES | 148 d | Fixed Duration | 2 | 148d |  | 2 September 2025 8:00 AM | 9 April 2026 5:00 PM | Tue 2/09/25 | Thu 9/04/26 | Wed 12/08/26 | Mon 9/11/26 | 149d | 149d | 0ed | 0 | NA | NA | 28 July 2025 8:00 AM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
489 | 4536 | Yes | Auto Scheduled | LEVEL 2 - BUILDING A | 58 d | Fixed Duration | 3 | 58d |  | 2 September 2025 8:00 AM | 21 November 2025 5:00 PM | Tue 2/09/25 | Fri 21/11/25 | Wed 19/08/26 | Mon 9/11/26 | 239d | 239d | 0ed | 0 | NA | NA | 28 July 2025 8:00 AM | 16 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
490 | 4537 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 341,375FS-10d | 2 September 2025 8:00 AM | 8 September 2025 5:00 PM | Tue 2/09/25 | Mon 8/09/25 | Wed 19/08/26 | Tue 25/08/26 | 0d | 239d | 0ed | 0 | NA | NA | 28 July 2025 8:00 AM | 1 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
491 | 4538 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 490 | 9 September 2025 8:00 AM | 11 September 2025 5:00 PM | Tue 9/09/25 | Thu 11/09/25 | Wed 26/08/26 | Fri 28/08/26 | 0d | 239d | 0ed | 0 | NA | NA | 4 August 2025 8:00 AM | 6 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
492 | 4539 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 491 | 12 September 2025 8:00 AM | 15 September 2025 5:00 PM | Fri 12/09/25 | Mon 15/09/25 | Mon 31/08/26 | Tue 1/09/26 | 0d | 239d | 0ed | 0 | NA | NA | 7 August 2025 8:00 AM | 8 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
493 | 4540 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 492 | 16 September 2025 8:00 AM | 22 September 2025 5:00 PM | Tue 16/09/25 | Mon 22/09/25 | Wed 2/09/26 | Tue 8/09/26 | 0d | 239d | 0ed | 0 | NA | NA | 11 August 2025 8:00 AM | 15 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
494 | 4541 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 493 | 23 September 2025 8:00 AM | 25 September 2025 5:00 PM | Tue 23/09/25 | Thu 25/09/25 | Wed 9/09/26 | Fri 11/09/26 | 0d | 239d | 0ed | 0 | NA | NA | 18 August 2025 8:00 AM | 20 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
495 | 4542 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 494 | 26 September 2025 8:00 AM | 30 September 2025 5:00 PM | Fri 26/09/25 | Tue 30/09/25 | Mon 14/09/26 | Wed 16/09/26 | 0d | 239d | 0ed | 0 | NA | NA | 21 August 2025 8:00 AM | 25 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
496 | 4543 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 495 | 1 October 2025 8:00 AM | 8 October 2025 5:00 PM | Wed 1/10/25 | Wed 8/10/25 | Thu 17/09/26 | Wed 23/09/26 | 0d | 239d | 0ed | 0 | NA | NA | 26 August 2025 8:00 AM | 1 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
497 | 4544 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 496 | 9 October 2025 8:00 AM | 22 October 2025 5:00 PM | Thu 9/10/25 | Wed 22/10/25 | Thu 24/09/26 | Thu 8/10/26 | 0d | 239d | 0ed | 0 | NA | NA | 2 September 2025 8:00 AM | 15 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
498 | 4545 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 497 | 23 October 2025 8:00 AM | 28 October 2025 5:00 PM | Thu 23/10/25 | Tue 28/10/25 | Wed 4/11/26 | Mon 9/11/26 | 257d | 257d | 0ed | 0 | NA | NA | 16 September 2025 8:00 AM | 19 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
499 | 4546 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 497 | 23 October 2025 8:00 AM | 29 October 2025 5:00 PM | Thu 23/10/25 | Wed 29/10/25 | Fri 9/10/26 | Thu 15/10/26 | 0d | 239d | 0ed | 0 | NA | NA | 16 September 2025 8:00 AM | 22 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
500 | 4551 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 499 | 30 October 2025 8:00 AM | 3 November 2025 5:00 PM | Thu 30/10/25 | Mon 3/11/25 | Fri 16/10/26 | Tue 20/10/26 | 0d | 239d | 0ed | 0 | NA | NA | 23 September 2025 8:00 AM | 25 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
501 | 4547 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 500 | 4 November 2025 8:00 AM | 6 November 2025 5:00 PM | Tue 4/11/25 | Thu 6/11/25 | Wed 21/10/26 | Fri 23/10/26 | 0d | 239d | 0ed | 0 | NA | NA | 26 September 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
502 | 4548 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 501 | 7 November 2025 8:00 AM | 13 November 2025 5:00 PM | Fri 7/11/25 | Thu 13/11/25 | Mon 26/10/26 | Fri 30/10/26 | 0d | 239d | 0ed | 0 | NA | NA | 1 October 2025 8:00 AM | 8 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
503 | 4549 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 502 | 14 November 2025 8:00 AM | 18 November 2025 5:00 PM | Fri 14/11/25 | Tue 18/11/25 | Mon 2/11/26 | Wed 4/11/26 | 0d | 239d | 0ed | 0 | NA | NA | 9 October 2025 8:00 AM | 13 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
504 | 4550 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 503 | 19 November 2025 8:00 AM | 21 November 2025 5:00 PM | Wed 19/11/25 | Fri 21/11/25 | Thu 5/11/26 | Mon 9/11/26 | 239d | 239d | 0ed | 0 | NA | NA | 14 October 2025 8:00 AM | 16 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.1.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
505 | 4552 | Yes | Auto Scheduled | LEVEL 2 - BUILDING B | 58 d | Fixed Duration | 3 | 58d |  | 9 September 2025 8:00 AM | 28 November 2025 5:00 PM | Tue 9/09/25 | Fri 28/11/25 | Wed 19/08/26 | Mon 9/11/26 | 234d | 234d | 0ed | 0 | NA | NA | 4 August 2025 8:00 AM | 23 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
506 | 4553 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 342,377FS-10d | 9 September 2025 8:00 AM | 15 September 2025 5:00 PM | Tue 9/09/25 | Mon 15/09/25 | Wed 19/08/26 | Tue 25/08/26 | 0d | 234d | 0ed | 0 | NA | NA | 4 August 2025 8:00 AM | 8 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
507 | 4554 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 506 | 16 September 2025 8:00 AM | 18 September 2025 5:00 PM | Tue 16/09/25 | Thu 18/09/25 | Wed 26/08/26 | Fri 28/08/26 | 0d | 234d | 0ed | 0 | NA | NA | 11 August 2025 8:00 AM | 13 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
508 | 4555 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 507 | 19 September 2025 8:00 AM | 22 September 2025 5:00 PM | Fri 19/09/25 | Mon 22/09/25 | Mon 31/08/26 | Tue 1/09/26 | 0d | 234d | 0ed | 0 | NA | NA | 14 August 2025 8:00 AM | 15 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
509 | 4556 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 508 | 23 September 2025 8:00 AM | 29 September 2025 5:00 PM | Tue 23/09/25 | Mon 29/09/25 | Wed 2/09/26 | Tue 8/09/26 | 0d | 234d | 0ed | 0 | NA | NA | 18 August 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
510 | 4557 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 509 | 30 September 2025 8:00 AM | 2 October 2025 5:00 PM | Tue 30/09/25 | Thu 2/10/25 | Wed 9/09/26 | Fri 11/09/26 | 0d | 234d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 27 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
511 | 4558 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 510 | 3 October 2025 8:00 AM | 8 October 2025 5:00 PM | Fri 3/10/25 | Wed 8/10/25 | Mon 14/09/26 | Wed 16/09/26 | 0d | 234d | 0ed | 0 | NA | NA | 28 August 2025 8:00 AM | 1 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
512 | 4559 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 511 | 9 October 2025 8:00 AM | 15 October 2025 5:00 PM | Thu 9/10/25 | Wed 15/10/25 | Thu 17/09/26 | Wed 23/09/26 | 0d | 234d | 0ed | 0 | NA | NA | 2 September 2025 8:00 AM | 8 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
513 | 4560 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 512 | 16 October 2025 8:00 AM | 29 October 2025 5:00 PM | Thu 16/10/25 | Wed 29/10/25 | Thu 24/09/26 | Thu 8/10/26 | 0d | 234d | 0ed | 0 | NA | NA | 9 September 2025 8:00 AM | 22 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
514 | 4561 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 513 | 30 October 2025 8:00 AM | 4 November 2025 5:00 PM | Thu 30/10/25 | Tue 4/11/25 | Wed 4/11/26 | Mon 9/11/26 | 252d | 252d | 0ed | 0 | NA | NA | 23 September 2025 8:00 AM | 26 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
515 | 4562 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 513 | 30 October 2025 8:00 AM | 5 November 2025 5:00 PM | Thu 30/10/25 | Wed 5/11/25 | Fri 9/10/26 | Thu 15/10/26 | 0d | 234d | 0ed | 0 | NA | NA | 23 September 2025 8:00 AM | 29 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
516 | 4563 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 515 | 6 November 2025 8:00 AM | 10 November 2025 5:00 PM | Thu 6/11/25 | Mon 10/11/25 | Fri 16/10/26 | Tue 20/10/26 | 0d | 234d | 0ed | 0 | NA | NA | 30 September 2025 8:00 AM | 2 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
517 | 4564 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 516 | 11 November 2025 8:00 AM | 13 November 2025 5:00 PM | Tue 11/11/25 | Thu 13/11/25 | Wed 21/10/26 | Fri 23/10/26 | 0d | 234d | 0ed | 0 | NA | NA | 3 October 2025 8:00 AM | 8 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
518 | 4565 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 517 | 14 November 2025 8:00 AM | 20 November 2025 5:00 PM | Fri 14/11/25 | Thu 20/11/25 | Mon 26/10/26 | Fri 30/10/26 | 0d | 234d | 0ed | 0 | NA | NA | 9 October 2025 8:00 AM | 15 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
519 | 4566 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 518 | 21 November 2025 8:00 AM | 25 November 2025 5:00 PM | Fri 21/11/25 | Tue 25/11/25 | Mon 2/11/26 | Wed 4/11/26 | 0d | 234d | 0ed | 0 | NA | NA | 16 October 2025 8:00 AM | 20 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
520 | 4567 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 519 | 26 November 2025 8:00 AM | 28 November 2025 5:00 PM | Wed 26/11/25 | Fri 28/11/25 | Thu 5/11/26 | Mon 9/11/26 | 234d | 234d | 0ed | 0 | NA | NA | 21 October 2025 8:00 AM | 23 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.2.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
521 | 4568 | Yes | Auto Scheduled | LEVEL 2 - BUILDING C | 52 d | Fixed Duration | 3 | 52d |  | 18 September 2025 8:00 AM | 1 December 2025 5:00 PM | Thu 18/09/25 | Mon 1/12/25 | Thu 27/08/26 | Mon 9/11/26 | 233d | 233d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 24 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
522 | 4569 | Yes | Auto Scheduled | Service Rough-In | 4 d | Fixed Duration | 4 | 4d | 343,379FS-8d | 18 September 2025 8:00 AM | 23 September 2025 5:00 PM | Thu 18/09/25 | Tue 23/09/25 | Thu 27/08/26 | Tue 1/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 13 August 2025 8:00 AM | 18 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
523 | 4570 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 2 d | Fixed Duration | 4 | 2d | 522 | 24 September 2025 8:00 AM | 25 September 2025 5:00 PM | Wed 24/09/25 | Thu 25/09/25 | Wed 2/09/26 | Thu 3/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 19 August 2025 8:00 AM | 20 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
524 | 4571 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 523 | 26 September 2025 8:00 AM | 29 September 2025 5:00 PM | Fri 26/09/25 | Mon 29/09/25 | Fri 4/09/26 | Mon 7/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 21 August 2025 8:00 AM | 22 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
525 | 4572 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 524 | 30 September 2025 8:00 AM | 7 October 2025 5:00 PM | Tue 30/09/25 | Tue 7/10/25 | Tue 8/09/26 | Mon 14/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 25 August 2025 8:00 AM | 29 August 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
526 | 4573 | Yes | Auto Scheduled | Wet Area Screeds | 2 d | Fixed Duration | 4 | 2d | 525 | 8 October 2025 8:00 AM | 9 October 2025 5:00 PM | Wed 8/10/25 | Thu 9/10/25 | Tue 15/09/26 | Wed 16/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 1 September 2025 8:00 AM | 2 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
527 | 4574 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 526 | 10 October 2025 8:00 AM | 14 October 2025 5:00 PM | Fri 10/10/25 | Tue 14/10/25 | Thu 17/09/26 | Mon 21/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 3 September 2025 8:00 AM | 5 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
528 | 4575 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 4 d | Fixed Duration | 4 | 4d | 527 | 15 October 2025 8:00 AM | 20 October 2025 5:00 PM | Wed 15/10/25 | Mon 20/10/25 | Tue 22/09/26 | Fri 25/09/26 | 0d | 233d | 0ed | 0 | NA | NA | 8 September 2025 8:00 AM | 11 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
529 | 4576 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 528 | 21 October 2025 8:00 AM | 3 November 2025 5:00 PM | Tue 21/10/25 | Mon 3/11/25 | Mon 28/09/26 | Mon 12/10/26 | 0d | 233d | 0ed | 0 | NA | NA | 12 September 2025 8:00 AM | 25 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
530 | 4577 | Yes | Auto Scheduled | Balcony Floor Tiles | 3 d | Fixed Duration | 4 | 3d | 529 | 4 November 2025 8:00 AM | 6 November 2025 5:00 PM | Tue 4/11/25 | Thu 6/11/25 | Thu 5/11/26 | Mon 9/11/26 | 250d | 250d | 0ed | 0 | NA | NA | 26 September 2025 8:00 AM | 30 September 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
531 | 4578 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 4 d | Fixed Duration | 4 | 4d | 529 | 4 November 2025 8:00 AM | 7 November 2025 5:00 PM | Tue 4/11/25 | Fri 7/11/25 | Tue 13/10/26 | Fri 16/10/26 | 0d | 233d | 0ed | 0 | NA | NA | 26 September 2025 8:00 AM | 1 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
532 | 4579 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 531 | 10 November 2025 8:00 AM | 12 November 2025 5:00 PM | Mon 10/11/25 | Wed 12/11/25 | Mon 19/10/26 | Wed 21/10/26 | 0d | 233d | 0ed | 0 | NA | NA | 2 October 2025 8:00 AM | 7 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
533 | 4580 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 532 | 13 November 2025 8:00 AM | 17 November 2025 5:00 PM | Thu 13/11/25 | Mon 17/11/25 | Thu 22/10/26 | Mon 26/10/26 | 0d | 233d | 0ed | 0 | NA | NA | 8 October 2025 8:00 AM | 10 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
534 | 4581 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 533 | 18 November 2025 8:00 AM | 24 November 2025 5:00 PM | Tue 18/11/25 | Mon 24/11/25 | Tue 27/10/26 | Mon 2/11/26 | 0d | 233d | 0ed | 0 | NA | NA | 13 October 2025 8:00 AM | 17 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
535 | 4582 | Yes | Auto Scheduled | Service Fit Off | 2 d | Fixed Duration | 4 | 2d | 534 | 25 November 2025 8:00 AM | 26 November 2025 5:00 PM | Tue 25/11/25 | Wed 26/11/25 | Tue 3/11/26 | Wed 4/11/26 | 0d | 233d | 0ed | 0 | NA | NA | 20 October 2025 8:00 AM | 21 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
536 | 4583 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 535 | 27 November 2025 8:00 AM | 1 December 2025 5:00 PM | Thu 27/11/25 | Mon 1/12/25 | Thu 5/11/26 | Mon 9/11/26 | 233d | 233d | 0ed | 0 | NA | NA | 22 October 2025 8:00 AM | 24 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.3.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
537 | 4584 | Yes | Auto Scheduled | LEVEL 3 - BUILDING A | 58 d | Fixed Duration | 3 | 58d |  | 5 November 2025 8:00 AM | 3 February 2026 5:00 PM | Wed 5/11/25 | Tue 3/02/26 | Wed 19/08/26 | Mon 9/11/26 | 194d | 194d | 0ed | 0 | NA | NA | 29 September 2025 8:00 AM | 18 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
538 | 4585 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 345,382FS-10d | 5 November 2025 8:00 AM | 11 November 2025 5:00 PM | Wed 5/11/25 | Tue 11/11/25 | Wed 19/08/26 | Tue 25/08/26 | 0d | 194d | 0ed | 0 | NA | NA | 29 September 2025 8:00 AM | 3 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
539 | 4586 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 538 | 12 November 2025 8:00 AM | 14 November 2025 5:00 PM | Wed 12/11/25 | Fri 14/11/25 | Wed 26/08/26 | Fri 28/08/26 | 0d | 194d | 0ed | 0 | NA | NA | 7 October 2025 8:00 AM | 9 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
540 | 4587 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 539 | 17 November 2025 8:00 AM | 18 November 2025 5:00 PM | Mon 17/11/25 | Tue 18/11/25 | Mon 31/08/26 | Tue 1/09/26 | 0d | 194d | 0ed | 0 | NA | NA | 10 October 2025 8:00 AM | 13 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
541 | 4588 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 540 | 19 November 2025 8:00 AM | 25 November 2025 5:00 PM | Wed 19/11/25 | Tue 25/11/25 | Wed 2/09/26 | Tue 8/09/26 | 0d | 194d | 0ed | 0 | NA | NA | 14 October 2025 8:00 AM | 20 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
542 | 4589 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 541 | 26 November 2025 8:00 AM | 28 November 2025 5:00 PM | Wed 26/11/25 | Fri 28/11/25 | Wed 9/09/26 | Fri 11/09/26 | 0d | 194d | 0ed | 0 | NA | NA | 21 October 2025 8:00 AM | 23 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
543 | 4590 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 542 | 1 December 2025 8:00 AM | 3 December 2025 5:00 PM | Mon 1/12/25 | Wed 3/12/25 | Mon 14/09/26 | Wed 16/09/26 | 0d | 194d | 0ed | 0 | NA | NA | 24 October 2025 8:00 AM | 28 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
544 | 4591 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 543 | 4 December 2025 8:00 AM | 10 December 2025 5:00 PM | Thu 4/12/25 | Wed 10/12/25 | Thu 17/09/26 | Wed 23/09/26 | 0d | 194d | 0ed | 0 | NA | NA | 29 October 2025 8:00 AM | 4 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
545 | 4592 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 544 | 11 December 2025 8:00 AM | 24 December 2025 5:00 PM | Thu 11/12/25 | Wed 24/12/25 | Thu 24/09/26 | Thu 8/10/26 | 0d | 194d | 0ed | 0 | NA | NA | 5 November 2025 8:00 AM | 18 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
546 | 4593 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 545 | 2 January 2026 8:00 AM | 7 January 2026 5:00 PM | Fri 2/01/26 | Wed 7/01/26 | Wed 4/11/26 | Mon 9/11/26 | 212d | 212d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 24 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
547 | 4594 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 545 | 2 January 2026 8:00 AM | 8 January 2026 5:00 PM | Fri 2/01/26 | Thu 8/01/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 194d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 25 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
548 | 4595 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 547 | 9 January 2026 8:00 AM | 13 January 2026 5:00 PM | Fri 9/01/26 | Tue 13/01/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 194d | 0ed | 0 | NA | NA | 26 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
549 | 4596 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 548 | 14 January 2026 8:00 AM | 16 January 2026 5:00 PM | Wed 14/01/26 | Fri 16/01/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 194d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
550 | 4597 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 549 | 19 January 2026 8:00 AM | 23 January 2026 5:00 PM | Mon 19/01/26 | Fri 23/01/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 194d | 0ed | 0 | NA | NA | 4 December 2025 8:00 AM | 10 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
551 | 4598 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 550 | 27 January 2026 8:00 AM | 29 January 2026 5:00 PM | Tue 27/01/26 | Thu 29/01/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 194d | 0ed | 0 | NA | NA | 11 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
552 | 4599 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 551 | 30 January 2026 8:00 AM | 3 February 2026 5:00 PM | Fri 30/01/26 | Tue 3/02/26 | Thu 5/11/26 | Mon 9/11/26 | 194d | 194d | 0ed | 0 | NA | NA | 16 December 2025 8:00 AM | 18 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.4.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
553 | 4600 | Yes | Auto Scheduled | LEVEL 3 - BUILDING B | 58 d | Fixed Duration | 3 | 58d |  | 12 November 2025 8:00 AM | 10 February 2026 5:00 PM | Wed 12/11/25 | Tue 10/02/26 | Wed 19/08/26 | Mon 9/11/26 | 189d | 189d | 0ed | 0 | NA | NA | 7 October 2025 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
554 | 4601 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 346,384FS-10d | 12 November 2025 8:00 AM | 18 November 2025 5:00 PM | Wed 12/11/25 | Tue 18/11/25 | Wed 19/08/26 | Tue 25/08/26 | 0d | 189d | 0ed | 0 | NA | NA | 7 October 2025 8:00 AM | 13 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
555 | 4602 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 554 | 19 November 2025 8:00 AM | 21 November 2025 5:00 PM | Wed 19/11/25 | Fri 21/11/25 | Wed 26/08/26 | Fri 28/08/26 | 0d | 189d | 0ed | 0 | NA | NA | 14 October 2025 8:00 AM | 16 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
556 | 4603 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 555 | 24 November 2025 8:00 AM | 25 November 2025 5:00 PM | Mon 24/11/25 | Tue 25/11/25 | Mon 31/08/26 | Tue 1/09/26 | 0d | 189d | 0ed | 0 | NA | NA | 17 October 2025 8:00 AM | 20 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
557 | 4604 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 556 | 26 November 2025 8:00 AM | 2 December 2025 5:00 PM | Wed 26/11/25 | Tue 2/12/25 | Wed 2/09/26 | Tue 8/09/26 | 0d | 189d | 0ed | 0 | NA | NA | 21 October 2025 8:00 AM | 27 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
558 | 4605 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 557 | 3 December 2025 8:00 AM | 5 December 2025 5:00 PM | Wed 3/12/25 | Fri 5/12/25 | Wed 9/09/26 | Fri 11/09/26 | 0d | 189d | 0ed | 0 | NA | NA | 28 October 2025 8:00 AM | 30 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
559 | 4606 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 558 | 8 December 2025 8:00 AM | 10 December 2025 5:00 PM | Mon 8/12/25 | Wed 10/12/25 | Mon 14/09/26 | Wed 16/09/26 | 0d | 189d | 0ed | 0 | NA | NA | 31 October 2025 8:00 AM | 4 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
560 | 4607 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 559 | 11 December 2025 8:00 AM | 17 December 2025 5:00 PM | Thu 11/12/25 | Wed 17/12/25 | Thu 17/09/26 | Wed 23/09/26 | 0d | 189d | 0ed | 0 | NA | NA | 5 November 2025 8:00 AM | 11 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
561 | 4608 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 560 | 18 December 2025 8:00 AM | 8 January 2026 5:00 PM | Thu 18/12/25 | Thu 8/01/26 | Thu 24/09/26 | Thu 8/10/26 | 0d | 189d | 0ed | 0 | NA | NA | 12 November 2025 8:00 AM | 25 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
562 | 4609 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 561 | 9 January 2026 8:00 AM | 14 January 2026 5:00 PM | Fri 9/01/26 | Wed 14/01/26 | Wed 4/11/26 | Mon 9/11/26 | 207d | 207d | 0ed | 0 | NA | NA | 26 November 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
563 | 4610 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 561 | 9 January 2026 8:00 AM | 15 January 2026 5:00 PM | Fri 9/01/26 | Thu 15/01/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 189d | 0ed | 0 | NA | NA | 26 November 2025 8:00 AM | 2 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
564 | 4611 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 563 | 16 January 2026 8:00 AM | 20 January 2026 5:00 PM | Fri 16/01/26 | Tue 20/01/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 189d | 0ed | 0 | NA | NA | 3 December 2025 8:00 AM | 5 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
565 | 4612 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 564 | 21 January 2026 8:00 AM | 23 January 2026 5:00 PM | Wed 21/01/26 | Fri 23/01/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 189d | 0ed | 0 | NA | NA | 8 December 2025 8:00 AM | 10 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
566 | 4613 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 565 | 27 January 2026 8:00 AM | 2 February 2026 5:00 PM | Tue 27/01/26 | Mon 2/02/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 189d | 0ed | 0 | NA | NA | 11 December 2025 8:00 AM | 17 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
567 | 4614 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 566 | 3 February 2026 8:00 AM | 5 February 2026 5:00 PM | Tue 3/02/26 | Thu 5/02/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 189d | 0ed | 0 | NA | NA | 18 December 2025 8:00 AM | 22 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
568 | 4615 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 567 | 6 February 2026 8:00 AM | 10 February 2026 5:00 PM | Fri 6/02/26 | Tue 10/02/26 | Thu 5/11/26 | Mon 9/11/26 | 189d | 189d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.5.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
569 | 4616 | Yes | Auto Scheduled | LEVEL 3 - BUILDING C | 52 d | Fixed Duration | 3 | 52d |  | 21 November 2025 8:00 AM | 11 February 2026 5:00 PM | Fri 21/11/25 | Wed 11/02/26 | Thu 27/08/26 | Mon 9/11/26 | 188d | 188d | 0ed | 0 | NA | NA | 16 October 2025 8:00 AM | 5 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
570 | 4617 | Yes | Auto Scheduled | Service Rough-In | 4 d | Fixed Duration | 4 | 4d | 347,386FS-8d | 21 November 2025 8:00 AM | 26 November 2025 5:00 PM | Fri 21/11/25 | Wed 26/11/25 | Thu 27/08/26 | Tue 1/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 16 October 2025 8:00 AM | 21 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
571 | 4618 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 2 d | Fixed Duration | 4 | 2d | 570 | 27 November 2025 8:00 AM | 28 November 2025 5:00 PM | Thu 27/11/25 | Fri 28/11/25 | Wed 2/09/26 | Thu 3/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 22 October 2025 8:00 AM | 23 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
572 | 4619 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 571 | 1 December 2025 8:00 AM | 2 December 2025 5:00 PM | Mon 1/12/25 | Tue 2/12/25 | Fri 4/09/26 | Mon 7/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 24 October 2025 8:00 AM | 27 October 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
573 | 4620 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 572 | 3 December 2025 8:00 AM | 9 December 2025 5:00 PM | Wed 3/12/25 | Tue 9/12/25 | Tue 8/09/26 | Mon 14/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 28 October 2025 8:00 AM | 3 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
574 | 4621 | Yes | Auto Scheduled | Wet Area Screeds | 2 d | Fixed Duration | 4 | 2d | 573 | 10 December 2025 8:00 AM | 11 December 2025 5:00 PM | Wed 10/12/25 | Thu 11/12/25 | Tue 15/09/26 | Wed 16/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 4 November 2025 8:00 AM | 5 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
575 | 4622 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 574 | 12 December 2025 8:00 AM | 16 December 2025 5:00 PM | Fri 12/12/25 | Tue 16/12/25 | Thu 17/09/26 | Mon 21/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 6 November 2025 8:00 AM | 10 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
576 | 4623 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 4 d | Fixed Duration | 4 | 4d | 575 | 17 December 2025 8:00 AM | 22 December 2025 5:00 PM | Wed 17/12/25 | Mon 22/12/25 | Tue 22/09/26 | Fri 25/09/26 | 0d | 188d | 0ed | 0 | NA | NA | 11 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
577 | 4624 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 576 | 23 December 2025 8:00 AM | 13 January 2026 5:00 PM | Tue 23/12/25 | Tue 13/01/26 | Mon 28/09/26 | Mon 12/10/26 | 0d | 188d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
578 | 4625 | Yes | Auto Scheduled | Balcony Floor Tiles | 3 d | Fixed Duration | 4 | 3d | 577 | 14 January 2026 8:00 AM | 16 January 2026 5:00 PM | Wed 14/01/26 | Fri 16/01/26 | Thu 5/11/26 | Mon 9/11/26 | 205d | 205d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
579 | 4626 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 4 d | Fixed Duration | 4 | 4d | 577 | 14 January 2026 8:00 AM | 19 January 2026 5:00 PM | Wed 14/01/26 | Mon 19/01/26 | Tue 13/10/26 | Fri 16/10/26 | 0d | 188d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 4 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
580 | 4627 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 579 | 20 January 2026 8:00 AM | 22 January 2026 5:00 PM | Tue 20/01/26 | Thu 22/01/26 | Mon 19/10/26 | Wed 21/10/26 | 0d | 188d | 0ed | 0 | NA | NA | 5 December 2025 8:00 AM | 9 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
581 | 4628 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 580 | 23 January 2026 8:00 AM | 28 January 2026 5:00 PM | Fri 23/01/26 | Wed 28/01/26 | Thu 22/10/26 | Mon 26/10/26 | 0d | 188d | 0ed | 0 | NA | NA | 10 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
582 | 4629 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 581 | 29 January 2026 8:00 AM | 4 February 2026 5:00 PM | Thu 29/01/26 | Wed 4/02/26 | Tue 27/10/26 | Mon 2/11/26 | 0d | 188d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
583 | 4630 | Yes | Auto Scheduled | Service Fit Off | 2 d | Fixed Duration | 4 | 2d | 582 | 5 February 2026 8:00 AM | 6 February 2026 5:00 PM | Thu 5/02/26 | Fri 6/02/26 | Tue 3/11/26 | Wed 4/11/26 | 0d | 188d | 0ed | 0 | NA | NA | 22 December 2025 8:00 AM | 23 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
584 | 4631 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 583 | 9 February 2026 8:00 AM | 11 February 2026 5:00 PM | Mon 9/02/26 | Wed 11/02/26 | Thu 5/11/26 | Mon 9/11/26 | 188d | 188d | 0ed | 0 | NA | NA | 24 December 2025 8:00 AM | 5 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.6.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
585 | 4632 | Yes | Auto Scheduled | LEVEL 4 - BUILDING A | 58 d | Fixed Duration | 3 | 58d |  | 9 December 2025 8:00 AM | 9 March 2026 5:00 PM | Tue 9/12/25 | Mon 9/03/26 | Wed 12/08/26 | Mon 9/11/26 | 165d | 165d | 0ed | 0 | NA | NA | 3 November 2025 8:00 AM | 30 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
586 | 4633 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 350,389FS-10d | 9 December 2025 8:00 AM | 15 December 2025 5:00 PM | Tue 9/12/25 | Mon 15/12/25 | Wed 12/08/26 | Tue 18/08/26 | 0d | 165d | 0ed | 0 | NA | NA | 3 November 2025 8:00 AM | 7 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
587 | 4634 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 586 | 16 December 2025 8:00 AM | 18 December 2025 5:00 PM | Tue 16/12/25 | Thu 18/12/25 | Wed 26/08/26 | Fri 28/08/26 | 0d | 170d | 0ed | 0 | NA | NA | 10 November 2025 8:00 AM | 12 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
588 | 4635 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 587 | 19 December 2025 8:00 AM | 22 December 2025 5:00 PM | Fri 19/12/25 | Mon 22/12/25 | Mon 31/08/26 | Tue 1/09/26 | 0d | 170d | 0ed | 0 | NA | NA | 13 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
589 | 4636 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 588 | 23 December 2025 8:00 AM | 6 January 2026 5:00 PM | Tue 23/12/25 | Tue 6/01/26 | Wed 2/09/26 | Tue 8/09/26 | 0d | 170d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 21 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
590 | 4637 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 589 | 7 January 2026 8:00 AM | 9 January 2026 5:00 PM | Wed 7/01/26 | Fri 9/01/26 | Wed 9/09/26 | Fri 11/09/26 | 0d | 170d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 26 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
591 | 4638 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 590 | 12 January 2026 8:00 AM | 14 January 2026 5:00 PM | Mon 12/01/26 | Wed 14/01/26 | Mon 14/09/26 | Wed 16/09/26 | 0d | 170d | 0ed | 0 | NA | NA | 27 November 2025 8:00 AM | 1 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
592 | 4639 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 591 | 15 January 2026 8:00 AM | 21 January 2026 5:00 PM | Thu 15/01/26 | Wed 21/01/26 | Thu 17/09/26 | Wed 23/09/26 | 0d | 170d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 8 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
593 | 4640 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 592 | 22 January 2026 8:00 AM | 5 February 2026 5:00 PM | Thu 22/01/26 | Thu 5/02/26 | Thu 24/09/26 | Thu 8/10/26 | 0d | 170d | 0ed | 0 | NA | NA | 9 December 2025 8:00 AM | 22 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
594 | 4641 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 593 | 6 February 2026 8:00 AM | 11 February 2026 5:00 PM | Fri 6/02/26 | Wed 11/02/26 | Wed 4/11/26 | Mon 9/11/26 | 188d | 188d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 5 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
595 | 4642 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 593 | 6 February 2026 8:00 AM | 12 February 2026 5:00 PM | Fri 6/02/26 | Thu 12/02/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 170d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
596 | 4643 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 595 | 13 February 2026 8:00 AM | 17 February 2026 5:00 PM | Fri 13/02/26 | Tue 17/02/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 170d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 9 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
597 | 4644 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 596 | 18 February 2026 8:00 AM | 20 February 2026 5:00 PM | Wed 18/02/26 | Fri 20/02/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 170d | 0ed | 0 | NA | NA | 12 January 2026 8:00 AM | 14 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
598 | 4645 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 597 | 23 February 2026 8:00 AM | 27 February 2026 5:00 PM | Mon 23/02/26 | Fri 27/02/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 170d | 0ed | 0 | NA | NA | 15 January 2026 8:00 AM | 21 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
599 | 4646 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 598 | 2 March 2026 8:00 AM | 4 March 2026 5:00 PM | Mon 2/03/26 | Wed 4/03/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 170d | 0ed | 0 | NA | NA | 22 January 2026 8:00 AM | 27 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
600 | 4647 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 599 | 5 March 2026 8:00 AM | 9 March 2026 5:00 PM | Thu 5/03/26 | Mon 9/03/26 | Thu 5/11/26 | Mon 9/11/26 | 170d | 170d | 0ed | 0 | NA | NA | 28 January 2026 8:00 AM | 30 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.7.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
601 | 4648 | Yes | Auto Scheduled | LEVEL 4 - BUILDING B | 58 d | Fixed Duration | 3 | 58d |  | 16 December 2025 8:00 AM | 16 March 2026 5:00 PM | Tue 16/12/25 | Mon 16/03/26 | Wed 12/08/26 | Mon 9/11/26 | 160d | 160d | 0ed | 0 | NA | NA | 10 November 2025 8:00 AM | 6 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
602 | 4649 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 351,391FS-10d | 16 December 2025 8:00 AM | 22 December 2025 5:00 PM | Tue 16/12/25 | Mon 22/12/25 | Wed 12/08/26 | Tue 18/08/26 | 0d | 160d | 0ed | 0 | NA | NA | 10 November 2025 8:00 AM | 14 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
603 | 4650 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 602 | 23 December 2025 8:00 AM | 2 January 2026 5:00 PM | Tue 23/12/25 | Fri 2/01/26 | Wed 26/08/26 | Fri 28/08/26 | 0d | 165d | 0ed | 0 | NA | NA | 17 November 2025 8:00 AM | 19 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
604 | 4651 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 603 | 5 January 2026 8:00 AM | 6 January 2026 5:00 PM | Mon 5/01/26 | Tue 6/01/26 | Mon 31/08/26 | Tue 1/09/26 | 0d | 165d | 0ed | 0 | NA | NA | 20 November 2025 8:00 AM | 21 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
605 | 4652 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 604 | 7 January 2026 8:00 AM | 13 January 2026 5:00 PM | Wed 7/01/26 | Tue 13/01/26 | Wed 2/09/26 | Tue 8/09/26 | 0d | 165d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
606 | 4653 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 605 | 14 January 2026 8:00 AM | 16 January 2026 5:00 PM | Wed 14/01/26 | Fri 16/01/26 | Wed 9/09/26 | Fri 11/09/26 | 0d | 165d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
607 | 4654 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 606 | 19 January 2026 8:00 AM | 21 January 2026 5:00 PM | Mon 19/01/26 | Wed 21/01/26 | Mon 14/09/26 | Wed 16/09/26 | 0d | 165d | 0ed | 0 | NA | NA | 4 December 2025 8:00 AM | 8 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
608 | 4655 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 607 | 22 January 2026 8:00 AM | 29 January 2026 5:00 PM | Thu 22/01/26 | Thu 29/01/26 | Thu 17/09/26 | Wed 23/09/26 | 0d | 165d | 0ed | 0 | NA | NA | 9 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
609 | 4656 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 608 | 30 January 2026 8:00 AM | 12 February 2026 5:00 PM | Fri 30/01/26 | Thu 12/02/26 | Thu 24/09/26 | Thu 8/10/26 | 0d | 165d | 0ed | 0 | NA | NA | 16 December 2025 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
610 | 4657 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 609 | 13 February 2026 8:00 AM | 18 February 2026 5:00 PM | Fri 13/02/26 | Wed 18/02/26 | Wed 4/11/26 | Mon 9/11/26 | 183d | 183d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
611 | 4658 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 609 | 13 February 2026 8:00 AM | 19 February 2026 5:00 PM | Fri 13/02/26 | Thu 19/02/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 165d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 13 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
612 | 4659 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 611 | 20 February 2026 8:00 AM | 24 February 2026 5:00 PM | Fri 20/02/26 | Tue 24/02/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 165d | 0ed | 0 | NA | NA | 14 January 2026 8:00 AM | 16 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
613 | 4660 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 612 | 25 February 2026 8:00 AM | 27 February 2026 5:00 PM | Wed 25/02/26 | Fri 27/02/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 165d | 0ed | 0 | NA | NA | 19 January 2026 8:00 AM | 21 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
614 | 4661 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 613 | 2 March 2026 8:00 AM | 6 March 2026 5:00 PM | Mon 2/03/26 | Fri 6/03/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 165d | 0ed | 0 | NA | NA | 22 January 2026 8:00 AM | 29 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
615 | 4662 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 614 | 9 March 2026 8:00 AM | 11 March 2026 5:00 PM | Mon 9/03/26 | Wed 11/03/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 165d | 0ed | 0 | NA | NA | 30 January 2026 8:00 AM | 3 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
616 | 4663 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 615 | 12 March 2026 8:00 AM | 16 March 2026 5:00 PM | Thu 12/03/26 | Mon 16/03/26 | Thu 5/11/26 | Mon 9/11/26 | 165d | 165d | 0ed | 0 | NA | NA | 4 February 2026 8:00 AM | 6 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.8.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
617 | 4664 | Yes | Auto Scheduled | LEVEL 4 - BUILDING C | 52 d | Fixed Duration | 3 | 52d |  | 2 January 2026 8:00 AM | 17 March 2026 5:00 PM | Fri 2/01/26 | Tue 17/03/26 | Fri 21/08/26 | Mon 9/11/26 | 160d | 160d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 9 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
618 | 4665 | Yes | Auto Scheduled | Service Rough-In | 4 d | Fixed Duration | 4 | 4d | 352,393FS-8d | 2 January 2026 8:00 AM | 7 January 2026 5:00 PM | Fri 2/01/26 | Wed 7/01/26 | Fri 21/08/26 | Wed 26/08/26 | 0d | 160d | 0ed | 0 | NA | NA | 19 November 2025 8:00 AM | 24 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
619 | 4666 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 2 d | Fixed Duration | 4 | 2d | 618 | 8 January 2026 8:00 AM | 9 January 2026 5:00 PM | Thu 8/01/26 | Fri 9/01/26 | Wed 2/09/26 | Thu 3/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 25 November 2025 8:00 AM | 26 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
620 | 4667 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 619 | 12 January 2026 8:00 AM | 13 January 2026 5:00 PM | Mon 12/01/26 | Tue 13/01/26 | Fri 4/09/26 | Mon 7/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 27 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
621 | 4668 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 620 | 14 January 2026 8:00 AM | 20 January 2026 5:00 PM | Wed 14/01/26 | Tue 20/01/26 | Tue 8/09/26 | Mon 14/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 5 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
622 | 4669 | Yes | Auto Scheduled | Wet Area Screeds | 2 d | Fixed Duration | 4 | 2d | 621 | 21 January 2026 8:00 AM | 22 January 2026 5:00 PM | Wed 21/01/26 | Thu 22/01/26 | Tue 15/09/26 | Wed 16/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 8 December 2025 8:00 AM | 9 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
623 | 4670 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 622 | 23 January 2026 8:00 AM | 28 January 2026 5:00 PM | Fri 23/01/26 | Wed 28/01/26 | Thu 17/09/26 | Mon 21/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 10 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
624 | 4671 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 4 d | Fixed Duration | 4 | 4d | 623 | 29 January 2026 8:00 AM | 3 February 2026 5:00 PM | Thu 29/01/26 | Tue 3/02/26 | Tue 22/09/26 | Fri 25/09/26 | 0d | 164d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 18 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
625 | 4672 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 624 | 4 February 2026 8:00 AM | 17 February 2026 5:00 PM | Wed 4/02/26 | Tue 17/02/26 | Mon 28/09/26 | Mon 12/10/26 | 0d | 164d | 0ed | 0 | NA | NA | 19 December 2025 8:00 AM | 9 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
626 | 4673 | Yes | Auto Scheduled | Balcony Floor Tiles | 3 d | Fixed Duration | 4 | 3d | 625 | 18 February 2026 8:00 AM | 20 February 2026 5:00 PM | Wed 18/02/26 | Fri 20/02/26 | Thu 5/11/26 | Mon 9/11/26 | 181d | 181d | 0ed | 0 | NA | NA | 12 January 2026 8:00 AM | 14 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
627 | 4674 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 4 d | Fixed Duration | 4 | 4d | 625 | 18 February 2026 8:00 AM | 23 February 2026 5:00 PM | Wed 18/02/26 | Mon 23/02/26 | Tue 13/10/26 | Fri 16/10/26 | 0d | 164d | 0ed | 0 | NA | NA | 12 January 2026 8:00 AM | 15 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
628 | 4675 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 627 | 24 February 2026 8:00 AM | 26 February 2026 5:00 PM | Tue 24/02/26 | Thu 26/02/26 | Mon 19/10/26 | Wed 21/10/26 | 0d | 164d | 0ed | 0 | NA | NA | 16 January 2026 8:00 AM | 20 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
629 | 4676 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 628 | 27 February 2026 8:00 AM | 3 March 2026 5:00 PM | Fri 27/02/26 | Tue 3/03/26 | Thu 22/10/26 | Mon 26/10/26 | 0d | 164d | 0ed | 0 | NA | NA | 21 January 2026 8:00 AM | 23 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
630 | 4677 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 629 | 4 March 2026 8:00 AM | 10 March 2026 5:00 PM | Wed 4/03/26 | Tue 10/03/26 | Tue 27/10/26 | Mon 2/11/26 | 0d | 164d | 0ed | 0 | NA | NA | 27 January 2026 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
631 | 4678 | Yes | Auto Scheduled | Service Fit Off | 2 d | Fixed Duration | 4 | 2d | 630 | 11 March 2026 8:00 AM | 12 March 2026 5:00 PM | Wed 11/03/26 | Thu 12/03/26 | Tue 3/11/26 | Wed 4/11/26 | 0d | 164d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 4 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
632 | 4679 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 631 | 13 March 2026 8:00 AM | 17 March 2026 5:00 PM | Fri 13/03/26 | Tue 17/03/26 | Thu 5/11/26 | Mon 9/11/26 | 164d | 164d | 0ed | 0 | NA | NA | 5 February 2026 8:00 AM | 9 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.9.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
633 | 4680 | Yes | Auto Scheduled | LEVEL 5 - BUILDING A | 58 d | Fixed Duration | 3 | 58d |  | 7 January 2026 8:00 AM | 30 March 2026 5:00 PM | Wed 7/01/26 | Mon 30/03/26 | Wed 19/08/26 | Mon 9/11/26 | 155d | 155d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 20 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
634 | 4681 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 355,586,396FS-10d | 7 January 2026 8:00 AM | 13 January 2026 5:00 PM | Wed 7/01/26 | Tue 13/01/26 | Wed 19/08/26 | Tue 25/08/26 | 0d | 155d | 0ed | 0 | NA | NA | 24 November 2025 8:00 AM | 28 November 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
635 | 4682 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 634 | 14 January 2026 8:00 AM | 16 January 2026 5:00 PM | Wed 14/01/26 | Fri 16/01/26 | Wed 26/08/26 | Fri 28/08/26 | 0d | 155d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
636 | 4683 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 635 | 19 January 2026 8:00 AM | 20 January 2026 5:00 PM | Mon 19/01/26 | Tue 20/01/26 | Mon 31/08/26 | Tue 1/09/26 | 0d | 155d | 0ed | 0 | NA | NA | 4 December 2025 8:00 AM | 5 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
637 | 4684 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 636 | 21 January 2026 8:00 AM | 28 January 2026 5:00 PM | Wed 21/01/26 | Wed 28/01/26 | Wed 2/09/26 | Tue 8/09/26 | 0d | 155d | 0ed | 0 | NA | NA | 8 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
638 | 4685 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 637 | 29 January 2026 8:00 AM | 2 February 2026 5:00 PM | Thu 29/01/26 | Mon 2/02/26 | Wed 9/09/26 | Fri 11/09/26 | 0d | 155d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 17 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
639 | 4686 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 638 | 3 February 2026 8:00 AM | 5 February 2026 5:00 PM | Tue 3/02/26 | Thu 5/02/26 | Mon 14/09/26 | Wed 16/09/26 | 0d | 155d | 0ed | 0 | NA | NA | 18 December 2025 8:00 AM | 22 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
640 | 4687 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 639 | 6 February 2026 8:00 AM | 12 February 2026 5:00 PM | Fri 6/02/26 | Thu 12/02/26 | Thu 17/09/26 | Wed 23/09/26 | 0d | 155d | 0ed | 0 | NA | NA | 23 December 2025 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
641 | 4688 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 640 | 13 February 2026 8:00 AM | 26 February 2026 5:00 PM | Fri 13/02/26 | Thu 26/02/26 | Thu 24/09/26 | Thu 8/10/26 | 0d | 155d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 20 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
642 | 4689 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 641 | 27 February 2026 8:00 AM | 4 March 2026 5:00 PM | Fri 27/02/26 | Wed 4/03/26 | Wed 4/11/26 | Mon 9/11/26 | 173d | 173d | 0ed | 0 | NA | NA | 21 January 2026 8:00 AM | 27 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
643 | 4690 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 641 | 27 February 2026 8:00 AM | 5 March 2026 5:00 PM | Fri 27/02/26 | Thu 5/03/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 155d | 0ed | 0 | NA | NA | 21 January 2026 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
644 | 4691 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 643 | 6 March 2026 8:00 AM | 10 March 2026 5:00 PM | Fri 6/03/26 | Tue 10/03/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 155d | 0ed | 0 | NA | NA | 29 January 2026 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
645 | 4692 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 644 | 11 March 2026 8:00 AM | 13 March 2026 5:00 PM | Wed 11/03/26 | Fri 13/03/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 155d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 5 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
646 | 4693 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 645 | 16 March 2026 8:00 AM | 20 March 2026 5:00 PM | Mon 16/03/26 | Fri 20/03/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 155d | 0ed | 0 | NA | NA | 6 February 2026 8:00 AM | 12 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
647 | 4694 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 646 | 23 March 2026 8:00 AM | 25 March 2026 5:00 PM | Mon 23/03/26 | Wed 25/03/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 155d | 0ed | 0 | NA | NA | 13 February 2026 8:00 AM | 17 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
648 | 4695 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 647 | 26 March 2026 8:00 AM | 30 March 2026 5:00 PM | Thu 26/03/26 | Mon 30/03/26 | Thu 5/11/26 | Mon 9/11/26 | 155d | 155d | 0ed | 0 | NA | NA | 18 February 2026 8:00 AM | 20 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.10.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
649 | 4696 | Yes | Auto Scheduled | LEVEL 5 - BUILDING B | 58 d | Fixed Duration | 3 | 58d |  | 14 January 2026 8:00 AM | 8 April 2026 5:00 PM | Wed 14/01/26 | Wed 8/04/26 | Wed 19/08/26 | Mon 9/11/26 | 150d | 150d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 27 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
650 | 4697 | Yes | Auto Scheduled | Service Rough-In | 5 d | Fixed Duration | 4 | 5d | 356,602,398FS-10d | 14 January 2026 8:00 AM | 20 January 2026 5:00 PM | Wed 14/01/26 | Tue 20/01/26 | Wed 19/08/26 | Tue 25/08/26 | 0d | 150d | 0ed | 0 | NA | NA | 1 December 2025 8:00 AM | 5 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
651 | 4698 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 3 d | Fixed Duration | 4 | 3d | 650 | 21 January 2026 8:00 AM | 23 January 2026 5:00 PM | Wed 21/01/26 | Fri 23/01/26 | Wed 26/08/26 | Fri 28/08/26 | 0d | 150d | 0ed | 0 | NA | NA | 8 December 2025 8:00 AM | 10 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
652 | 4699 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 651 | 27 January 2026 8:00 AM | 28 January 2026 5:00 PM | Tue 27/01/26 | Wed 28/01/26 | Mon 31/08/26 | Tue 1/09/26 | 0d | 150d | 0ed | 0 | NA | NA | 11 December 2025 8:00 AM | 12 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
653 | 4700 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 652 | 29 January 2026 8:00 AM | 4 February 2026 5:00 PM | Thu 29/01/26 | Wed 4/02/26 | Wed 2/09/26 | Tue 8/09/26 | 0d | 150d | 0ed | 0 | NA | NA | 15 December 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
654 | 4701 | Yes | Auto Scheduled | Wet Area Screeds | 3 d | Fixed Duration | 4 | 3d | 653 | 5 February 2026 8:00 AM | 9 February 2026 5:00 PM | Thu 5/02/26 | Mon 9/02/26 | Wed 9/09/26 | Fri 11/09/26 | 0d | 150d | 0ed | 0 | NA | NA | 22 December 2025 8:00 AM | 24 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
655 | 4702 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 654 | 10 February 2026 8:00 AM | 12 February 2026 5:00 PM | Tue 10/02/26 | Thu 12/02/26 | Mon 14/09/26 | Wed 16/09/26 | 0d | 150d | 0ed | 0 | NA | NA | 2 January 2026 8:00 AM | 6 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
656 | 4703 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 5 d | Fixed Duration | 4 | 5d | 655 | 13 February 2026 8:00 AM | 19 February 2026 5:00 PM | Fri 13/02/26 | Thu 19/02/26 | Thu 17/09/26 | Wed 23/09/26 | 0d | 150d | 0ed | 0 | NA | NA | 7 January 2026 8:00 AM | 13 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
657 | 4704 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 656 | 20 February 2026 8:00 AM | 5 March 2026 5:00 PM | Fri 20/02/26 | Thu 5/03/26 | Thu 24/09/26 | Thu 8/10/26 | 0d | 150d | 0ed | 0 | NA | NA | 14 January 2026 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
658 | 4705 | Yes | Auto Scheduled | Balcony Floor Tiles | 4 d | Fixed Duration | 4 | 4d | 657 | 6 March 2026 8:00 AM | 11 March 2026 5:00 PM | Fri 6/03/26 | Wed 11/03/26 | Wed 4/11/26 | Mon 9/11/26 | 168d | 168d | 0ed | 0 | NA | NA | 29 January 2026 8:00 AM | 3 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
659 | 4706 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 5 d | Fixed Duration | 4 | 5d | 657 | 6 March 2026 8:00 AM | 12 March 2026 5:00 PM | Fri 6/03/26 | Thu 12/03/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 150d | 0ed | 0 | NA | NA | 29 January 2026 8:00 AM | 4 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
660 | 4707 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 659 | 13 March 2026 8:00 AM | 17 March 2026 5:00 PM | Fri 13/03/26 | Tue 17/03/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 150d | 0ed | 0 | NA | NA | 5 February 2026 8:00 AM | 9 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
661 | 4708 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 660 | 18 March 2026 8:00 AM | 20 March 2026 5:00 PM | Wed 18/03/26 | Fri 20/03/26 | Wed 21/10/26 | Fri 23/10/26 | 0d | 150d | 0ed | 0 | NA | NA | 10 February 2026 8:00 AM | 12 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
662 | 4709 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 661 | 23 March 2026 8:00 AM | 27 March 2026 5:00 PM | Mon 23/03/26 | Fri 27/03/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 150d | 0ed | 0 | NA | NA | 13 February 2026 8:00 AM | 19 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
663 | 4710 | Yes | Auto Scheduled | Service Fit Off | 3 d | Fixed Duration | 4 | 3d | 662 | 30 March 2026 8:00 AM | 1 April 2026 5:00 PM | Mon 30/03/26 | Wed 1/04/26 | Mon 2/11/26 | Wed 4/11/26 | 0d | 150d | 0ed | 0 | NA | NA | 20 February 2026 8:00 AM | 24 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
664 | 4711 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 663 | 2 April 2026 8:00 AM | 8 April 2026 5:00 PM | Thu 2/04/26 | Wed 8/04/26 | Thu 5/11/26 | Mon 9/11/26 | 150d | 150d | 0ed | 0 | NA | NA | 25 February 2026 8:00 AM | 27 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.11.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
665 | 4712 | Yes | Auto Scheduled | LEVEL 5 - BUILDING C | 52 d | Fixed Duration | 3 | 52d |  | 23 January 2026 8:00 AM | 9 April 2026 5:00 PM | Fri 23/01/26 | Thu 9/04/26 | Thu 27/08/26 | Mon 9/11/26 | 149d | 149d | 0ed | 0 | NA | NA | 10 December 2025 8:00 AM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
666 | 4713 | Yes | Auto Scheduled | Service Rough-In | 4 d | Fixed Duration | 4 | 4d | 357,618,400FS-8d | 23 January 2026 8:00 AM | 29 January 2026 5:00 PM | Fri 23/01/26 | Thu 29/01/26 | Thu 27/08/26 | Tue 1/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 10 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
667 | 4714 | Yes | Auto Scheduled | Light Weight Wall & Ceiling Frames | 2 d | Fixed Duration | 4 | 2d | 666 | 30 January 2026 8:00 AM | 2 February 2026 5:00 PM | Fri 30/01/26 | Mon 2/02/26 | Wed 2/09/26 | Thu 3/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 16 December 2025 8:00 AM | 17 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
668 | 4715 | Yes | Auto Scheduled | In Wall Services | 2 d | Fixed Duration | 4 | 2d | 667 | 3 February 2026 8:00 AM | 4 February 2026 5:00 PM | Tue 3/02/26 | Wed 4/02/26 | Fri 4/09/26 | Mon 7/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 18 December 2025 8:00 AM | 19 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
669 | 4716 | Yes | Auto Scheduled | Wall & Ceiling Linings | 5 d | Fixed Duration | 4 | 5d | 668 | 5 February 2026 8:00 AM | 11 February 2026 5:00 PM | Thu 5/02/26 | Wed 11/02/26 | Tue 8/09/26 | Mon 14/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 22 December 2025 8:00 AM | 5 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
670 | 4717 | Yes | Auto Scheduled | Wet Area Screeds | 2 d | Fixed Duration | 4 | 2d | 669 | 12 February 2026 8:00 AM | 13 February 2026 5:00 PM | Thu 12/02/26 | Fri 13/02/26 | Tue 15/09/26 | Wed 16/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 6 January 2026 8:00 AM | 7 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
671 | 4718 | Yes | Auto Scheduled | Wet Area Waterproofing | 3 d | Fixed Duration | 4 | 3d | 670 | 16 February 2026 8:00 AM | 18 February 2026 5:00 PM | Mon 16/02/26 | Wed 18/02/26 | Thu 17/09/26 | Mon 21/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 8 January 2026 8:00 AM | 12 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
672 | 4719 | Yes | Auto Scheduled | Wet Area Floor & Wall Tiles | 4 d | Fixed Duration | 4 | 4d | 671 | 19 February 2026 8:00 AM | 24 February 2026 5:00 PM | Thu 19/02/26 | Tue 24/02/26 | Tue 22/09/26 | Fri 25/09/26 | 0d | 149d | 0ed | 0 | NA | NA | 13 January 2026 8:00 AM | 16 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
673 | 4720 | Yes | Auto Scheduled | Living/ Dining/ Kitchen Floor Tiles | 10 d | Fixed Duration | 4 | 10d | 672 | 25 February 2026 8:00 AM | 10 March 2026 5:00 PM | Wed 25/02/26 | Tue 10/03/26 | Mon 28/09/26 | Mon 12/10/26 | 0d | 149d | 0ed | 0 | NA | NA | 19 January 2026 8:00 AM | 2 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
674 | 4721 | Yes | Auto Scheduled | Balcony Floor Tiles | 3 d | Fixed Duration | 4 | 3d | 673 | 11 March 2026 8:00 AM | 13 March 2026 5:00 PM | Wed 11/03/26 | Fri 13/03/26 | Thu 5/11/26 | Mon 9/11/26 | 166d | 166d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 5 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
675 | 4722 | Yes | Auto Scheduled | Carpentry Fix Out - Skirts, Archs & Frames | 4 d | Fixed Duration | 4 | 4d | 673 | 11 March 2026 8:00 AM | 16 March 2026 5:00 PM | Wed 11/03/26 | Mon 16/03/26 | Tue 13/10/26 | Fri 16/10/26 | 0d | 149d | 0ed | 0 | NA | NA | 3 February 2026 8:00 AM | 6 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
676 | 4723 | Yes | Auto Scheduled | Doors & Door Hardware | 3 d | Fixed Duration | 4 | 3d | 675 | 17 March 2026 8:00 AM | 19 March 2026 5:00 PM | Tue 17/03/26 | Thu 19/03/26 | Mon 19/10/26 | Wed 21/10/26 | 0d | 149d | 0ed | 0 | NA | NA | 9 February 2026 8:00 AM | 11 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
677 | 4724 | Yes | Auto Scheduled | Initial Paint | 3 d | Fixed Duration | 4 | 3d | 676 | 20 March 2026 8:00 AM | 24 March 2026 5:00 PM | Fri 20/03/26 | Tue 24/03/26 | Thu 22/10/26 | Mon 26/10/26 | 0d | 149d | 0ed | 0 | NA | NA | 12 February 2026 8:00 AM | 16 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.12 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
678 | 4725 | Yes | Auto Scheduled | Joinery Installation | 5 d | Fixed Duration | 4 | 5d | 677 | 25 March 2026 8:00 AM | 31 March 2026 5:00 PM | Wed 25/03/26 | Tue 31/03/26 | Tue 27/10/26 | Mon 2/11/26 | 0d | 149d | 0ed | 0 | NA | NA | 17 February 2026 8:00 AM | 23 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.13 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
679 | 4726 | Yes | Auto Scheduled | Service Fit Off | 2 d | Fixed Duration | 4 | 2d | 678 | 1 April 2026 8:00 AM | 2 April 2026 5:00 PM | Wed 1/04/26 | Thu 2/04/26 | Tue 3/11/26 | Wed 4/11/26 | 0d | 149d | 0ed | 0 | NA | NA | 24 February 2026 8:00 AM | 25 February 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.14 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
680 | 4727 | Yes | Auto Scheduled | Final Paint | 3 d | Fixed Duration | 4 | 3d | 679 | 7 April 2026 8:00 AM | 9 April 2026 5:00 PM | Tue 7/04/26 | Thu 9/04/26 | Thu 5/11/26 | Mon 9/11/26 | 0d | 149d | 0ed | 0 | NA | NA | 26 February 2026 8:00 AM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 3/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.15 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
681 | 4736 | Yes | Auto Scheduled | Internal Finishes Complete | 0 d | Fixed Duration | 4 | 0d | 680 | 9 April 2026 5:00 PM | 9 April 2026 5:00 PM | Thu 9/04/26 | Thu 9/04/26 | Mon 9/11/26 | Mon 9/11/26 | 0d | 149d | 0ed | 0 | NA | NA | 2 March 2026 5:00 PM | 2 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.5.12.16 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
682 | 4738 | Yes | Auto Scheduled | EXTERNAL WORKS & STREETSCAPE | 106 d | Fixed Duration | 2 | 106d |  | 15 January 2026 8:00 AM | 18 June 2026 5:00 PM | Thu 15/01/26 | Thu 18/06/26 | Wed 22/04/26 | Mon 9/11/26 | 66d | 66d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 12 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
683 | 4739 | Yes | Auto Scheduled | STREET WIDENING - BEERWAH PDE, PHIPPS ST & FREE ST | 35 d | Fixed Duration | 3 | 35d |  | 15 January 2026 8:00 AM | 5 March 2026 5:00 PM | Thu 15/01/26 | Thu 5/03/26 | Mon 21/09/26 | Mon 9/11/26 | 172d | 172d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
684 | 4761 | Yes | Auto Scheduled | Removal of Street Trees | 2 d | Fixed Duration | 4 | 2d | 337 | 15 January 2026 8:00 AM | 16 January 2026 5:00 PM | Thu 15/01/26 | Fri 16/01/26 | Mon 21/09/26 | Tue 22/09/26 | 0d | 172d | 0ed | 0 | NA | NA | 2 December 2025 8:00 AM | 3 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
685 | 4762 | Yes | Auto Scheduled | Demolition of Exising Footpath & Crossovers | 3 d | Fixed Duration | 4 | 3d | 684 | 19 January 2026 8:00 AM | 21 January 2026 5:00 PM | Mon 19/01/26 | Wed 21/01/26 | Wed 23/09/26 | Fri 25/09/26 | 0d | 172d | 0ed | 0 | NA | NA | 4 December 2025 8:00 AM | 8 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
686 | 4763 | Yes | Auto Scheduled | Lay of Stormwater Pipes & Pits, incl. Connection to Existing | 5 d | Fixed Duration | 4 | 5d | 685 | 22 January 2026 8:00 AM | 29 January 2026 5:00 PM | Thu 22/01/26 | Thu 29/01/26 | Mon 28/09/26 | Fri 2/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 9 December 2025 8:00 AM | 15 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
687 | 4764 | Yes | Auto Scheduled | Subgrade Preparation | 3 d | Fixed Duration | 4 | 3d | 686 | 30 January 2026 8:00 AM | 3 February 2026 5:00 PM | Fri 30/01/26 | Tue 3/02/26 | Tue 6/10/26 | Thu 8/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 16 December 2025 8:00 AM | 18 December 2025 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
688 | 4765 | Yes | Auto Scheduled | Kerb, Gutter & Crossover Construction | 5 d | Fixed Duration | 4 | 5d | 687 | 4 February 2026 8:00 AM | 10 February 2026 5:00 PM | Wed 4/02/26 | Tue 10/02/26 | Fri 9/10/26 | Thu 15/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 19 December 2025 8:00 AM | 2 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
689 | 4766 | Yes | Auto Scheduled | New Ashphalt/ Flexible Pavement to Road | 3 d | Fixed Duration | 4 | 3d | 688 | 11 February 2026 8:00 AM | 13 February 2026 5:00 PM | Wed 11/02/26 | Fri 13/02/26 | Fri 16/10/26 | Tue 20/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 5 January 2026 8:00 AM | 7 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
690 | 4767 | Yes | Auto Scheduled | Footpath & Crossover Construction (FRP) - Beerwah Pde | 4 d | Fixed Duration | 4 | 4d | 689 | 16 February 2026 8:00 AM | 19 February 2026 5:00 PM | Mon 16/02/26 | Thu 19/02/26 | Wed 21/10/26 | Mon 26/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 8 January 2026 8:00 AM | 13 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
691 | 4768 | Yes | Auto Scheduled | Footpath Construction (FRP) - Phipps St | 5 d | Fixed Duration | 4 | 5d | 690FS-1d | 19 February 2026 8:00 AM | 25 February 2026 5:00 PM | Thu 19/02/26 | Wed 25/02/26 | Mon 26/10/26 | Fri 30/10/26 | 0d | 172d | 0ed | 0 | NA | NA | 13 January 2026 8:00 AM | 19 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
692 | 4769 | Yes | Auto Scheduled | Footpath & Crossover Construction (FRP) - Free St | 4 d | Fixed Duration | 4 | 4d | 691FS-1d | 25 February 2026 8:00 AM | 2 March 2026 5:00 PM | Wed 25/02/26 | Mon 2/03/26 | Fri 30/10/26 | Wed 4/11/26 | 0d | 172d | 0ed | 0 | NA | NA | 19 January 2026 8:00 AM | 22 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
693 | 4770 | Yes | Auto Scheduled | Sign Posts | 1 d | Fixed Duration | 4 | 1d | 692 | 3 March 2026 8:00 AM | 3 March 2026 5:00 PM | Tue 3/03/26 | Tue 3/03/26 | Thu 5/11/26 | Thu 5/11/26 | 0d | 172d | 0ed | 0 | NA | NA | 23 January 2026 8:00 AM | 23 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
694 | 4771 | Yes | Auto Scheduled | Grass Verge | 2 d | Fixed Duration | 4 | 2d | 693 | 4 March 2026 8:00 AM | 5 March 2026 5:00 PM | Wed 4/03/26 | Thu 5/03/26 | Fri 6/11/26 | Mon 9/11/26 | 172d | 172d | 0ed | 0 | NA | NA | 27 January 2026 8:00 AM | 28 January 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.1.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
695 | 4772 | Yes | Auto Scheduled | LANDSCAPING - LEVEL 1 | 40 d | Fixed Duration | 3 | 40d |  | 22 April 2026 8:00 AM | 18 June 2026 5:00 PM | Wed 22/04/26 | Thu 18/06/26 | Wed 22/04/26 | Thu 18/06/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 March 2026 8:00 AM | 12 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
696 | 4740 | Yes | Auto Scheduled | Subgrade Preparation/ Cut to Grade | 3 d | Fixed Duration | 4 | 3d | 473 | 22 April 2026 8:00 AM | 24 April 2026 5:00 PM | Wed 22/04/26 | Fri 24/04/26 | Wed 22/04/26 | Fri 24/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 March 2026 8:00 AM | 17 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
697 | 4775 | Yes | Auto Scheduled | Internal Path Construction (FRP) - Beerwah Pde | 3 d | Fixed Duration | 4 | 3d | 696 | 27 April 2026 8:00 AM | 29 April 2026 5:00 PM | Mon 27/04/26 | Wed 29/04/26 | Mon 27/04/26 | Wed 29/04/26 | 0d | 0d | 0ed | 0 | NA | NA | 18 March 2026 8:00 AM | 20 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
698 | 4776 | Yes | Auto Scheduled | Internal Path Construction (FRP) - Phipps St | 3 d | Fixed Duration | 4 | 3d | 697 | 30 April 2026 8:00 AM | 5 May 2026 5:00 PM | Thu 30/04/26 | Tue 5/05/26 | Thu 30/04/26 | Tue 5/05/26 | 0d | 0d | 0ed | 0 | NA | NA | 23 March 2026 8:00 AM | 25 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
699 | 4777 | Yes | Auto Scheduled | Internal Path Construction (FRP) - Free St | 3 d | Fixed Duration | 4 | 3d | 698 | 6 May 2026 8:00 AM | 8 May 2026 5:00 PM | Wed 6/05/26 | Fri 8/05/26 | Wed 6/05/26 | Fri 8/05/26 | 0d | 0d | 0ed | 0 | NA | NA | 26 March 2026 8:00 AM | 30 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
700 | 4785 | Yes | Auto Scheduled | Bio-Retention Swale | 5 d | Fixed Duration | 4 | 5d | 699 | 11 May 2026 8:00 AM | 15 May 2026 5:00 PM | Mon 11/05/26 | Fri 15/05/26 | Mon 11/05/26 | Fri 15/05/26 | 0d | 0d | 0ed | 0 | NA | NA | 31 March 2026 8:00 AM | 8 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
701 | 4786 | Yes | Auto Scheduled | Hardscaping to BBQ Area | 5 d | Fixed Duration | 4 | 5d | 700 | 18 May 2026 8:00 AM | 22 May 2026 5:00 PM | Mon 18/05/26 | Fri 22/05/26 | Mon 18/05/26 | Fri 22/05/26 | 0d | 0d | 0ed | 0 | NA | NA | 9 April 2026 8:00 AM | 15 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
702 | 4778 | Yes | Auto Scheduled | External Pergola Structures | 5 d | Fixed Duration | 4 | 5d | 701 | 25 May 2026 8:00 AM | 29 May 2026 5:00 PM | Mon 25/05/26 | Fri 29/05/26 | Mon 25/05/26 | Fri 29/05/26 | 0d | 0d | 0ed | 0 | NA | NA | 16 April 2026 8:00 AM | 22 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
703 | 4787 | Yes | Auto Scheduled | Soil Importation | 2 d | Fixed Duration | 4 | 2d | 702 | 1 June 2026 8:00 AM | 2 June 2026 5:00 PM | Mon 1/06/26 | Tue 2/06/26 | Mon 1/06/26 | Tue 2/06/26 | 0d | 0d | 0ed | 0 | NA | NA | 23 April 2026 8:00 AM | 24 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
704 | 4779 | Yes | Auto Scheduled | Gates & Fences | 5 d | Fixed Duration | 4 | 5d | 703 | 3 June 2026 8:00 AM | 9 June 2026 5:00 PM | Wed 3/06/26 | Tue 9/06/26 | Wed 3/06/26 | Tue 9/06/26 | 0d | 0d | 0ed | 0 | NA | NA | 27 April 2026 8:00 AM | 1 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
705 | 4780 | Yes | Auto Scheduled | Irrigation System | 3 d | Fixed Duration | 4 | 3d | 704 | 10 June 2026 8:00 AM | 12 June 2026 5:00 PM | Wed 10/06/26 | Fri 12/06/26 | Wed 10/06/26 | Fri 12/06/26 | 0d | 0d | 0ed | 0 | NA | NA | 5 May 2026 8:00 AM | 7 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
706 | 4781 | Yes | Auto Scheduled | Planting & Mulch | 3 d | Fixed Duration | 4 | 3d | 705 | 15 June 2026 8:00 AM | 18 June 2026 5:00 PM | Mon 15/06/26 | Thu 18/06/26 | Mon 15/06/26 | Thu 18/06/26 | 0d | 0d | 0ed | 0 | NA | NA | 8 May 2026 8:00 AM | 12 May 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.2.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
707 | 4744 | Yes | Auto Scheduled | LANDSCAPING - LEVEL 2/ PODIUM | 35 d | Fixed Duration | 3 | 35d |  | 15 April 2026 8:00 AM | 3 June 2026 5:00 PM | Wed 15/04/26 | Wed 3/06/26 | Mon 21/09/26 | Mon 9/11/26 | 111d | 111d | 0ed | 0 | NA | NA | 6 March 2026 8:00 AM | 27 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
708 | 4789 | Yes | Auto Scheduled | Blockwork to Planter Boxes | 4 d | Fixed Duration | 4 | 4d | 470 | 15 April 2026 8:00 AM | 20 April 2026 5:00 PM | Wed 15/04/26 | Mon 20/04/26 | Mon 21/09/26 | Thu 24/09/26 | 0d | 111d | 0ed | 0 | NA | NA | 6 March 2026 8:00 AM | 11 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
709 | 4790 | Yes | Auto Scheduled | Render & Paint to Planterboxes | 5 d | Fixed Duration | 4 | 5d | 708 | 21 April 2026 8:00 AM | 27 April 2026 5:00 PM | Tue 21/04/26 | Mon 27/04/26 | Fri 25/09/26 | Thu 1/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 12 March 2026 8:00 AM | 18 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
710 | 4791 | Yes | Auto Scheduled | Waterproofing to Planterboxes | 3 d | Fixed Duration | 4 | 3d | 709 | 28 April 2026 8:00 AM | 30 April 2026 5:00 PM | Tue 28/04/26 | Thu 30/04/26 | Thu 5/11/26 | Mon 9/11/26 | 134d | 134d | 0ed | 0 | NA | NA | 19 March 2026 8:00 AM | 23 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
711 | 4792 | Yes | Auto Scheduled | Waterproofing Bandage to Construction Joints | 3 d | Fixed Duration | 4 | 3d | 709 | 28 April 2026 8:00 AM | 30 April 2026 5:00 PM | Tue 28/04/26 | Thu 30/04/26 | Fri 2/10/26 | Wed 7/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 19 March 2026 8:00 AM | 23 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
712 | 4793 | Yes | Auto Scheduled | Tiling & Floor Finishes | 5 d | Fixed Duration | 4 | 5d | 711 | 1 May 2026 8:00 AM | 8 May 2026 5:00 PM | Fri 1/05/26 | Fri 8/05/26 | Thu 8/10/26 | Wed 14/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 24 March 2026 8:00 AM | 30 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
713 | 4794 | Yes | Auto Scheduled | Western Pergola Structure | 5 d | Fixed Duration | 4 | 5d | 712 | 11 May 2026 8:00 AM | 15 May 2026 5:00 PM | Mon 11/05/26 | Fri 15/05/26 | Thu 15/10/26 | Wed 21/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 31 March 2026 8:00 AM | 8 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
714 | 4795 | Yes | Auto Scheduled | Gates, Fences & Screens | 3 d | Fixed Duration | 4 | 3d | 713 | 18 May 2026 8:00 AM | 20 May 2026 5:00 PM | Mon 18/05/26 | Wed 20/05/26 | Thu 22/10/26 | Mon 26/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 9 April 2026 8:00 AM | 13 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
715 | 4796 | Yes | Auto Scheduled | Seating & Hardscaping | 4 d | Fixed Duration | 4 | 4d | 714 | 21 May 2026 8:00 AM | 26 May 2026 5:00 PM | Thu 21/05/26 | Tue 26/05/26 | Tue 27/10/26 | Fri 30/10/26 | 0d | 111d | 0ed | 0 | NA | NA | 14 April 2026 8:00 AM | 17 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.8 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
716 | 4797 | Yes | Auto Scheduled | Soil Importation | 2 d | Fixed Duration | 4 | 2d | 715 | 27 May 2026 8:00 AM | 28 May 2026 5:00 PM | Wed 27/05/26 | Thu 28/05/26 | Mon 2/11/26 | Tue 3/11/26 | 0d | 111d | 0ed | 0 | NA | NA | 20 April 2026 8:00 AM | 21 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.9 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
717 | 4798 | Yes | Auto Scheduled | Irrigation System | 2 d | Fixed Duration | 4 | 2d | 716 | 29 May 2026 8:00 AM | 1 June 2026 5:00 PM | Fri 29/05/26 | Mon 1/06/26 | Wed 4/11/26 | Thu 5/11/26 | 0d | 111d | 0ed | 0 | NA | NA | 22 April 2026 8:00 AM | 23 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.10 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
718 | 4741 | Yes | Auto Scheduled | Planting & Mulch | 2 d | Fixed Duration | 4 | 2d | 717 | 2 June 2026 8:00 AM | 3 June 2026 5:00 PM | Tue 2/06/26 | Wed 3/06/26 | Fri 6/11/26 | Mon 9/11/26 | 10d | 111d | 0ed | 0 | NA | NA | 24 April 2026 8:00 AM | 27 April 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.6.3.11 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
719 | 4836 | Yes | Auto Scheduled | CAR PARK FIT OUT | 10 d | Fixed Duration | 2 | 10d |  | 15 April 2026 8:00 AM | 28 April 2026 5:00 PM | Wed 15/04/26 | Tue 28/04/26 | Tue 27/10/26 | Mon 9/11/26 | 136d | 136d | 0ed | 0 | NA | NA | 6 March 2026 8:00 AM | 19 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.7 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
720 | 4837 | Yes | Auto Scheduled | Slab Clean & Seal | 3 d | Fixed Duration | 3 | 3d | 470 | 15 April 2026 8:00 AM | 17 April 2026 5:00 PM | Wed 15/04/26 | Fri 17/04/26 | Tue 27/10/26 | Thu 29/10/26 | 0d | 136d | 0ed | 0 | NA | NA | 6 March 2026 8:00 AM | 10 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.7.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
721 | 4838 | Yes | Auto Scheduled | Line Marking | 2 d | Fixed Duration | 3 | 2d | 720 | 20 April 2026 8:00 AM | 21 April 2026 5:00 PM | Mon 20/04/26 | Tue 21/04/26 | Fri 30/10/26 | Mon 2/11/26 | 0d | 136d | 0ed | 0 | NA | NA | 11 March 2026 8:00 AM | 12 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.7.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
722 | 4839 | Yes | Auto Scheduled | Bike Rack & Handrail Installation | 2 d | Fixed Duration | 3 | 2d | 721 | 22 April 2026 8:00 AM | 23 April 2026 5:00 PM | Wed 22/04/26 | Thu 23/04/26 | Tue 3/11/26 | Wed 4/11/26 | 0d | 136d | 0ed | 0 | NA | NA | 13 March 2026 8:00 AM | 16 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.7.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
723 | 4840 | Yes | Auto Scheduled | Garage Door Installation | 3 d | Fixed Duration | 3 | 3d | 722 | 24 April 2026 8:00 AM | 28 April 2026 5:00 PM | Fri 24/04/26 | Tue 28/04/26 | Thu 5/11/26 | Mon 9/11/26 | 136d | 136d | 0ed | 0 | NA | NA | 17 March 2026 8:00 AM | 19 March 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Wed 5/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.7.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
724 | 4854 | Yes | Auto Scheduled | INCLEMENT WEATHER ALLOWANCE | 60 d | Fixed Duration | 2 | 60d |  | 19 June 2026 8:00 AM | 10 September 2026 5:00 PM | Fri 19/06/26 | Thu 10/09/26 | Fri 19/06/26 | Thu 10/09/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 May 2026 8:00 AM | 5 August 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 13/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.8 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
725 | 4853 | Yes | Auto Scheduled | Anticipated Wet Weather Days | 60 d | Fixed Duration | 3 | 60d | 706 | 19 June 2026 8:00 AM | 10 September 2026 5:00 PM | Fri 19/06/26 | Thu 10/09/26 | Fri 19/06/26 | Thu 10/09/26 | 0d | 0d | 0ed | 0 | NA | NA | 13 May 2026 8:00 AM | 5 August 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Thu 13/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.8.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
726 | 4743 | Yes | Auto Scheduled | PROJECT COMPLETION | 66 d | Fixed Duration | 2 | 66d |  | 7 August 2026 8:00 AM | 9 November 2026 5:00 PM | Fri 7/08/26 | Mon 9/11/26 | Fri 11/09/26 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | NA | NA | 2 July 2026 8:00 AM | 1 October 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9 | 500 | No | Yes | Yes | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
727 | 4745 | Yes | Auto Scheduled | Testing & Commissioning | 10 d | Fixed Duration | 3 | 10d | 728SF | 7 August 2026 8:00 AM | 21 August 2026 8:00 AM | Fri 7/08/26 | Fri 21/08/26 | Tue 27/10/26 | Mon 9/11/26 | 56d | 56d | 0ed | 0 | NA | NA | 2 July 2026 8:00 AM | 16 July 2026 8:00 AM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.1 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | Yes | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
728 | 4746 | Yes | Auto Scheduled | Defects | 15 d | Fixed Duration | 3 | 15d | 729SF | 21 August 2026 8:00 AM | 11 September 2026 8:00 AM | Fri 21/08/26 | Fri 11/09/26 | Tue 20/10/26 | Mon 9/11/26 | 0d | 41d | 0ed | 0 | NA | NA | 16 July 2026 8:00 AM | 6 August 2026 8:00 AM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.2 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
729 | 4856 | Yes | Auto Scheduled | Authority & Council Inspections & Sign Off | 10 d | Fixed Duration | 3 | 10d | 725 | 11 September 2026 8:00 AM | 24 September 2026 5:00 PM | Fri 11/09/26 | Thu 24/09/26 | Fri 11/09/26 | Thu 24/09/26 | 0d | 0d | 0ed | 0 | NA | NA | 6 August 2026 8:00 AM | 19 August 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 14/08/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.3 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
730 | 4860 | Yes | Auto Scheduled | PCA Completion Inspection | 1 d | Fixed Duration | 3 | 1d | 729FF | 24 September 2026 8:00 AM | 24 September 2026 5:00 PM | Thu 24/09/26 | Thu 24/09/26 | Thu 24/09/26 | Thu 24/09/26 | 0d | 0d | 0ed | 0 | NA | NA | 19 August 2026 8:00 AM | 19 August 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 14/08/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.4 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
731 | 4859 | Yes | Auto Scheduled | PCA Certification/ Completion Requirements | 10 d | Fixed Duration | 3 | 10d | 730 | 25 September 2026 8:00 AM | 9 October 2026 5:00 PM | Fri 25/09/26 | Fri 9/10/26 | Fri 25/09/26 | Fri 9/10/26 | 0d | 0d | 0ed | 0 | NA | NA | 20 August 2026 8:00 AM | 2 September 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 14/08/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.5 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
732 | 4868 | Yes | Auto Scheduled | Achievement of Occupation Certification | 1 d | Fixed Duration | 3 | 1d | 731 | 12 October 2026 8:00 AM | 12 October 2026 5:00 PM | Mon 12/10/26 | Mon 12/10/26 | Mon 12/10/26 | Mon 12/10/26 | 0d | 0d | 0ed | 0 | NA | NA | 3 September 2026 8:00 AM | 3 September 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 14/08/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.6 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
733 | 4857 | Yes | Auto Scheduled | Plan Sealing preparation, incl. Easements & Covenants | 20 d | Fixed Duration | 3 | 20d | 732 | 13 October 2026 8:00 AM | 9 November 2026 5:00 PM | Tue 13/10/26 | Mon 9/11/26 | Tue 13/10/26 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | NA | NA | 4 September 2026 8:00 AM | 1 October 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Mon 14/08/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.7 | 500 | No | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0
734 | 4750 | Yes | Auto Scheduled | Project Completion | 0 d | Fixed Duration | 3 | 0d | 733 | 9 November 2026 5:00 PM | 9 November 2026 5:00 PM | Mon 9/11/26 | Mon 9/11/26 | Mon 9/11/26 | Mon 9/11/26 | 0d | 0d | 0ed | 0 | NA | NA | 1 October 2026 5:00 PM | 1 October 2026 5:00 PM | As Soon As Possible | NA | NA | NA | Tue 4/07/23 | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 5.9.8 | 500 | Yes | No | No | [10 empty] | 0 | 0 | 0 | 0d | 0d | 0d | No | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0